## Slide 1
PMG 220
AI Project Management and Implementation Planning
Program Management Role-Based Track
Course level: applied/foundational • Prepared for Codex pairing with module JSON
AI Playbook and Toolkit for Public Health Departments

## Slide 2
PMG 220
Program Management Role-Based Track
Learning Objectives
Define the major phases of an AI implementation project.
Develop an AI project charter that includes scope, objectives, roles, risks, dependencies, and governance gates.
Identify implementation dependencies across data, systems, privacy, security, procurement, workflow, training, and evaluation.
Create a launch readiness checklist for an AI-supported workflow.
Plan transition from pilot to operations, including ownership, monitoring, maintenance, and sustainability.
Evidence expectation: AI project charter
Primary track: Program Management Role-Based Track
Codex key: pmg-220-ai-project-management-and-implementation-planning
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 3
PMG 220
Program Management Role-Based Track
Why This Matters for Public Health AI
Instructional focus: connect the technical idea to public health purpose, workflow risk, equity, accountability, and operational decision-making.
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 4
PMG 220
Program Management Role-Based Track
Core Concepts
Key terms
Project charter: A document that defines the purpose, scope, objectives, roles, governance, risks, and deliverables for a…
Governance gate: A decision point where a project must receive approval before moving to the next phase.
Launch readiness: The determination that a workflow, users, systems, documentation, training, and monitoring are ready for…
What learners should apply
Transition to operations: The handoff from implementation to routine management, monitoring, support, and continuous improvement.
Dependency: A task, decision, resource, or condition that must be completed or available for another activity to proceed.
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 5
PMG 220
Program Management Role-Based Track
Public Health Application
Example workflow
A public health agency plans to pilot an AI tool that drafts summaries of incoming case reports.
The project plan identifies governance approval, data access, system integration, validation, user training, SOP development, incident…
The project cannot launch simply because the tool works in a demonstration.
It must pass readiness checks showing that staff know how to review the output, errors can be reported, and the tool is monitored after launch.
AI-supported use
Identify what AI may support, what humans must decide, and how outputs should be reviewed.
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 6
PMG 220
Program Management Role-Based Track
Technical and Operational Deep Dive
AI project planning should begin with a charter that defines the use case and sets boundaries.
The charter should explain the public health problem, intended users, expected benefits, data involved, systems affected, approved use,…
It should also identify the sponsor, product owner, implementation lead, technical lead, privacy or legal contacts, security contact,…
Implementation should be organized into phases.
Early phases usually include discovery, intake, feasibility review, governance approval, and business analysis.
Middle phases include design, procurement or configuration, data access setup, integration, validation, workflow design, SOP development,…
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 7
PMG 220
Program Management Role-Based Track
Risks, Failure Modes, and Guardrails
Risks and failure modes include the following:
Pilots launching without governance approval or operational ownership.
Project plans overlooking data, privacy, security, workflow, or training dependencies.
Vendors controlling implementation timelines without agency readiness gates.
No transition plan from pilot to routine operations.
Guardrail pattern:
1. Name the risk
2. Define the review
3. Assign an owner
4. Monitor after launch
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 8
PMG 220
Program Management Role-Based Track
Practical Exercise and Resources
Create an AI project charter and implementation plan for one proposed AI-supported public health workflow.
Include project purpose, scope, objectives, roles, governance gates, milestones, workstreams, dependencies, risks, launch readiness criteria,…
Expected evidence
AI project charter
Implementation workplan
AI-specific risk log
Launch readiness checklist
References and resources
NIST Artificial Intelligence Risk Management Framework
NIST Generative AI Profile
CDC Public Health Data Strategy and Data Modernization resources
OWASP guidance for LLM application security
Agency policies for privacy, cybersecurity, records, procurement, accessibility, and…
Relevant public health program SOPs, data governance documentation, and implementation…
AI Playbook and Toolkit for Public Health Departments
PMG 220

## Slide 9
PMG 220
Program Management Role-Based Track
Knowledge Check Preview
1. What distinguishes AI project management from ordinary software implementation?
2. What is a governance gate?
3. Which item belongs in an AI project charter?
4. Why is transition to operations important?
5. What is strong completion evidence?
For learner-facing slides, hide correct answers. For facilitator notes or template ingestion, use the JSON source as the authoritative answer key.
AI Playbook and Toolkit for Public Health Departments
PMG 220