## Slide 1
EXE 420
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
Notes: EXE 420 AI Investment Strategy and Business Case Review AI investments compete with many other public health priorities. Leaders need a disciplined way to decide when AI is worth funding, what costs must be considered, and how benefits will be measured. A business case review helps agencies avoid buying tools that are impressive in demonstrations but weak in operational value, sustainability, interoperability, or public health impact. This module teaches leaders to evaluate AI investments across cost, value, readiness, risk, staffing, procurement, lifecycle support, and sustainability. The business case should not focus only on software price. It should include data preparation, implementation, integration, training, governance, validation, monitoring, maintenance, vendor management, cybersecurity, accessibility, and eventual replacement or retirement.

## Slide 2
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
What this module helps you do
AI investments compete with many other public health priorities.
Leaders need a disciplined way to decide when AI is worth funding, what costs must be considered, and how benefits will be measured.
A business case review helps agencies avoid buying tools that are impressive in demonstrations but weak in operational value, sustainability,.
This module teaches leaders to evaluate AI investments across cost, value, readiness, risk, staffing, procurement, lifecycle support, and.
Module details
Level: advanced/leadership
Primary track: Public Health Executive Leadership Track
Appears in tracks: governance-security
Learning approach
Review the core ideas, complete the practical exercise, check your understanding, and use the related plays and tools to apply the lesson.
Notes: Module Context Level: advanced/leadership Primary track: Public Health Executive Leadership Track Appears in tracks: governance-security AI investments compete with many other public health priorities. Leaders need a disciplined way to decide when AI is worth funding, what costs must be considered, and how benefits will be measured. A business case review helps agencies avoid buying tools that are impressive in demonstrations but weak in operational value, sustainability, interoperability, or public health impact. This module teaches leaders to evaluate AI investments across cost, value, readiness, risk, staffing, procurement, lifecycle support, and sustainability. The business case should not focus only on software price. It should include data preparation, implementation, integration, training, governance, validation, monitoring, maintenance, vendor management, cybersecurity, accessibility, and eventual replacement or retirement.

## Slide 3
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
How this module connects to the playbook
Play 11: Build and Deploy AI Solutions - This lesson informs Play 11 by helping learners connect the lesson topic to build and deploy.
Play 2: Readiness Assessment - This lesson informs Play 2 by helping learners connect the lesson topic to readiness assessment work.
Play 3: Establish AI Governance - This lesson informs Play 3 by helping learners connect the lesson topic to establish ai governance.
Play 1: Vision & Guardrails - This lesson informs Play 1 by helping learners connect the lesson topic to vision & guardrails work in.
Apply the lesson
Use the related plays to identify decisions, participants, timing, approvals, and documentation needed for responsible implementation.
Keep in mind
The playbook connection helps turn training into agency work, not just individual knowledge.
Notes: Related Playbook Plays Play 11: Build and Deploy AI Solutions - This lesson informs Play 11 by helping learners connect the lesson topic to build and deploy ai solutions work in the AI Playbook. Play 2: Readiness Assessment - This lesson informs Play 2 by helping learners connect the lesson topic to readiness assessment work in the AI Playbook sequence. Play 3: Establish AI Governance - This lesson informs Play 3 by helping learners connect the lesson topic to establish ai governance work in the AI Playbook sequence. Play 1: Vision & Guardrails - This lesson informs Play 1 by helping learners connect the lesson topic to vision & guardrails work in the AI Playbook sequence.

## Slide 4
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
Related toolkit resources
Tool 4: AI Policy Landscape Scan (Worksheet) - Use AI Policy Landscape Scan to translate this lesson into a documented public health.
Tool 5: AI Environmental and Resource Impact Review (Checklist) - Use this tool to complete or strengthen the practical exercise for.
Tool 6: Human-Centered AI Decision Rule Checklist (Checklist) - Use Human-Centered AI Decision Rule Checklist to translate this.
Tool 8: AI Project Charter (Planning) - Use AI Project Charter to translate this lesson into a documented public health AI planning,.
Tool 9: Data Quality Assessment Checklist (Checklist) - Use this tool to complete or strengthen the practical exercise for the module.
Use the tools
Use linked tools when your department needs a structured worksheet, template, checklist, review process, or documentation artifact.
Avoid duplication
If your department already has a strong equivalent tool, adapt or use the existing process instead of recreating it.
Notes: Related Toolkit Resources Tool 4: AI Policy Landscape Scan (Worksheet) - Use AI Policy Landscape Scan to translate this lesson into a documented public health AI planning, governance, implementation,. Tool 5: AI Environmental and Resource Impact Review (Checklist) - Use this tool to complete or strengthen the practical exercise for the module using fictional, de-identified, or generalized. Tool 6: Human-Centered AI Decision Rule Checklist (Checklist) - Use Human-Centered AI Decision Rule Checklist to translate this lesson into a documented public health AI planning, governance,. Tool 8: AI Project Charter (Planning) - Use AI Project Charter to translate this lesson into a documented public health AI planning, governance, implementation, or. Tool 9: Data Quality Assessment Checklist (Checklist) - Use this tool to complete or strengthen the practical exercise for the module using fictional, de-identified, or generalized. Tool 10: Tiered Data Classification for AI Use (Worksheet) - Use Tiered Data Classification for AI Use to translate this lesson into a documented public health AI planning, governance,.

## Slide 5
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
1
Learning Objectives
Identify the full cost components of AI implementation and operations.
Evaluate expected benefits in terms of public health value, workflow improvement, equity, quality, timeliness, and staff burden.
Distinguish between a vendor demonstration and a credible business case.
Develop business case questions for AI procurement or internal development.
Key idea
Identify the full cost components of AI implementation and operations.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Learning Objectives Identify the full cost components of AI implementation and operations. Evaluate expected benefits in terms of public health value, workflow improvement, equity, quality, timeliness, and staff burden. Distinguish between a vendor demonstration and a credible business case. Develop business case questions for AI procurement or internal development. Produce an AI business case review worksheet.

## Slide 6
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
2
Module Overview
AI investments compete with many other public health priorities.
Leaders need a disciplined way to decide when AI is worth funding, what costs must be considered, and how benefits will be.
A business case review helps agencies avoid buying tools that are impressive in demonstrations but weak in operational.
This module teaches leaders to evaluate AI investments across cost, value, readiness, risk, staffing, procurement,.
Key idea
AI investments compete with many other public health priorities.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Module Overview AI investments compete with many other public health priorities. Leaders need a disciplined way to decide when AI is worth funding, what costs must be considered, and how benefits will be measured. A business case review helps agencies avoid buying tools that are impressive in demonstrations but weak in operational value, sustainability, interoperability, or public health impact. This module teaches leaders to evaluate AI investments across cost, value, readiness, risk, staffing, procurement, lifecycle support, and sustainability. The business case should not focus only on software price. It should include data preparation, implementation, integration, training, governance, validation, monitoring, maintenance, vendor management, cybersecurity, accessibility, and eventual replacement or retirement.

## Slide 7
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
3
Jurisdiction and Agency Policy Note
This national-level module is intended for training and planning purposes.
It does not replace legal, privacy, procurement, civil rights, records, or agency policy review.
Learners should confirm applicable requirements in their own jurisdiction and organization before implementing AI-supported.
Key idea
This national-level module is intended for training and planning purposes.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Jurisdiction and Agency Policy Note This national-level module is intended for training and planning purposes. It does not replace legal, privacy, procurement, civil rights, records, or agency policy review. Learners should confirm applicable requirements in their own jurisdiction and organization before implementing AI-supported workflows.

## Slide 8
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
4
Why This Topic Matters for Public Health AI
Public health agencies often face short-term funding cycles and urgent operational needs.
AI products may be marketed as quick solutions, but the true cost of responsible implementation is broader than.
Agencies may need to update data pipelines, configure security controls, develop validation plans, train staff, write.
A strong business case also protects mission focus.
Key idea
Public health agencies often face short-term funding cycles and urgent operational needs.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Why This Topic Matters for Public Health AI Public health agencies often face short-term funding cycles and urgent operational needs. AI products may be marketed as quick solutions, but the true cost of responsible implementation is broader than subscription fees. Agencies may need to update data pipelines, configure security controls, develop validation plans, train staff, write policies, monitor performance, and manage vendor relationships. A strong business case also protects mission focus. AI should not be funded because it is novel. It should be funded when it addresses a meaningful public health problem, fits agency capacity, can be governed responsibly, and can produce measurable value. Business case review helps leaders compare AI investments with non-AI alternatives, such as workflow redesign, staffing changes, data quality improvements, or simpler automation.

## Slide 9
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
5
Public Health Example
A vendor offers an AI tool that promises to reduce disease investigator workload by summarizing case reports.
The annual license appears affordable, but the agency must also pay for integration with the surveillance system, security.
If those costs are not considered, leadership may underestimate the investment required.
A business case review asks whether the tool will meaningfully reduce burden, improve timeliness, maintain quality, and fit.
Key idea
A vendor offers an AI tool that promises to reduce disease investigator workload by summarizing case reports.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Public Health Example A vendor offers an AI tool that promises to reduce disease investigator workload by summarizing case reports. The annual license appears affordable, but the agency must also pay for integration with the surveillance system, security review, staff training, validation, legal review, vendor support, monitoring dashboards, and staff time for governance. If those costs are not considered, leadership may underestimate the investment required. A business case review asks whether the tool will meaningfully reduce burden, improve timeliness, maintain quality, and fit the agency's workflow. It also asks whether a simpler approach, such as better case report templates or workflow redesign, would solve the problem at lower cost and risk. The review does not assume AI is the answer; it tests whether AI is the right answer.

## Slide 10
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
6
Technical and Governance Deep Dive
An AI business case should begin with a problem statement.
The problem should be operational and measurable, such as delayed case review, inconsistent public response drafting, high.
A vague desire to 'use AI' is not a sufficient problem statement.
The business case should connect the proposed AI use to a real public health need.
Key idea
An AI business case should begin with a problem statement.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Technical and Governance Deep Dive An AI business case should begin with a problem statement. The problem should be operational and measurable, such as delayed case review, inconsistent public response drafting, high manual data cleanup burden, or inability to search internal guidance efficiently. A vague desire to 'use AI' is not a sufficient problem statement. The business case should connect the proposed AI use to a real public health need. The review should compare alternatives. Options may include doing nothing, improving workflow, improving data quality, using rules-based automation, procuring a vendor product, developing an internal tool, or joining a shared service. Each option should be assessed for benefit, cost, risk, time, staffing, sustainability, and governance burden. This comparison prevents AI from becoming the default answer to every operational problem. Success measures should be defined before funding. Measures might include reduced processing time, improved completeness, fewer manual touches, better routing accuracy, staff satisfaction, fewer errors, improved language access, or reduced backlog. Measures should also include safety and equity indicators. A tool that saves time but increases error rates, widens disparities, or erodes public trust should not be considered successful.

## Slide 11
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
7
Risks, Failure Modes, and Guardrails
One risk is hidden cost.
Agencies may purchase an AI tool without funding integration, monitoring, validation, staff training, or ongoing support.
A guardrail is to require total cost of ownership in every business case.
Another risk is benefits inflation.
Key idea
One risk is hidden cost.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Risks, Failure Modes, and Guardrails One risk is hidden cost. Agencies may purchase an AI tool without funding integration, monitoring, validation, staff training, or ongoing support. A guardrail is to require total cost of ownership in every business case. Another risk is benefits inflation. Vendors or project champions may overstate time savings or accuracy without local evidence. A guardrail is to require pilot success criteria and benefits realization review before scaling.

## Slide 12
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
8
Application to AI-Supported Workflows
Generative AI business cases should include review time, source verification, and records considerations.
Predictive analytics business cases should include validation data, subgroup testing, and monitoring costs.
Agentic AI business cases should include security architecture, approval workflows, rollback, logging, and incident response.
Cost and value must reflect responsible use.
Key idea
Generative AI business cases should include review time, source verification, and records considerations.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Application to AI-Supported Workflows Generative AI business cases should include review time, source verification, and records considerations. Predictive analytics business cases should include validation data, subgroup testing, and monitoring costs. Agentic AI business cases should include security architecture, approval workflows, rollback, logging, and incident response. Cost and value must reflect responsible use.

## Slide 13
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
9
Reflection Questions
Which current or proposed AI use case in your agency raises this leadership or governance issue most clearly?
Who currently has authority to make decisions about this issue, and is that authority documented?
What evidence would governance or leadership need before approving the use case?
Key idea
Which current or proposed AI use case in your agency raises this leadership or governance issue most clearly?
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Reflection Questions Which current or proposed AI use case in your agency raises this leadership or governance issue most clearly? Who currently has authority to make decisions about this issue, and is that authority documented? What evidence would governance or leadership need before approving the use case?

## Slide 14
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
Reflection Questions Continued
Which staff, partners, or communities would be affected if this issue were handled poorly?
What policy, process, or artifact should be created or updated after this module?
Key idea
Which staff, partners, or communities would be affected if this issue were handled poorly?
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Reflection Questions Which staff, partners, or communities would be affected if this issue were handled poorly? What policy, process, or artifact should be created or updated after this module?

## Slide 15
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
10
Practical Exercise
Complete an AI business case review worksheet for one proposed investment.
Include problem, alternatives, expected benefits, total cost of ownership, risk, equity considerations, implementation.
Key idea
Complete an AI business case review worksheet for one proposed investment.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Practical Exercise Complete an AI business case review worksheet for one proposed investment. Include problem, alternatives, expected benefits, total cost of ownership, risk, equity considerations, implementation needs, and success measures.

## Slide 16
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
11
Before You Begin
Choose a real or realistic public health AI use case.
Document assumptions, unresolved questions, and which agency roles would need to review the artifact before it is adopted.
The exercise should produce a work product that could support governance review, leadership discussion, implementation.
Key idea
Choose a real or realistic public health AI use case.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Before You Begin Choose a real or realistic public health AI use case. Document assumptions, unresolved questions, and which agency roles would need to review the artifact before it is adopted. The exercise should produce a work product that could support governance review, leadership discussion, implementation planning, or policy development.

## Slide 17
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
12
Expected Artifact or Evidence
AI business case worksheet; total cost of ownership estimate; benefits realization plan; alternatives analysis.
Key idea
AI business case worksheet; total cost of ownership estimate; benefits realization plan; alternatives analysis.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Expected Artifact or Evidence AI business case worksheet; total cost of ownership estimate; benefits realization plan; alternatives analysis.

## Slide 18
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
13
Expected Assignment
AI business case worksheet; total cost of ownership estimate; benefits realization plan; alternatives analysis.
Key idea
AI business case worksheet; total cost of ownership estimate; benefits realization plan; alternatives analysis.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Expected Assignment AI business case worksheet; total cost of ownership estimate; benefits realization plan; alternatives analysis.

## Slide 19
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
14
Knowledge Check
1. What is the strongest reason this module topic belongs in AI leadership and governance training?
2. Which practice best supports accountable public health AI governance?
3. When should an AI use case be escalated for leadership or governance review?
4. What is weak evidence of completion for a leadership and governance module?
Key idea
1. What is the strongest reason this module topic belongs in AI leadership and governance training?
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: Knowledge Check 1. What is the strongest reason this module topic belongs in AI leadership and governance training? 2. Which practice best supports accountable public health AI governance? 3. When should an AI use case be escalated for leadership or governance review? 4. What is weak evidence of completion for a leadership and governance module? 5. What should leaders do when an AI use case has meaningful benefits but unresolved risks?

## Slide 20
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
15
References and Resources
NIST Artificial Intelligence Risk Management Framework (AI RMF 1.0): https://www.nist.gov/itl/ai-risk-management-framework
NIST Generative AI Profile:.
NIST Privacy Framework
CDC Public Health Data Strategy and Data Modernization resources:.
Key idea
NIST Artificial Intelligence Risk Management Framework (AI RMF 1.0): https://www.nist.gov/itl/ai-risk-management-framework
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: References and Resources NIST Artificial Intelligence Risk Management Framework (AI RMF 1.0): https://www.nist.gov/itl/ai-risk-management-framework NIST Generative AI Profile: https://www.nist.gov/publications/artificial-intelligence-risk-management-framework-generative-artificial-intelligence NIST Privacy Framework CDC Public Health Data Strategy and Data Modernization resources: https://www.cdc.gov/public-health-data-strategy/php/about/index.html WHO Ethics and Governance of Artificial Intelligence for Health: https://www.who.int/publications/i/item/9789240029200

## Slide 21
AI Investment Strategy and Business Case Review
AI Playbook and Toolkit for Public Health Departments
© Paula Soper
References and Resources Continued
OMB Memorandum M-24-10 on federal AI governance, risk management, and innovation, where relevant to public-sector governance.
Agency strategic plans, procurement policies, privacy policies, cybersecurity policies, records policies, and equity plans
Key idea
OMB Memorandum M-24-10 on federal AI governance, risk management, and innovation, where relevant to public-sector governance.
Use this for
Connect the concept to public health decisions, safeguards, documentation, or implementation work.
Notes: References and Resources OMB Memorandum M-24-10 on federal AI governance, risk management, and innovation, where relevant to public-sector governance models Agency strategic plans, procurement policies, privacy policies, cybersecurity policies, records policies, and equity plans