## Slide 1
PMG 220
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
1
Notes: PMG 220 AI Project Management and Implementation Planning AI projects require disciplined implementation planning because they combine technology, data, governance, workflow change, training, validation, procurement, security, and evaluation. A project that appears small, such as adding an AI summarization tool, may still require data access decisions, system integration, human review design, communications planning, and post-launch monitoring. Public health agencies need project management methods that account for these dependencies before implementation begins. This module teaches program managers, product owners, implementation leads, and technical staff how to structure AI initiatives from concept through deployment and operations. The focus is on practical project controls: charters, milestones, governance gates, risk logs, stakeholder engagement, testing, training, launch readiness, and transition to operations. Strong AI project management helps agencies avoid pilots that never scale, tools that are deployed without ownership, and vendor-led projects that outpace governance or public health readiness. It also helps leadership understand what resources are needed for safe and sustainable implementation.

## Slide 2
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
2
What this module helps you do
AI projects require disciplined implementation planning because they combine technology, data, governance,.
A project that appears small, such as adding an AI summarization tool, may still require data access decisions,.
Public health agencies need project management methods that account for these dependencies before implementation.
Module details
Level: applied/foundational
Primary track: Program Management Role-Based Track
Appears in tracks: program-management, operations-and-data-quality, technical-architecture, public-health-executive-leadership
Learn
Apply
Document
Notes: Module Context Level: applied/foundational Primary track: Program Management Role-Based Track Appears in tracks: program-management, operations-and-data-quality, technical-architecture, public-health-executive-leadership AI projects require disciplined implementation planning because they combine technology, data, governance, workflow change, training, validation, procurement, security, and evaluation. A project that appears small, such as adding an AI summarization tool, may still require data access decisions, system integration, human review design, communications planning, and post-launch monitoring. Public health agencies need project management methods that account for these dependencies before implementation begins. This module teaches program managers, product owners, implementation leads, and technical staff how to structure AI initiatives from concept through deployment and operations. The focus is on practical project controls: charters, milestones, governance gates, risk logs, stakeholder engagement, testing, training, launch readiness, and transition to operations. Strong AI project management helps agencies avoid pilots that never scale, tools that are deployed without ownership, and vendor-led projects that outpace governance or public health readiness. It also helps leadership understand what resources are needed for safe and sustainable implementation.

## Slide 3
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
3
How this module connects to the playbook
Play 11: Build and Deploy AI Solutions - This lesson informs Play 11 by helping learners connect the lesson.
Play 2: Readiness Assessment - This lesson informs Play 2 by helping learners connect the lesson topic to.
Play 1: Vision & Guardrails - This lesson informs Play 1 by helping learners connect the lesson topic to.
Play 7: Prioritize Use Cases - This lesson informs Play 7 by helping learners connect the lesson topic to.
Apply the lesson
Use the related plays to identify decisions, participants, timing, approvals, and documentation needed for responsible implementation.
Lesson
Plays
Action
Notes: Related Playbook Plays Play 11: Build and Deploy AI Solutions - This lesson informs Play 11 by helping learners connect the lesson topic to build and deploy ai solutions work in the AI Playbook. Play 2: Readiness Assessment - This lesson informs Play 2 by helping learners connect the lesson topic to readiness assessment work in the AI Playbook sequence. Play 1: Vision & Guardrails - This lesson informs Play 1 by helping learners connect the lesson topic to vision & guardrails work in the AI Playbook sequence. Play 7: Prioritize Use Cases - This lesson informs Play 7 by helping learners connect the lesson topic to prioritize use cases work in the AI Playbook sequence.

## Slide 4
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
4
Related toolkit resources
Tool 4: AI Policy Landscape Scan (Worksheet) - Use AI Policy Landscape Scan to translate this lesson into a.
Tool 5: AI Environmental and Resource Impact Review (Checklist) - Use this tool to complete or strengthen.
Tool 6: Human-Centered AI Decision Rule Checklist (Checklist) - Use Human-Centered AI Decision Rule.
Tool 8: AI Project Charter (Planning) - Use this tool to complete or strengthen the practical exercise for.
Use the tools
Use linked tools when your department needs a structured worksheet, template, checklist, review process, or documentation artifact.
Concept
Tool
Artifact
Notes: Related Toolkit Resources Tool 4: AI Policy Landscape Scan (Worksheet) - Use AI Policy Landscape Scan to translate this lesson into a documented public health AI planning, governance, implementation,. Tool 5: AI Environmental and Resource Impact Review (Checklist) - Use this tool to complete or strengthen the practical exercise for the module using fictional, de-identified, or generalized. Tool 6: Human-Centered AI Decision Rule Checklist (Checklist) - Use Human-Centered AI Decision Rule Checklist to translate this lesson into a documented public health AI planning, governance,. Tool 8: AI Project Charter (Planning) - Use this tool to complete or strengthen the practical exercise for the module using fictional, de-identified, or generalized. Tool 9: Data Quality Assessment Checklist (Checklist) - Use this tool to complete or strengthen the practical exercise for the module using fictional, de-identified, or generalized. Tool 10: Tiered Data Classification for AI Use (Worksheet) - Use this tool to complete or strengthen the practical exercise for the module using fictional, de-identified, or generalized.

## Slide 5
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
5
Learning Objectives
Define the major phases of an AI implementation project.
Develop an AI project charter that includes scope, objectives, roles, risks, dependencies, and.
Identify implementation dependencies across data, systems, privacy, security, procurement, workflow,.
Implementation cue
Define the major phases of an AI implementation project.
Plan
Do
Review
Dependencies visible
Next action
Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.
Notes: Learning Objectives Define the major phases of an AI implementation project. Develop an AI project charter that includes scope, objectives, roles, risks, dependencies, and governance gates. Identify implementation dependencies across data, systems, privacy, security, procurement, workflow, training, and evaluation. Create a launch readiness checklist for an AI-supported workflow. Plan transition from pilot to operations, including ownership, monitoring, maintenance, and sustainability. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 6
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
6
Module Overview
AI projects require disciplined implementation planning because they combine technology, data,.
A project that appears small, such as adding an AI summarization tool, may still require data access.
Public health agencies need project management methods that account for these dependencies before.
Implementation cue
AI projects require disciplined implementation planning because they combine technology, data,.
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Module Overview AI projects require disciplined implementation planning because they combine technology, data, governance, workflow change, training, validation, procurement, security, and evaluation. A project that appears small, such as adding an AI summarization tool, may still require data access decisions, system integration, human review design, communications planning, and post-launch monitoring. Public health agencies need project management methods that account for these dependencies before implementation begins. This module teaches program managers, product owners, implementation leads, and technical staff how to structure AI initiatives from concept through deployment and operations. The focus is on practical project controls: charters, milestones, governance gates, risk logs, stakeholder engagement, testing, training, launch readiness, and transition to operations. Strong AI project management helps agencies avoid pilots that never scale, tools that are deployed without ownership, and vendor-led projects that outpace governance or public health readiness. It also helps leadership understand what resources are needed for safe and sustainable implementation. Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 7
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
7
Public Health Example
A public health agency plans to pilot an AI tool that drafts summaries of incoming case reports.
The project plan identifies governance approval, data access, system integration, validation, user.
The project cannot launch simply because the tool works in a demonstration.
Implementation cue
A public health agency plans to pilot an AI tool that drafts summaries of incoming case reports.
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Public Health Example A public health agency plans to pilot an AI tool that drafts summaries of incoming case reports. The project plan identifies governance approval, data access, system integration, validation, user training, SOP development, incident response, and monitoring as required workstreams. The project cannot launch simply because the tool works in a demonstration. It must pass readiness checks showing that staff know how to review the output, errors can be reported, and the tool is monitored after launch. Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 8
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
8
Topic Deep Dive
AI project planning should begin with a charter that defines the use case and sets boundaries.
The charter should explain the public health problem, intended users, expected benefits, data involved,.
It should also identify the sponsor, product owner, implementation lead, technical lead, privacy or.
Implementation cue
AI project planning should begin with a charter that defines the use case and sets boundaries.
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Topic Deep Dive AI project planning should begin with a charter that defines the use case and sets boundaries. The charter should explain the public health problem, intended users, expected benefits, data involved, systems affected, approved use, prohibited use, and success measures. It should also identify the sponsor, product owner, implementation lead, technical lead, privacy or legal contacts, security contact, evaluation lead, and operational owner. Implementation should be organized into phases. Early phases usually include discovery, intake, feasibility review, governance approval, and business analysis. Middle phases include design, procurement or configuration, data access setup, integration, validation, workflow design, SOP development, and training. Later phases include user acceptance testing, launch readiness review, deployment, monitoring, and transition to operations. Governance gates should be placed between phases to prevent premature launch. AI project risk management should be more detailed than a general project risk log. Risks may include poor data quality, unavailable interfaces, unclear authority, model performance problems, vendor delays, privacy concerns, security vulnerabilities, staff resistance, workflow burden, community trust concerns, and sustainability gaps. Each risk should have an owner, mitigation plan, status, and escalation threshold. Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 9
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
9
Topic Deep Dive Continued
Transition to operations is often neglected.
A pilot may show promise, but routine use requires support, monitoring, maintenance, budget, staff.
The project plan should define when the implementation team ends and who becomes responsible for.
Implementation cue
Transition to operations is often neglected.
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Topic Deep Dive Transition to operations is often neglected. A pilot may show promise, but routine use requires support, monitoring, maintenance, budget, staff training, user feedback, incident response, and periodic review. The project plan should define when the implementation team ends and who becomes responsible for ongoing operations. Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 10
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
10
Risks, Failure Modes, and Guardrails
Risks and failure modes include the following:
Pilots launching without governance approval or operational ownership.
Project plans overlooking data, privacy, security, workflow, or training dependencies.
Risk check
Risks and failure modes include the following:
Risk
Human review
Safeguard to plan
Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.
Notes: Risks, Failure Modes, and Guardrails Risks and failure modes include the following: Pilots launching without governance approval or operational ownership. Project plans overlooking data, privacy, security, workflow, or training dependencies. Application guidance: Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.

## Slide 11
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
11
Risks, Failure Modes, and Guardrails Continued
Vendors controlling implementation timelines without agency readiness gates.
No transition plan from pilot to routine operations.
Success measured only by deployment rather than public health value and safe use.
Risk check
Vendors controlling implementation timelines without agency readiness gates.
Risk
Human review
Safeguard to plan
Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.
Notes: Risks, Failure Modes, and Guardrails Vendors controlling implementation timelines without agency readiness gates. No transition plan from pilot to routine operations. Success measured only by deployment rather than public health value and safe use. Application guidance: Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.

## Slide 12
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
12
Risks, Failure Modes, and Guardrails Continued
Recommended guardrails include the following:
Use an AI-specific project charter and risk log.
Define governance gates before implementation begins.
Risk check
Recommended guardrails include the following:
Risk
Human review
Safeguard to plan
Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.
Notes: Risks, Failure Modes, and Guardrails Recommended guardrails include the following: Use an AI-specific project charter and risk log. Define governance gates before implementation begins. Application guidance: Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.

## Slide 13
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
13
Risks, Failure Modes, and Guardrails Continued
Create separate workstreams for data, technology, governance, workflow, training, validation, and.
Require launch readiness review before deployment.
Document transition to operations and sustainability responsibilities.
Risk check
Create separate workstreams for data, technology, governance, workflow, training, validation, and.
Risk
Human review
Safeguard to plan
Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.
Notes: Risks, Failure Modes, and Guardrails Create separate workstreams for data, technology, governance, workflow, training, validation, and evaluation. Require launch readiness review before deployment. Document transition to operations and sustainability responsibilities. Application guidance: Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.

## Slide 14
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
14
Reflection Questions
Where does this topic appear in your agency, program, or workflow?
Which staff roles would need to understand or apply this concept before AI use is approved?
What could go wrong if this topic is not addressed before implementation?
Implementation cue
Where does this topic appear in your agency, program, or workflow?
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Reflection Questions Where does this topic appear in your agency, program, or workflow? Which staff roles would need to understand or apply this concept before AI use is approved? What could go wrong if this topic is not addressed before implementation? Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 15
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
15
Reflection Questions Continued
What evidence would governance, leadership, or operations staff need before moving forward?
Which policy, data, equity, privacy, security, or workflow questions remain unresolved?
Implementation cue
What evidence would governance, leadership, or operations staff need before moving forward?
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Reflection Questions What evidence would governance, leadership, or operations staff need before moving forward? Which policy, data, equity, privacy, security, or workflow questions remain unresolved? Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 16
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
16
Practical Exercise
Create an AI project charter and implementation plan for one proposed AI-supported public health.
Include project purpose, scope, objectives, roles, governance gates, milestones, workstreams,.
Implementation cue
Create an AI project charter and implementation plan for one proposed AI-supported public health.
Plan
Do
Review
Dependencies visible
Next action
Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.
Notes: Practical Exercise Create an AI project charter and implementation plan for one proposed AI-supported public health workflow. Include project purpose, scope, objectives, roles, governance gates, milestones, workstreams, dependencies, risks, launch readiness criteria, and transition-to-operations plan. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 17
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
17
Expected Artifact or Evidence
AI project charter
Implementation workplan
AI-specific risk log
Implementation cue
AI project charter
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Expected Artifact or Evidence AI project charter Implementation workplan AI-specific risk log Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 18
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
18
Expected Artifact or Evidence Continued
Launch readiness checklist
Transition-to-operations plan
Implementation cue
Launch readiness checklist
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: Expected Artifact or Evidence Launch readiness checklist Transition-to-operations plan Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 19
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
19
Expected Assignment
AI project charter
Implementation workplan
AI-specific risk log
Implementation cue
AI project charter
Plan
Do
Review
Dependencies visible
Next action
Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.
Notes: Expected Assignment AI project charter Implementation workplan AI-specific risk log Launch readiness checklist Transition-to-operations plan Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 20
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
20
Knowledge Check
1. What distinguishes AI project management from ordinary software implementation?
2. What is a governance gate?
3. Which item belongs in an AI project charter?
Implementation cue
1. What distinguishes AI project management from ordinary software implementation?
Plan
Do
Review
Dependencies visible
Next action
Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.
Notes: Knowledge Check 1. What distinguishes AI project management from ordinary software implementation? 2. What is a governance gate? 3. Which item belongs in an AI project charter? 4. Why is transition to operations important? 5. What is strong completion evidence? Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 21
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
21
References and Resources
NIST Artificial Intelligence Risk Management Framework:.
NIST Generative AI Profile:.
CDC Public Health Data Strategy and Data Modernization resources:.
Implementation cue
NIST Artificial Intelligence Risk Management Framework:.
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: References and Resources NIST Artificial Intelligence Risk Management Framework: https://www.nist.gov/itl/ai-risk-management-framework NIST Generative AI Profile: https://www.nist.gov/publications/artificial-intelligence-risk-management-framework-generative-artificial-intelligence CDC Public Health Data Strategy and Data Modernization resources: https://www.cdc.gov/public-health-data-strategy/php/about/index.html OWASP guidance for LLM application security Agency policies for privacy, cybersecurity, records, procurement, accessibility, and public communications Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 22
AI Project Management and Implementation Planning
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
22
References and Resources Continued
Relevant public health program SOPs, data governance documentation, and implementation plans
Implementation cue
Relevant public health program SOPs, data governance documentation, and implementation plans
Plan
Do
Review
Dependencies visible
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.
Notes: References and Resources Relevant public health program SOPs, data governance documentation, and implementation plans Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.