## Slide 1
PGM 100
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
1
Notes: PGM 100 Managing AI Projects in Public Health Programs This module introduces program managers to the practical responsibilities involved in managing AI projects in public health settings. It focuses on problem definition, governance intake, stakeholder coordination, approved-tool awareness, workflow fit, risk review, implementation planning, and monitoring. It is written for national use, so it does not assume a specific agency tool, procurement process, or governance structure.

## Slide 2
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
2
What this module helps you do
• This module introduces program managers to the practical responsibilities.
• It focuses on problem definition, governance intake, stakeholder.
• It is written for national use, so it does not assume a specific agency.
Module details
Level: introductory/applied Primary track: Program Management Track Appears in.
Learning sequence
Read the module for shared vocabulary and context.
Complete the practical exercise to apply the.
Use the notes and references for deeper review.
Notes: Module Context Level: introductory/applied Primary track: Program Management Track Appears in tracks: program-management This module introduces program managers to the practical responsibilities involved in managing AI projects in public health settings. It focuses on problem definition, governance intake, stakeholder coordination, approved-tool awareness, workflow fit, risk review, implementation planning, and monitoring. It is written for national use, so it does not assume a specific agency tool, procurement process, or governance structure.

## Slide 3
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
3
Learning Objectives
• Describe the program manager role in responsible AI project planning and.
• Distinguish between tool-first ideas and workflow-based public health use.
• Identify the governance, data, workforce, vendor, equity, privacy, and.
Practice focus
Describe the program manager role in responsible AI project planning and.
Concept checkpoints
Identify the governance, data, workforce, vendor,.
Create a project framing brief for a proposed.
What to produce
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Learning Objectives Describe the program manager role in responsible AI project planning and implementation. Distinguish between tool-first ideas and workflow-based public health use cases. Identify the governance, data, workforce, vendor, equity, privacy, and monitoring questions that must be addressed before implementation. Create a project framing brief for a proposed AI-supported public health workflow. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 4
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
4
Module Overview
• This module introduces program managers to the practical responsibilities.
• It focuses on problem definition, governance intake, stakeholder.
• It is written for national use, so it does not assume a specific agency.
Core concept
This module introduces program managers to the practical responsibilities.
Implementation path
Need
Build
Adopt
Implementation work should make dependencies, approvals, training, and.
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: Module Overview This module introduces program managers to the practical responsibilities involved in managing AI projects in public health settings. It focuses on problem definition, governance intake, stakeholder coordination, approved-tool awareness, workflow fit, risk review, implementation planning, and monitoring. It is written for national use, so it does not assume a specific agency tool, procurement process, or governance structure. Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.

## Slide 5
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
5
Jurisdiction and Agency Policy Note
• This national-level training module is intended for public health education,.
• It does not replace agency policy, legal review, privacy review, security.
• Learners should confirm applicable requirements, approved tools, data rules,.
Governance lens
This national-level training module is intended for public health education,.
Governance pathway
Submit
Review
Oversee
A proposed AI use should move through documented review before it.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Jurisdiction and Agency Policy Note This national-level training module is intended for public health education, planning, and workforce development. It does not replace agency policy, legal review, privacy review, security review, procurement review, communications clearance, civil rights review, Tribal consultation, or governance approval. Learners should confirm applicable requirements, approved tools, data rules, and review pathways within their own jurisdiction and organization before implementing AI-supported workflows. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 6
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
6
Why This Topic Matters for Public Health AI
• Many AI projects fail or create risk because they begin as technology.
• Program managers are often the people who must turn an idea into a defined.
• They do not need to be data scientists, but they need enough AI literacy to.
Core concept
Many AI projects fail or create risk because they begin as technology.
Implementation path
Need
Build
Adopt
Implementation work should make dependencies, approvals, training, and.
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: Why This Topic Matters for Public Health AI Many AI projects fail or create risk because they begin as technology demonstrations rather than managed public health projects. Program managers are often the people who must turn an idea into a defined problem, a feasible workflow, an accountable team, and an implementation plan. They do not need to be data scientists, but they need enough AI literacy to ask the right questions and route the project to the right reviewers. Responsible AI project management begins with governance intake and continues through monitoring and lifecycle decisions. Public health AI projects often involve multiple teams, including programs, epidemiology, IT, legal, privacy, security, procurement, communications, equity, community engagement, and leadership. Without coordination, projects may move forward with unclear ownership, unapproved tools, poor data readiness, unrealistic timelines, or no plan for human review. Program managers help prevent these failures by making assumptions, decisions, dependencies, and review needs visible. They also ensure that AI work remains connected to public health value rather than novelty. Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.

## Slide 7
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
7
Public Health Example
• A chronic disease program wants to use AI to identify communities that may.
• The program manager first documents the public health purpose, data sources,.
• Instead of asking a vendor to build a model immediately, the manager routes.
Core concept
A chronic disease program wants to use AI to identify communities that may.
Concept checkpoints
A chronic disease program wants to use AI to.
The program manager first documents the public.
Instead of asking a vendor to build a model.
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: Public Health Example A chronic disease program wants to use AI to identify communities that may benefit from outreach about hypertension screening. The program manager first documents the public health purpose, data sources, affected populations, intended users, proposed workflow, human review points, and governance questions. Instead of asking a vendor to build a model immediately, the manager routes the idea through intake and triage to determine data readiness, privacy review, equity concerns, and whether a simpler analytic approach might be sufficient. This helps the team decide whether the project should proceed, change scope, or wait for additional preparation. Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.

## Slide 8
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
8
Technical, Programmatic, and Operational Deep Dive
• A program manager should begin by clarifying the problem and the decision.
• The project framing brief should explain who experiences the problem, why.
• It should also identify whether AI is necessary or whether a policy,.
Core concept
A program manager should begin by clarifying the problem and the decision that.
Concept checkpoints
The project framing brief should explain who.
It should also identify whether AI is necessary or.
This protects the agency from investing in AI when.
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: Technical, Programmatic, and Operational Deep Dive A program manager should begin by clarifying the problem and the decision that AI would support. The project framing brief should explain who experiences the problem, why current workflows are insufficient, and what improvement would matter. It should also identify whether AI is necessary or whether a policy, staffing, workflow, data quality, or communication change would solve the problem more directly. This protects the agency from investing in AI when the underlying issue is not technical. The next step is to map stakeholders and review needs. Program managers should identify business owners, technical owners, data stewards, intended users, affected groups, and reviewers for privacy, security, legal, equity, procurement, communications, and governance. They should also determine whether the project involves public-facing outputs, decision support, sensitive data, automation, external vendors, or community impact. These factors determine the level of review required before implementation. AI project management also requires planning beyond the pilot. The project plan should address training, change management, user acceptance testing, validation, monitoring, incident reporting, funding, sustainment, and retirement criteria. Program managers should document what evidence will be used to decide whether the project should scale, revise, pause, or stop. This makes AI implementation accountable rather than experimental by default. Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.

## Slide 9
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
9
Risks, Failure Modes, and Guardrails
• A major failure mode is allowing a project to become vendor-led before the.
• Vendors may demonstrate impressive capabilities, but the agency remains.
• Guardrails include use case intake, governance triage, internal.
Risk check
A major failure mode is allowing a project to become vendor-led before the.
Concept checkpoints
A major failure mode is allowing a project to.
Vendors may demonstrate impressive capabilities,.
Guardrails include use case intake, governance.
Safeguard to plan
Identify what could go wrong, who could be affected, what safeguards are needed,.
Notes: Risks, Failure Modes, and Guardrails A major failure mode is allowing a project to become vendor-led before the public health problem is defined. Vendors may demonstrate impressive capabilities, but the agency remains responsible for purpose, data use, equity, privacy, and public impact. Guardrails include use case intake, governance triage, internal requirements, and clear decision rights before vendor engagement. Program managers should ensure that vendor conversations do not replace public health problem definition. Another risk is underestimating workflow and workforce impacts. AI tools may add review steps, change roles, alter documentation, or create new monitoring responsibilities. If staff are not prepared, the tool may be ignored, misused, or overtrusted. Guardrails include workflow mapping, training plans, supervisor readiness, and feedback loops before and during implementation. A third risk is treating project launch as success. An AI-supported workflow can be launched and still fail to improve outcomes, reduce burden, or maintain equity. Program managers should require monitoring metrics, user feedback, and governance review after go-live. The project should have explicit criteria for continuation, revision, pause, or retirement. Application guidance: Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.

## Slide 10
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
10
Application to AI-Supported Workflows
• This module applies to any AI-supported workflow being proposed, piloted,.
• The program manager should use intake and project framing to define scope,.
• The project should not proceed to procurement or technical build until the.
Implementation cue
This module applies to any AI-supported workflow being proposed, piloted,.
Concept checkpoints
This module applies to any AI-supported workflow.
The program manager should use intake and project.
The project should not proceed to procurement or.
Next action
Use the concept to clarify workflow changes, dependencies, staffing, procurement.
Notes: Application to AI-Supported Workflows This module applies to any AI-supported workflow being proposed, piloted, procured, implemented, or evaluated by a public health program. The program manager should use intake and project framing to define scope, owners, review needs, and evidence requirements. The project should not proceed to procurement or technical build until the team understands data, risk, workflow, human review, and monitoring expectations. Approved-tool awareness should be part of the project plan because teams must know which tools are authorized for which data and tasks. Application guidance: Use the concept to clarify workflow changes, dependencies, staffing, procurement requirements, training needs, and implementation checkpoints.

## Slide 11
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
11
Reflection Questions
• What AI ideas in your program are actually workflow problems that need.
• Who needs to review an AI project before a pilot or vendor discussion begins?
• What evidence would show that an AI project is worth scaling or continuing?
Core concept
What AI ideas in your program are actually workflow problems that need better.
Concept checkpoints
What AI ideas in your program are actually.
Who needs to review an AI project before a pilot.
What evidence would show that an AI project is.
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: Reflection Questions What AI ideas in your program are actually workflow problems that need better definition? Who needs to review an AI project before a pilot or vendor discussion begins? What evidence would show that an AI project is worth scaling or continuing? Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.

## Slide 12
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
12
Practical Exercise
• Create a project framing brief for a proposed AI-supported public health.
• Include the public health problem, proposed AI support, users, data,.
• Example: For an AI-supported referral follow-up workflow, the brief might.
Practice focus
Create a project framing brief for a proposed AI-supported public health program.
Concept checkpoints
Include the public health problem, proposed AI.
Example: For an AI-supported referral follow-up.
What to produce
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Practical Exercise Create a project framing brief for a proposed AI-supported public health program workflow. Include the public health problem, proposed AI support, users, data, affected populations, owners, review needs, approved-tool considerations, risks, expected benefits, monitoring metrics, and next decision point. Example: For an AI-supported referral follow-up workflow, the brief might explain that staff need help prioritizing follow-up calls, identify referral data as sensitive, require human review before outreach decisions, include equity review for missed populations, and define success as improved timely contact without reducing service access for lower-data groups. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 13
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
13
Expected Artifact or Evidence
• AI project framing brief.
• Stakeholder and reviewer list.
• Initial monitoring and decision criteria.
Core concept
AI project framing brief.
Concept checkpoints
AI project framing brief.
Stakeholder and reviewer list.
Initial monitoring and decision criteria.
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: Expected Artifact or Evidence AI project framing brief. Stakeholder and reviewer list. Initial monitoring and decision criteria. Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.

## Slide 14
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
14
Knowledge Check
1. What should come before vendor selection in an AI project?
2. Why do program managers need AI literacy?
3. What is a tool-first project?
Practice focus
What should come before vendor selection in an AI project?
Concept checkpoints
What should come before vendor selection in an AI.
What to produce
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Knowledge Check 1. What should come before vendor selection in an AI project? 2. Why do program managers need AI literacy? 3. What is a tool-first project? 4. What should be planned beyond the pilot? 5. What is one appropriate program manager guardrail? Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 15
Managing AI Projects in Public Health Programs
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
15
References and Resources
• [object Object]
• [object Object]
• [object Object]
Core concept
[object Object]
Concept checkpoints
[object Object]
[object Object]
[object Object]
Apply it
Connect the concept to public health purpose, responsible use, required.
Notes: References and Resources [object Object] [object Object] [object Object] [object Object] Application guidance: Connect the concept to public health purpose, responsible use, required safeguards, documentation, and the next action a department should take.