## Slide 1
PGM 120
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
1
Notes: PGM 120 AI Pilot Planning and Governance Coordination This module prepares public health program managers to plan AI pilots that are limited, governed, measurable, and safe. It focuses on pilot scope, governance conditions, data boundaries, user training, evaluation criteria, risk controls, and go/no-go decisions. The module emphasizes that pilots are structured learning activities, not automatic paths to scale.

## Slide 2
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
2
What this module helps you do
• This module prepares public health program managers to plan AI pilots that.
• It focuses on pilot scope, governance conditions, data boundaries, user.
• The module emphasizes that pilots are structured learning activities, not.
Module details
Level: applied Primary track: Program Management Track Appears in tracks:.
Learning sequence
Read the module for shared vocabulary and context.
Complete the practical exercise to apply the.
Use the notes and references for deeper review.
Notes: Module Context Level: applied Primary track: Program Management Track Appears in tracks: program-management This module prepares public health program managers to plan AI pilots that are limited, governed, measurable, and safe. It focuses on pilot scope, governance conditions, data boundaries, user training, evaluation criteria, risk controls, and go/no-go decisions. The module emphasizes that pilots are structured learning activities, not automatic paths to scale.

## Slide 3
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
3
Learning Objectives
• Define the purpose, scope, and boundaries of an AI pilot.
• Coordinate governance, privacy, security, equity, technical, and program.
• Develop pilot success criteria, monitoring measures, and pause criteria.
Governance lens
Define the purpose, scope, and boundaries of an AI pilot.
Concept checkpoints
Define the purpose, scope, and boundaries of an AI.
Coordinate governance, privacy, security, equity,.
Develop pilot success criteria, monitoring.
What to document
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Learning Objectives Define the purpose, scope, and boundaries of an AI pilot. Coordinate governance, privacy, security, equity, technical, and program review before pilot launch. Develop pilot success criteria, monitoring measures, and pause criteria. Create a pilot plan that supports responsible go/no-go decisions. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 4
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
4
Module Overview
• This module prepares public health program managers to plan AI pilots that.
• It focuses on pilot scope, governance conditions, data boundaries, user.
• The module emphasizes that pilots are structured learning activities, not.
Governance lens
This module prepares public health program managers to plan AI pilots that are.
Governance pathway
Submit
Review
Oversee
A proposed AI use should move through documented review before it.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Module Overview This module prepares public health program managers to plan AI pilots that are limited, governed, measurable, and safe. It focuses on pilot scope, governance conditions, data boundaries, user training, evaluation criteria, risk controls, and go/no-go decisions. The module emphasizes that pilots are structured learning activities, not automatic paths to scale. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 5
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
5
Jurisdiction and Agency Policy Note
• This national-level training module is intended for public health education,.
• It does not replace agency policy, legal review, privacy review, security.
• Learners should confirm applicable requirements, approved tools, data rules,.
Governance lens
This national-level training module is intended for public health education,.
Governance pathway
Submit
Review
Oversee
A proposed AI use should move through documented review before it.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Jurisdiction and Agency Policy Note This national-level training module is intended for public health education, planning, and workforce development. It does not replace agency policy, legal review, privacy review, security review, procurement review, communications clearance, civil rights review, Tribal consultation, or governance approval. Learners should confirm applicable requirements, approved tools, data rules, and review pathways within their own jurisdiction and organization before implementing AI-supported workflows. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 6
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
6
Why This Topic Matters for Public Health AI
• AI pilots can be valuable because they allow agencies to test feasibility,.
• However, pilots can also create risk if they use real data without approval,.
• A pilot should be time-limited, documented, reviewed, and connected to a.
Governance lens
AI pilots can be valuable because they allow agencies to test feasibility, user.
Governance pathway
Submit
Review
Oversee
A proposed AI use should move through documented review before it.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Why This Topic Matters for Public Health AI AI pilots can be valuable because they allow agencies to test feasibility, user experience, workflow fit, and risk controls before broader implementation. However, pilots can also create risk if they use real data without approval, expand beyond scope, or become permanent without evaluation. A pilot should be time-limited, documented, reviewed, and connected to a clear decision. Program managers play a key role in making sure the pilot remains a learning activity rather than an uncontrolled deployment. Governance coordination is essential before a pilot begins. The team should know what has been approved, what conditions apply, which data can be used, who may participate, what outputs may be used for, and what activities are prohibited. The pilot plan should also identify what evidence will be collected and who will decide whether to revise, scale, pause, or stop. Without those elements, a pilot can bypass the very safeguards it was supposed to test. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 7
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
7
Public Health Example
• A disease surveillance team wants to pilot an AI tool that summarizes.
• The pilot uses fictional and de-identified test data at first, limits users.
• The program manager documents success measures, including time saved,.
Governance lens
A disease surveillance team wants to pilot an AI tool that summarizes notifiable.
Concept checkpoints
A disease surveillance team wants to pilot an AI.
The pilot uses fictional and de-identified test.
The program manager documents success measures,.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Public Health Example A disease surveillance team wants to pilot an AI tool that summarizes notifiable condition case notes for internal epidemiologist review. The pilot uses fictional and de-identified test data at first, limits users to a small trained group, requires human verification of every summary, and prohibits using AI output for official case classification. The program manager documents success measures, including time saved, summary accuracy, reviewer burden, missed information, and user concerns. At the end of the pilot, governance reviews the evidence before deciding whether any broader use should be considered. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 8
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
8
Technical, Programmatic, and Operational Deep Dive
• A pilot plan should begin with a specific question.
• The team may be testing whether the AI tool improves workflow efficiency,.
• A vague pilot question leads to vague evaluation and makes it easier for the.
Governance lens
A pilot plan should begin with a specific question.
Concept checkpoints
The team may be testing whether the AI tool.
A vague pilot question leads to vague evaluation.
The plan should also state what the pilot is not.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Technical, Programmatic, and Operational Deep Dive A pilot plan should begin with a specific question. The team may be testing whether the AI tool improves workflow efficiency, whether staff can review outputs safely, whether data can be processed in an approved environment, or whether the use case creates unacceptable risk. A vague pilot question leads to vague evaluation and makes it easier for the pilot to continue without a decision. The plan should also state what the pilot is not testing and what actions are out of scope. Governance coordination should be visible in the pilot plan. The plan should list required reviewers, approval conditions, data restrictions, security requirements, equity considerations, human review rules, documentation requirements, and user training. It should also identify who can authorize changes to scope, such as adding data, users, vendors, or operational uses. Scope changes should not occur informally during the pilot. Evaluation should be designed before launch. Metrics may include accuracy, completeness, time, user burden, error types, equity concerns, accessibility, adoption, incidents, and public health value. The plan should also define pause criteria, such as data exposure, repeated unsafe outputs, unmanageable reviewer burden, user overreliance, or evidence that the tool worsens inequity. Pilot findings should be documented in a way that supports governance and leadership decisions. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 9
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
9
Risks, Failure Modes, and Guardrails
• A common failure mode is pilot creep.
• A small test may gradually add users, data, workflows, or real decisions.
• Guardrails include written scope, change-control rules, named owners, and.
Governance lens
A common failure mode is pilot creep.
Concept checkpoints
Guardrails include written scope, change-control.
Program managers should treat changes in data,.
Another risk is evaluating only whether staff like.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Risks, Failure Modes, and Guardrails A common failure mode is pilot creep. A small test may gradually add users, data, workflows, or real decisions without formal approval. Guardrails include written scope, change-control rules, named owners, and governance review of any expansion. Program managers should treat changes in data, users, automation, or decision consequence as governance events. Another risk is evaluating only whether staff like the tool. User satisfaction matters, but it is not enough to determine safety, equity, or effectiveness. The pilot should evaluate output quality, workflow impact, human review burden, errors, and unintended consequences. Feedback from users should be paired with evidence from monitoring and review. A third risk is failing to define what happens after the pilot. Without a go/no-go process, a pilot may become an unreviewed operational system. The pilot plan should identify the decision-makers, evidence package, timeline, and possible decisions. Possible outcomes should include revise, scale, defer, pause, or retire. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 10
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
10
Application to AI-Supported Workflows
• This module applies when an AI use case has passed initial intake and is.
• The pilot should not begin until governance has reviewed scope, data, risks,.
• Program managers should coordinate across teams so that the pilot produces.
Governance lens
This module applies when an AI use case has passed initial intake and is being.
Concept checkpoints
This module applies when an AI use case has passed.
Program managers should coordinate across teams so.
The pilot plan should become part of the project.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Application to AI-Supported Workflows This module applies when an AI use case has passed initial intake and is being considered for controlled testing. The pilot should not begin until governance has reviewed scope, data, risks, and safeguards. Program managers should coordinate across teams so that the pilot produces useful evidence and does not create unapproved operational dependence. The pilot plan should become part of the project record. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 11
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
11
Reflection Questions
• What would your team need to learn from a pilot before deciding whether to.
• What conditions should require an AI pilot to pause?
• Who should approve changes to pilot scope?
Governance lens
What would your team need to learn from a pilot before deciding whether to scale?
Concept checkpoints
What would your team need to learn from a pilot.
What conditions should require an AI pilot to pause?
Who should approve changes to pilot scope?
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Reflection Questions What would your team need to learn from a pilot before deciding whether to scale? What conditions should require an AI pilot to pause? Who should approve changes to pilot scope? Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 12
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
12
Practical Exercise
• Create an AI pilot planning brief.
• Include the pilot question, scope, data boundaries, users, approved-tool.
• Example: For an AI-assisted document summarization pilot, the brief might.
Governance lens
Create an AI pilot planning brief.
Concept checkpoints
Include the pilot question, scope, data.
Example: For an AI-assisted document summarization.
What to document
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Practical Exercise Create an AI pilot planning brief. Include the pilot question, scope, data boundaries, users, approved-tool requirements, governance conditions, training plan, metrics, pause criteria, go/no-go decision process, and documentation requirements. Example: For an AI-assisted document summarization pilot, the brief might limit the pilot to de-identified test documents, require reviewer scoring of accuracy and completeness, prohibit external sharing of summaries, define pause criteria for missing critical information, and require governance review before any real operational use. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 13
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
13
Expected Artifact or Evidence
• AI pilot planning brief.
• Governance coordination checklist.
• Pilot evaluation and pause criteria.
Governance lens
AI pilot planning brief.
Concept checkpoints
AI pilot planning brief.
Governance coordination checklist.
Pilot evaluation and pause criteria.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Expected Artifact or Evidence AI pilot planning brief. Governance coordination checklist. Pilot evaluation and pause criteria. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 14
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
14
Knowledge Check
1. What is the best description of an AI pilot?
2. What is pilot creep?
3. Why should metrics be defined before launch?
Governance lens
What is the best description of an AI pilot?
Concept checkpoints
What is the best description of an AI pilot?
What to document
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Knowledge Check 1. What is the best description of an AI pilot? 2. What is pilot creep? 3. Why should metrics be defined before launch? 4. What should happen if a pilot repeatedly produces unsafe outputs? 5. Who should approve scope changes? Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 15
AI Pilot Planning and Governance Coordination
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
15
References and Resources
• [object Object]
• [object Object]
• [object Object]
Governance lens
[object Object]
Concept checkpoints
[object Object]
[object Object]
[object Object]
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: References and Resources [object Object] [object Object] [object Object] [object Object] Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.