## Slide 1
PGM 130
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
1
Notes: PGM 130 AI Implementation Metrics and Value Tracking for Program Managers This module helps program managers define and track whether AI-supported workflows create public health value. It focuses on practical metrics, burden, equity, quality, safety, adoption, cost, sustainability, and lifecycle decisions. The module emphasizes that value should be measured against public health purpose, not only speed, automation, or user enthusiasm.

## Slide 2
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
2
What this module helps you do
• This module helps program managers define and track whether AI-supported.
• It focuses on practical metrics, burden, equity, quality, safety, adoption,.
• The module emphasizes that value should be measured against public health.
Module details
Level: applied Primary track: Program Management Track Appears in tracks:.
Learning sequence
Read the module for shared vocabulary and context.
Complete the practical exercise to apply the.
Use the notes and references for deeper review.
Notes: Module Context Level: applied Primary track: Program Management Track Appears in tracks: program-management This module helps program managers define and track whether AI-supported workflows create public health value. It focuses on practical metrics, burden, equity, quality, safety, adoption, cost, sustainability, and lifecycle decisions. The module emphasizes that value should be measured against public health purpose, not only speed, automation, or user enthusiasm.

## Slide 3
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
3
Learning Objectives
• Define meaningful value measures for AI-supported public health workflows.
• Distinguish productivity metrics from public health value, equity, quality,.
• Develop a monitoring plan that includes adoption, burden, errors, equity,.
Data decision
Define meaningful value measures for AI-supported public health workflows.
Concept checkpoints
Define meaningful value measures for AI-supported.
Distinguish productivity metrics from public.
Develop a monitoring plan that includes adoption,.
How to validate
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Learning Objectives Define meaningful value measures for AI-supported public health workflows. Distinguish productivity metrics from public health value, equity, quality, and safety measures. Develop a monitoring plan that includes adoption, burden, errors, equity, and sustainment. Use implementation evidence to inform decisions to scale, revise, pause, or retire AI uses. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 4
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
4
Module Overview
• This module helps program managers define and track whether AI-supported.
• It focuses on practical metrics, burden, equity, quality, safety, adoption,.
• The module emphasizes that value should be measured against public health.
Data decision
This module helps program managers define and track whether AI-supported.
Data-to-decision flow
Data
Analysis
Review
The important handoff is not from data to AI; it is from analysis to.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Module Overview This module helps program managers define and track whether AI-supported workflows create public health value. It focuses on practical metrics, burden, equity, quality, safety, adoption, cost, sustainability, and lifecycle decisions. The module emphasizes that value should be measured against public health purpose, not only speed, automation, or user enthusiasm. Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 5
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
5
Jurisdiction and Agency Policy Note
• This national-level training module is intended for public health education,.
• It does not replace agency policy, legal review, privacy review, security.
• Learners should confirm applicable requirements, approved tools, data rules,.
Governance lens
This national-level training module is intended for public health education,.
Governance pathway
Submit
Review
Oversee
A proposed AI use should move through documented review before it.
What to document
Translate this concept into clear decision rights, review steps, documentation.
Notes: Jurisdiction and Agency Policy Note This national-level training module is intended for public health education, planning, and workforce development. It does not replace agency policy, legal review, privacy review, security review, procurement review, communications clearance, civil rights review, Tribal consultation, or governance approval. Learners should confirm applicable requirements, approved tools, data rules, and review pathways within their own jurisdiction and organization before implementing AI-supported workflows. Application guidance: Translate this concept into clear decision rights, review steps, documentation expectations, and escalation paths before an AI-supported workflow is approved.

## Slide 6
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
6
Why This Topic Matters for Public Health AI
• AI projects are often justified by expected efficiency, but public health.
• A tool may reduce one task while increasing review burden, widening.
• Program managers need to define what success means before implementation and.
Data decision
AI projects are often justified by expected efficiency, but public health value.
Data-to-decision flow
Data
Analysis
Review
The important handoff is not from data to AI; it is from analysis to.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Why This Topic Matters for Public Health AI AI projects are often justified by expected efficiency, but public health value is broader than time saved. A tool may reduce one task while increasing review burden, widening inequities, weakening trust, or creating new monitoring responsibilities. Program managers need to define what success means before implementation and track whether the workflow actually delivers value. This protects agencies from scaling tools that are impressive but not useful, safe, equitable, or sustainable. Value tracking also supports governance. Governance bodies need evidence to decide whether an AI use should continue, change, expand, pause, or retire. Metrics should include process measures, quality measures, equity measures, user experience, risk indicators, and public health outcomes where feasible. A balanced approach helps teams avoid narrow success claims based only on speed or volume. Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 7
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
7
Public Health Example
• A maternal and child health program pilots an AI-assisted referral follow-up.
• The team tracks not only the number of referrals reviewed per day, but also.
• The evidence shows that speed improved, but the prioritization logic missed.
Data decision
A maternal and child health program pilots an AI-assisted referral follow-up.
Concept checkpoints
The team tracks not only the number of referrals.
The evidence shows that speed improved, but the.
The program revises the workflow before.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Public Health Example A maternal and child health program pilots an AI-assisted referral follow-up prioritization process. The team tracks not only the number of referrals reviewed per day, but also whether high-priority families are contacted faster, whether staff spend more time correcting outputs, whether certain communities are under-prioritized, and whether families report clearer service navigation. The evidence shows that speed improved, but the prioritization logic missed families with incomplete data. The program revises the workflow before considering scale. Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 8
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
8
Technical, Programmatic, and Operational Deep Dive
• A strong measurement plan begins with the public health purpose.
• The team should define the problem, the intended improvement, and the.
• Measures may include timeliness, completeness, accuracy, consistency,.
Data decision
A strong measurement plan begins with the public health purpose.
Concept checkpoints
Measures may include timeliness, completeness,.
The plan should also identify measures that would.
Productivity metrics should be interpreted.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Technical, Programmatic, and Operational Deep Dive A strong measurement plan begins with the public health purpose. The team should define the problem, the intended improvement, and the evidence that would show progress. Measures may include timeliness, completeness, accuracy, consistency, workload, user experience, service access, equity, safety, and cost. The plan should also identify measures that would show harm or unacceptable burden. Productivity metrics should be interpreted carefully. Time saved may be meaningful, but only if quality and equity are maintained. A summarization tool that saves staff time but omits critical context is not valuable. A routing tool that processes more cases but misses low-data populations may worsen inequity. Program managers should pair efficiency measures with quality, safety, and equity indicators. Value tracking should continue after go-live. AI-supported workflows can change over time because data, users, policies, populations, and vendor systems change. Monitoring should have owners, cadence, thresholds, and escalation pathways. The project record should show how evidence is used to improve the workflow and whether continuation remains justified. Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 9
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
9
Risks, Failure Modes, and Guardrails
• A common failure mode is measuring only activity.
• Counts of messages processed, drafts generated, or cases flagged do not show.
• Guardrails include linking measures to the original use case purpose and.
Risk check
A common failure mode is measuring only activity.
Concept checkpoints
Counts of messages processed, drafts generated, or.
Guardrails include linking measures to the.
Teams should ask what better decision, service,.
Safeguard to plan
Identify what could go wrong, who could be affected, what safeguards are needed,.
Notes: Risks, Failure Modes, and Guardrails A common failure mode is measuring only activity. Counts of messages processed, drafts generated, or cases flagged do not show whether the workflow improved public health practice. Guardrails include linking measures to the original use case purpose and including quality and equity measures. Teams should ask what better decision, service, communication, or outcome the AI use is supposed to support. Another risk is ignoring hidden burden. AI may shift work to reviewers, supervisors, IT, data stewards, or community partners. A workflow that appears efficient for one team may create more work elsewhere. Burden measures should include time, cognitive load, rework, training, monitoring, and incident response. Staff feedback should be part of value tracking. A third risk is failing to act on evidence. Monitoring has little value if findings are not reviewed or used. Governance and program leadership should define thresholds for revision, pause, or retirement. Evidence should support decisions rather than becoming a dashboard that no one uses. Application guidance: Identify what could go wrong, who could be affected, what safeguards are needed, and what evidence should be reviewed before use expands.

## Slide 10
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
10
Application to AI-Supported Workflows
• This module applies to AI-supported workflows that are being piloted,.
• The measurement plan should be created before implementation and updated as.
• Program managers should coordinate with data, IT, equity, privacy, security,.
Data decision
This module applies to AI-supported workflows that are being piloted,.
Concept checkpoints
This module applies to AI-supported workflows that.
Program managers should coordinate with data, IT,.
Approved tools should be used for measurement and.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Application to AI-Supported Workflows This module applies to AI-supported workflows that are being piloted, implemented, monitored, or considered for scale. The measurement plan should be created before implementation and updated as the workflow matures. Program managers should coordinate with data, IT, equity, privacy, security, communications, and governance reviewers to ensure the measures reflect real risks and goals. Approved tools should be used for measurement and reporting when local policy requires them. Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 11
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
11
Reflection Questions
• What would count as public health value for an AI-supported workflow in your.
• Which metrics could reveal hidden burden or inequitable impact?
• Who should review the evidence and decide whether the AI use should continue?
Data decision
What would count as public health value for an AI-supported workflow in your.
Concept checkpoints
What would count as public health value for an.
Which metrics could reveal hidden burden or.
Who should review the evidence and decide whether.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Reflection Questions What would count as public health value for an AI-supported workflow in your program? Which metrics could reveal hidden burden or inequitable impact? Who should review the evidence and decide whether the AI use should continue? Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 12
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
12
Practical Exercise
• Develop an AI implementation value tracking plan for one workflow.
• Include the public health purpose, efficiency measures, quality measures,.
• Example: For AI-assisted call center FAQ support, the plan might track.
Data decision
Develop an AI implementation value tracking plan for one workflow.
Concept checkpoints
Include the public health purpose, efficiency.
Example: For AI-assisted call center FAQ support,.
How to validate
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Practical Exercise Develop an AI implementation value tracking plan for one workflow. Include the public health purpose, efficiency measures, quality measures, equity measures, burden measures, safety indicators, data sources, owners, review cadence, thresholds, and lifecycle decision options. Example: For AI-assisted call center FAQ support, the plan might track response time, accuracy of answers, staff corrections, accessibility of language, caller satisfaction, escalation rates, and whether certain language groups receive less accurate support. Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 13
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
13
Expected Artifact or Evidence
• AI implementation value tracking plan.
• Balanced measure set with at least one efficiency, quality, equity, burden,.
• Lifecycle decision criteria.
Data decision
AI implementation value tracking plan.
Concept checkpoints
AI implementation value tracking plan.
Balanced measure set with at least one efficiency,.
Lifecycle decision criteria.
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: Expected Artifact or Evidence AI implementation value tracking plan. Balanced measure set with at least one efficiency, quality, equity, burden, and safety measure. Lifecycle decision criteria. Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.

## Slide 14
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
14
Knowledge Check
1. Why should AI value tracking include more than time saved?
2. What is a burden measure?
3. What should happen when monitoring identifies unacceptable harm?
Data decision
Why should AI value tracking include more than time saved?
Concept checkpoints
Why should AI value tracking include more than.
How to validate
Use the assignment to test whether you can explain the concept, apply it to a.
Notes: Knowledge Check 1. Why should AI value tracking include more than time saved? 2. What is a burden measure? 3. What should happen when monitoring identifies unacceptable harm? 4. Which measure set is most balanced? 5. When should value measures be defined? Application guidance: Use the assignment to test whether you can explain the concept, apply it to a realistic public health situation, and identify what would need review before the work moves forward.

## Slide 15
AI Implementation Metrics and Value Tracking for Program Managers
AI Playbook and Toolkit for Public Health Departments
Copyright Paula Soper
15
References and Resources
• [object Object]
• [object Object]
• [object Object]
Data decision
[object Object]
Concept checkpoints
[object Object]
[object Object]
[object Object]
How to validate
Connect the concept to data quality, model performance, validation evidence,.
Notes: References and Resources [object Object] [object Object] [object Object] [object Object] Application guidance: Connect the concept to data quality, model performance, validation evidence, monitoring measures, and decisions that remain under human control.