AI Playbook and Toolkit for Public Health Departments

Website Reference Guide

This document compiles public website content from the Start Here, Learn, AI Support Areas, Assess, Maturity Model, Plays, Toolkit, Case Studies, Resources, and In the News pages. My Account, Organization Hub, Community, and Contribute content are intentionally excluded.

# Contents

Executive Overview

Implementation Phases

Background Foundations

Areas Where AI Can Support Public Health Activities

Readiness Assessment

AI Maturity Model

13-Play Planning and Implementation Framework

Toolkit Inventory

Case Studies and Promising Practices

Resources and Bibliography

In the News

# Executive Overview

The AI Playbook and Toolkit helps public health departments adopt generative and agentic AI responsibly through phased planning, governance, readiness assessment, stakeholder engagement, workforce development, use case prioritization, funding, deployment, oversight, and evaluation.

The ASPPH AI framework report has been incorporated into the website through added foundations on AI as a systems shift, digital determinants of health, human-centered AI, staff AI literacy, automation bias, missing voices analysis, transparency, tiered data use, environmental impacts, and the bridge professional role.

# Implementation Phases

| Phase | Range | Summary |
| --- | --- | --- |
| PLAN | Plays 1-7 | Vision, readiness, governance, stakeholders, workforce, change planning, use cases |
| BUILD | Plays 8-9 | Funding and roadmap |
| DEPLOY | Plays 10-11 | Change execution, build, deploy |
| GOVERN | Plays 12-13 | Monitor, evaluate, oversight |

# Background Foundations

## Staff Training and Shared Readiness

Use these modules to build your own foundation before you participate in AI project work. The learning section can support self-paced learning, onboarding, leadership orientation, governance preparation, and role-specific readiness.

This overview explains how you can use the learning section as a staff training curriculum, not just a reference library. You can use the modules before workshops, during facilitated sessions, or as onboarding if you will participate in AI-supported work.

The goal is to help you understand your role in shared readiness. You may need to understand what AI can and cannot do in their workflows. If you are in a leadership role, you need to understand governance and resource implications. If you work in privacy, legal, procurement, IT, communications, equity, or data, you need enough shared language to review proposals consistently.

You can adapt the modules into short training sessions by pairing the narrative content with the discussion questions and staff exercise. The expected takeaways should become practical implementation artifacts, such as a training plan, a list of governance questions, or a completed readiness input.

### Module Overview

These learning modules are designed to help health departments create a shared baseline before you begin AI project work. They can be used for staff onboarding, leadership orientation, governance preparation, cross-program training, or pre-work before readiness assessment and use case prioritization.

### How You Can Use the Learning Modules

Use the modules as self-paced reading before workshops or governance meetings.

Work through one module at a time as a 30- to 60-minute learning session.

Complete modules as pre-work before completing the readiness assessment or prioritizing AI use cases.

Use module exercises to generate artifacts that feed directly into playbook tools, governance review, and implementation planning.

### Recommended Training Sequence

Start with Understanding Artificial Intelligence, Generative AI, and Agentic AI so you have the basic vocabulary.

Move into Risks, Human-Centered AI, Missing Voices, Public Transparency, and Tiered Data Use before use cases are selected.

Use AI Literacy, Bridge Professional Role, Funding, procurement, privacy, validation, incident response, and role-based guidance when preparing implementation work.

Use AI Support Areas after foundational topics so you can discuss practical opportunities without skipping governance.

### Facilitation Tips

Start each session with a concrete public health workflow rather than a general technology discussion.

Ask yourself to identify what AI may support, what humans must decide, and what data safeguards are needed.

End each session with a documented takeaway: a question for governance, a possible tool to complete, or a readiness gap to address.

Keep examples local to the department's programs, authorities, data systems, and community context.

### Why This Matters for Your Practice

Health departments can use the learning modules as practical training material rather than static background reading. The modules help staff, leaders, governance members, and program teams build a common foundation before you begin AI project work.

### Reflection Questions

Which staff groups need baseline AI training before tools are approved?

Which modules should be required before governance participation, vendor review, or use case prioritization?

How will the department document that staff understand data safeguards, human review expectations, and escalation pathways?

### Practical Exercise

Create a short training plan that assigns modules to staff groups, identifies which exercises should be completed, and connects each module to a play or tool that the department will use next.

### Expected Takeaways

Staff AI training plan

Module assignment matrix by role

Training completion expectations

List of governance or implementation artifacts produced during training

## Understanding Artificial Intelligence

AI is a family of methods that enable systems to learn from data, recognize patterns, generate content, and support action toward defined goals.

Artificial intelligence should be introduced as a set of capabilities rather than a single product. In public health, AI may appear as predictive analytics, classification, natural-language summarization, generative drafting, document search, translation support, or workflow automation. Staff need to recognize these differences because each capability has different risks, data needs, and review requirements.

A shared foundation also helps departments avoid technology-first decisions. The central question is not whether an AI tool is impressive, but whether it fits a public health purpose, uses appropriate data, improves a workflow, and remains accountable to humans. This matters when AI is embedded in vendor products, offered through enterprise software, or used informally by staff.

By the end of this module, you should be able to describe an AI-supported workflow in plain language: what the system does, what data it uses, who reviews the output, what decision remains human, and what safeguards are required before use.

### Module Overview

You do not need to become a machine learning engineer, but you do need a shared working understanding of what AI is, where it can fail, and what kinds of tasks are appropriate for different AI approaches. This module helps you distinguish pattern recognition, predictive analytics, generative AI, retrieval-augmented generation, and agentic workflows so planning discussions do not treat every AI product as the same kind of intervention.

### What You Should Be Able to Do

Explain AI in plain language to program colleagues, leaders, partners, and community members.

Identify whether a proposed use is content generation, search and retrieval, prediction, classification, workflow automation, or decision support.

Name the human role responsible for reviewing, approving, correcting, or rejecting AI-supported outputs.

Recognize that data quality, workflow design, governance, and public trust are as important as model performance.

### Public Health Application

Use AI concepts to map where an agency already has informal AI use, such as staff drafting messages with public tools or vendors embedding AI into existing platforms.

Use a common vocabulary during governance review so privacy, IT, program, legal, equity, and communications staff can evaluate the same workflow together.

Translate technical capabilities into public health value: faster review, better consistency, broader language access, clearer documentation, or earlier signal detection.

### Implementation Check

Before any AI project begins, confirm the purpose, data involved, intended users, public impact, review requirements, and escalation pathway.

Document what the AI is allowed to do and what decisions remain with qualified public health staff.

Avoid selecting tools before the department has established vision, readiness, governance, and data-use expectations.

### Why This Matters for Your Practice

A shared AI vocabulary prevents agencies from approving tools before they understand the workflow, data, risk level, and accountability structure. This is especially important for STLT public health departments because AI may enter through many doors: staff productivity tools, vendor platforms, analytics systems, communications workflows, or grant-funded pilots.

### Reflection Questions

What AI tools or AI-enabled vendor products are already being used informally?

Which public health decisions should never be delegated to an AI system?

Who needs enough AI literacy to participate in governance, procurement, or implementation decisions?

### Practical Exercise

Ask each program area to list one current task that involves searching, summarizing, drafting, routing, predicting, translating, or prioritizing. Classify each task by AI type and identify the human decision owner.

### Expected Takeaways

Agency AI vocabulary list

Initial inventory of known or suspected AI use

Draft list of decisions that require human accountability

### What AI Means for Public Health

Artificial intelligence is a family of methods that enable computer systems to learn from data, recognize patterns, generate new content, and support action toward defined goals. For public health agencies, the most consequential near-term branches are generative AI and agentic AI.

### Why This Comes First

Understanding what these systems can and cannot do is the starting point for responsible adoption. Agencies need a shared vocabulary before they can set guardrails, evaluate vendors, select use cases, or explain AI-supported workflows to staff and communities.

### Core concepts

AI is not one technology or one product category.

Generative AI produces new content from prompts and source material.

Agentic AI can coordinate a sequence of actions across systems under defined rules.

Public health use requires human review, privacy protections, equity monitoring, and governance.

### References and Resources

NIST AI Risk Management Framework. Foundational vocabulary for trustworthy AI risk management. https://www.nist.gov/itl/ai-risk-management-framework

ASPPH AI Framework Report. Public health framing for responsible AI education, research, practice, governance, and workforce preparation. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

WHO: Ethics and governance of artificial intelligence for health. Health-sector principles for ethical and responsible AI use. https://www.who.int/publications/i/item/9789240029200

## Generative AI

Generative AI produces new text, images, code, summaries, or synthetic data from prompts and examples.

Generative AI is especially relevant to public health because so much agency work involves drafting, explaining, summarizing, and adapting information for different audiences. It can help create first drafts of education materials, staff communications, grant language, policy summaries, meeting notes, and leadership briefings.

The same fluency that makes generative AI useful also makes it risky. A generated answer can sound polished while including outdated guidance, fabricated details, missing caveats, or language that does not fit the community context. Departments should treat outputs as drafts that require source checking and subject matter review.

For training purposes, staff should practice distinguishing low-risk drafting support from high-risk public-facing or decision-support uses. A safe implementation approach defines approved tools, prohibited data, source requirements, review steps, and documentation expectations before staff use generative AI in routine work.

### Module Overview

Generative AI is most useful when public health work requires drafting, summarizing, translating, organizing, or explaining information. It can reduce the time required to create first drafts, compare documents, prepare meeting materials, or convert technical findings into plain language. It should not be used as an unchecked authority on scientific evidence, law, policy, clinical guidance, or public communication.

### High-Value Uses

Draft public health education materials that staff revise for accuracy, tone, literacy level, and cultural context.

Summarize long guidance documents, inspection notes, surveillance updates, grant requirements, or policy changes for internal review.

Create first drafts of FAQs, talking points, training materials, meeting agendas, standard operating procedures, and implementation checklists.

Support grant writing by organizing goals, activities, staffing needs, evaluation measures, and sustainability plans.

### Quality Controls

Require staff review for factual accuracy, citations, public health recommendations, legal requirements, and equity implications.

Use approved source materials or retrieval-augmented generation when the output must reflect specific agency policy or current guidance.

Keep protected health information, confidential investigations, sensitive partner data, and restricted records out of public AI tools.

Label AI-assisted drafts internally so reviewers understand where human verification is needed.

### When Not to Use It

Do not use generative AI to make final eligibility, enforcement, clinical, outbreak response, or public warning decisions.

Do not rely on unsourced outputs for legal interpretation, epidemiologic conclusions, or scientific claims.

Do not deploy public-facing chatbots without governance approval, testing, monitoring, and an escalation pathway to staff.

### Why This Matters for Your Practice

Generative AI can improve staff efficiency, but it can also produce fluent misinformation, incomplete summaries, biased language, or unsupported recommendations. Public health departments need practical rules for when generative AI can draft, when it can summarize, when it must use approved source material, and when it should not be used at all.

### Reflection Questions

Which materials may be drafted with generative AI and which require approved templates or source documents?

What human review is required before AI-assisted content is shared with the public, partners, or leadership?

What data are prohibited from public or consumer AI tools?

### Practical Exercise

Take a public health education message, a policy memo, and an internal meeting summary. Define what generative AI could help draft, what source material it would need, and what review steps would be required before use.

### Expected Takeaways

Generative AI acceptable-use rules

Human review checklist for AI-assisted drafts

Approved-source guidance for RAG or document-grounded generation

### Definition

Generative AI refers to systems trained on large bodies of existing data that can produce new content, including text, images, code, summaries, and synthetic datasets, when prompted by a user.

### Large Language Models

The most widely deployed generative AI systems are large language models. They learn statistical patterns across very large text collections and can generate fluent responses to natural-language questions or instructions.

### Public health capabilities

Draft health education materials, vaccination messages, press releases, and program protocols.

Retrieve and synthesize regulatory guidance, policy documents, and scientific literature using retrieval-augmented generation.

Translate statistical outputs and surveillance findings into plain-language summaries.

Write, debug, and explain code for data analysis and visualization.

Generate realistic but de-identified synthetic datasets for model testing and training.

### References and Resources

WHO: Regulatory considerations on artificial intelligence for health. Health-focused regulatory considerations for AI systems. https://iris.who.int/handle/10665/373421

NIST Generative AI Profile. Risk management profile for generative AI systems. https://www.nist.gov/itl/ai-risk-management-framework

ASPPH AI Framework Report. Guidance on human-centered and responsible generative AI use in public health contexts. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

OpenAI Prompt Engineering Guide. Practical guidance on writing clearer prompts, decomposing tasks, using examples, and improving model outputs through structured instructions. https://platform.openai.com/docs/guides/prompt-engineering

Google Cloud Prompt Engineering Guide. Plain-language overview of prompt engineering concepts, prompt structure, examples, and responsible use considerations. https://cloud.google.com/discover/what-is-prompt-engineering

Microsoft Prompt Engineering Techniques. Prompting techniques for Azure OpenAI and Microsoft Foundry models, including instructions, grounding, examples, and output formatting. https://learn.microsoft.com/en-us/azure/ai-services/openai/concepts/prompt-engineering

## Agentic AI

Agentic AI can coordinate multi-step workflows across systems under explicit rules and human oversight.

Agentic AI introduces a different level of operational complexity because it can coordinate steps rather than simply produce content. A bounded agentic workflow might monitor incoming information, classify it, retrieve relevant documents, create a task, and route it to a staff member. That can be valuable in time-sensitive public health operations, but it also creates new accountability questions.

Departments should train staff to think of agentic AI as workflow infrastructure. The most important design decisions involve boundaries: what the system can access, what actions it can take, when it must stop, when a human must approve, and how every action is logged.

Agentic systems are not appropriate for unsupervised public health decisions. They are best introduced in controlled internal workflows where humans remain responsible for validation, communication, prioritization, and final action.

### Module Overview

Agentic AI moves beyond drafting and summarizing by coordinating multiple steps toward a defined goal. In public health, this might mean monitoring incoming reports, gathering relevant data, preparing a draft brief, routing it to the right team, and updating a task queue. Because agentic systems can initiate actions, they require tighter boundaries, audit logs, role-based access, and human approval before consequential steps occur.

### Appropriate Starting Points

Internal workflows where the AI can gather, organize, and route information without contacting the public or making final decisions.

Surveillance support tasks such as clustering incoming signals, preparing evidence packets, or flagging items for epidemiologist review.

Administrative workflows such as creating task lists from meeting notes, tracking approvals, or reminding owners about deadlines.

Care coordination support where staff review all outreach recommendations before any member, client, or patient contact.

### Required Controls

Define allowable actions, prohibited actions, required human approvals, and emergency shutoff procedures.

Maintain audit logs showing what the AI accessed, generated, changed, routed, or recommended.

Limit access to the minimum systems and data needed for the workflow.

Test failure scenarios, including wrong routing, stale data, biased prioritization, hallucinated summaries, and inappropriate escalation.

### Public Health Accountability

A named program or operational owner should remain accountable for the workflow.

The AI should never obscure who made a public health decision or why a particular action was taken.

Governance should approve agentic workflows before deployment and review performance after launch.

### Why This Matters for Your Practice

Agentic AI can coordinate work across systems, but that makes it higher risk than simple drafting. In public health operations, even routing a task, prioritizing a signal, or preparing an outreach list can affect response time, workload, trust, and equity. Agentic workflows need explicit boundaries before they are piloted.

### Reflection Questions

What actions may the AI take without approval, and what actions require human approval?

What audit logs are needed to reconstruct what happened?

How will staff pause, override, or escalate an agentic workflow?

### Practical Exercise

Map a multi-step workflow such as outbreak signal review, inspection report preparation, or care coordination outreach. Mark which steps the AI may support, which steps require human approval, and which steps are prohibited.

### Expected Takeaways

Agentic workflow boundary statement

Human approval and escalation map

Audit log and monitoring requirements

### Definition

Agentic AI systems can analyze information, generate outputs, and take a sequence of actions toward a defined goal across multiple systems while following explicit rules and retaining human oversight.

### Why It Matters

Agentic capabilities are most useful where public health work already involves multi-step workflows: gathering evidence, monitoring information streams, routing tasks, drafting updates, and handing decisions back to qualified staff.

### Practical agentic uses

Pull data from multiple systems, summarize findings, and route a draft brief for epidemiologist review.

Monitor incoming news feeds or case reports, classify and prioritize items, and create surveillance task queues.

Draft follow-up messages to patients or partners and queue them for staff approval.

Coordinate dashboards, case management systems, and communication platforms when predefined thresholds are crossed.

### References and Resources

NIST AI Risk Management Framework. Useful for defining boundaries, oversight, monitoring, and accountability for agentic systems. https://www.nist.gov/itl/ai-risk-management-framework

WHO: Ethics and governance of artificial intelligence for health. Health-sector governance principles for systems that can influence decisions or workflows. https://www.who.int/publications/i/item/9789240029200

ASPPH AI Framework Report. Public health governance, human oversight, and AI literacy context for agentic workflows. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

## Deep Research

Deep Research tools autonomously plan multi-step research tasks, gather sources, and draft citation-based reports for expert review.

Deep Research tools can help departments organize complex evidence, policy, or funding questions into structured summaries. They are useful when staff need a first-pass scan of literature, agency guidance, jurisdictional policies, implementation examples, or grant requirements.

These tools should not be treated as substitutes for professional judgment or formal evidence review. Staff still need to verify citations, check dates, assess source quality, and decide whether findings apply to the department's population, authority, and operational context.

A strong training approach asks staff to evaluate a generated research brief: Are the sources real and current? Are claims supported? Are limitations stated? Does the summary separate evidence from opinion or vendor claims? What decisions could this support, and what review is still required?

### Module Overview

Deep Research tools can help public health departments move faster when they need a structured scan of literature, policies, funding requirements, legal materials, program models, or emerging issues. These tools are best treated as research assistants that produce a starting synthesis. Staff still need to verify sources, check dates, resolve conflicting evidence, and decide what applies to the department's context.

### Useful Assignments

Scan peer-reviewed and agency sources on an emerging disease, intervention, risk factor, or public health technology.

Compare AI policies, procurement requirements, or governance models across jurisdictions.

Summarize grant notices, eligibility requirements, evaluation expectations, and allowable costs.

Prepare a briefing that separates strong evidence, emerging evidence, implementation examples, and unanswered questions.

### Review Standards

Require source links and citations for every consequential claim.

Check publication dates, jurisdiction, population relevance, and whether the source is primary, secondary, vendor-authored, or opinion-based.

Have subject matter experts review conclusions before they inform policy, funding, public communication, or operational decisions.

Document what sources were included or excluded when the synthesis supports governance or leadership decisions.

### Actionable Output

Ask for a decision-ready format: summary, implications for STLT public health, risks, resource needs, equity considerations, and recommended next steps.

Convert the research output into a tool artifact such as a policy scan, gap register, governance memo, funding brief, or implementation roadmap.

Update scans when guidance, funding rules, laws, or evidence change.

### Why This Matters for Your Practice

Deep Research tools can make literature scans and policy reviews faster, but public health departments still need defensible evidence standards. A generated synthesis is only useful if sources are current, relevant, independently verifiable, and interpreted by staff who understand the public health context.

### Reflection Questions

What source types are acceptable for the decision being supported?

Who verifies citations, dates, jurisdictional relevance, and evidence strength?

How will the department distinguish evidence, implementation examples, vendor claims, and unresolved questions?

### Practical Exercise

Use a current public health topic and design a research brief template with sections for evidence summary, source quality, STLT relevance, equity considerations, operational implications, and open questions.

### Expected Takeaways

AI-assisted research brief template

Source verification checklist

Policy or literature scan protocol

### A Practical Agentic Capability

Deep Research tools autonomously plan and execute multi-step research tasks, gather and cross-reference sources, and generate citation-based reports with transparent reasoning for expert review.

### Best Fit

These tools are well suited for first drafts of literature synthesis, policy and legal scans, strategic planning, scenario analysis, and comparative program reviews. They should accelerate expert work, not replace expert validation.

### Appropriate tasks

Literature synthesis on emerging threats or intervention strategies.

Policy and legal scans across jurisdictions.

Strategic planning and scenario analysis.

Comparative analysis of public health programs, interventions, or regulations.

### References and Resources

NIH PubMed. Primary source for biomedical and public health literature searches. https://pubmed.ncbi.nlm.nih.gov/

CDC Publications and Resources. Public health reports, guidance, and evidence sources for staff review. https://www.cdc.gov/publications/

ASPPH AI Framework Report. Framework language for responsible use of AI-supported research and synthesis. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

## AI-Supported Public Health Workflows

AI can support signal detection, evidence gathering, analysis, synthesis, briefing, communication, and decision support.

Public health AI should start with workflows, not tools. A workflow lens helps teams identify where work is slow, repetitive, inconsistent, or difficult to coordinate, and where AI might help without replacing public health judgment.

Examples include summarizing incoming reports, detecting unusual patterns, drafting situation updates, routing tasks, preparing evidence packets, or tracking implementation deadlines. Each potential use should be evaluated in context: who uses the output, what decision follows, what could go wrong, and what evidence would show improvement.

Before redesigning a workflow around AI, teams should complete basic business process analysis: define the current-state process, identify actors and handoffs, document information flows, locate bottlenecks and rework, and clarify what the future-state process should accomplish. This prevents teams from automating a broken workflow or adding AI before the operational problem is well understood.

Your training should help staff map a real workflow from trigger to output. Once the workflow is visible, the team can decide which steps AI may support, which require human review, and which should remain outside AI support altogether.

### Module Overview

AI is most useful when it is tied to a specific public health workflow rather than introduced as a general productivity tool. Workflow mapping helps teams identify where AI could support signal detection, evidence gathering, analysis, synthesis, communication, decision support, documentation, monitoring, or service delivery without displacing accountability.

### Workflow Mapping Questions

What event starts the workflow, and what output ends it?

Where do staff spend time searching, summarizing, routing, checking, rewriting, or reconciling information?

Which steps require judgment, legal authority, community relationship, scientific interpretation, or public accountability?

What data systems, forms, emails, dashboards, or documents are involved?

### Potential AI Support

Detect unusual patterns and prepare alerts for human review.

Summarize reports, partner updates, inspection notes, or case records into structured fields.

Draft situation reports, FAQs, or internal updates from approved source material.

Track implementation tasks, deadlines, approvals, and follow-up actions across teams.

### Design Safeguards

Keep AI support close to the staff workflow and test whether it actually saves time or improves quality.

Measure false positives, false negatives, staff burden, equity effects, and downstream operational impact.

Make handoffs explicit so staff know when an AI output is a draft, a flag, a recommendation, or a required review item.

### Why This Matters for Your Practice

AI projects often fail when they are not anchored in a real workflow. Public health work includes handoffs, legal authorities, partner relationships, community trust, and time-sensitive decisions. Workflow mapping helps agencies find where AI can reduce burden while preserving judgment and accountability.

### Reflection Questions

What problem in the workflow is AI expected to solve?

Where does the workflow require professional judgment, legal authority, or community knowledge?

How will staff know whether AI improves timeliness, quality, consistency, equity, or workload?

### Practical Exercise

Choose one workflow and map the trigger, inputs, staff roles, decisions, outputs, handoffs, risks, and performance measures. Identify one AI support point and one step that should remain fully human-controlled.

### Expected Takeaways

AI workflow map

Workflow risk and control table

Pilot success measures

### Common Public Health Workflow

Many public health activities move from signal detection to evidence gathering, analysis, synthesis, briefing, communication, and decision support. Mapping AI to workflow stages helps agencies choose bounded, reviewable uses.

### Reference Table

Signal Detection - Identify signals from surveillance systems, laboratory reporting, emergency departments, or environmental monitoring. - Anomaly detection and LLM-assisted monitoring of open-source information streams.

Evidence Gathering - Collect evidence to determine whether a signal represents a meaningful concern. - Agentic systems retrieve datasets, compile literature, and assemble supporting documentation.

Analysis - Evaluate collected information to determine significance. - AI-supported statistical analysis, exploratory visualization, and pattern identification.

Synthesis - Combine information from multiple sources into a coherent picture. - Generative AI summarizes findings, consolidates reports, and drafts evidence summaries.

Briefing and Communication - Communicate findings through dashboards, situation reports, policy briefs, or advisories. - Generative AI drafts reports, summarizes trends, and adapts messages for audiences.

Decision Support - Use evidence to guide response activities and policy decisions. - AI organizes relevant information and produces structured briefing materials for leadership review.

### References and Resources

CDC Data Modernization Initiative. Context for modern public health data flows and AI-ready infrastructure. https://www.cdc.gov/surveillance/data-modernization/index.html

CDC STLT Data Connection. Peer-learning resource for public health data modernization and workflow improvement. https://www.cdc.gov/data-modernization/php/stlt-data-connection/index.html

NIST AI Risk Management Framework. Framework for mapping workflow risks, controls, and monitoring. https://www.nist.gov/itl/ai-risk-management-framework

## Risks, Limitations, and Guardrails

Public health AI risks include hallucination, bias, privacy exposure, automation bias, model drift, and performance loss on complex tasks.

AI risk in public health is broader than technical model performance. A system can be accurate in a test setting but still create harm if it exposes sensitive data, increases inequity, produces unclear recommendations, encourages over-trust, or undermines community confidence.

Risk management should be practical and repeatable. You should learn to ask what harm could occur, who could be affected, how likely the harm is, how it would be detected, and who has authority to pause or correct the system.

This module should prepare staff to participate in risk review discussions. The goal is not to eliminate all risk, but to make risk visible, assign ownership, document mitigations, and monitor whether safeguards work after deployment.

### Module Overview

AI risks in public health are not limited to technical errors. They include privacy exposure, hallucinated guidance, biased prioritization, automation bias, model drift, vendor opacity, accessibility barriers, environmental burden, and loss of public trust. Risk management should begin before tool selection and continue through deployment and monitoring.

### Common Risk Categories

Accuracy risk: the output is wrong, incomplete, out of date, or unsupported by evidence.

Equity risk: the system performs worse for a subgroup, language community, rural area, disability group, Tribal community, or underrepresented population.

Privacy and security risk: sensitive data are exposed to an inappropriate tool, vendor, model, or user.

Operational risk: staff over-trust the system, workarounds emerge, or responsibilities become unclear.

Transparency risk: the public cannot understand when AI is used, what humans decide, or how to raise concerns.

### Mitigation Practices

Use risk tiers so higher-impact systems receive deeper review, documentation, validation, and monitoring.

Require human review, source verification, and documented decision ownership.

Test outputs with realistic public health examples before use.

Monitor errors, incidents, complaints, subgroup performance, and drift after deployment.

### Governance Triggers

Escalate to governance when AI affects public communication, eligibility, enforcement, surveillance prioritization, resource allocation, clinical or care coordination decisions, or community trust.

Pause or retire systems when risk controls fail, performance changes, or the use no longer aligns with agency principles.

### Why This Matters for Your Practice

Responsible AI risk management is not a one-time checklist. Public health risks change as data, models, vendors, disease patterns, staff behavior, and community needs change. Agencies need repeatable risk review methods that can be used before approval and after deployment.

### Reflection Questions

What harms could occur if the AI output is wrong, biased, delayed, misunderstood, or over-trusted?

What data, populations, or workflows are most vulnerable to error?

What conditions should trigger pause, review, correction, or retirement?

### Practical Exercise

Select a proposed AI use case and identify risks across accuracy, privacy, security, equity, transparency, workforce burden, legal authority, and public trust. Define one mitigation for each risk.

### Expected Takeaways

Risk register

Mitigation plan

Incident escalation criteria

### Risk Is Operational

Generative and agentic AI risks are especially consequential in public health because errors can affect trust, equity, privacy, resource allocation, and public communication.

### Limitations, Risks, and Mitigations

Hallucination - AI can generate plausible-sounding but incorrect information. - Require human adjudication before consequential action.

Performance degradation with complexity - Accuracy can drop as tasks become more complex or ambiguous. - Match AI tools to bounded tasks and validate before deployment.

Data and representational bias - Models trained on non-representative data can underperform for underrepresented populations. - Assess data provenance and monitor subgroup performance continuously.

Privacy and data sovereignty - Sending protected or sensitive data to unsuitable tools can violate HIPAA or tribal data sovereignty principles. - Use appropriate legal agreements, access controls, and approved environments.

Automation bias - Staff may reduce critical scrutiny after working with AI outputs over time. - Use audits, review checkpoints, training, and governance reporting.

### References and Resources

NIST AI Risk Management Framework. Core framework for identifying, measuring, managing, and governing AI risk. https://www.nist.gov/itl/ai-risk-management-framework

HHS Civil Rights and AI. Civil rights and nondiscrimination considerations for AI in health and human services. https://www.hhs.gov/civil-rights/for-individuals/special-topics/ai/index.html

WHO: Ethics and governance of artificial intelligence for health. Health AI risk, equity, transparency, and accountability guidance. https://www.who.int/publications/i/item/9789240029200

## AI as a Public Health Systems Shift

AI changes public health infrastructure, workforce expectations, policy, data systems, procurement, public trust, communications, surveillance, and service delivery.

AI adoption changes the operating system of a public health department. It affects data infrastructure, workforce expectations, procurement, governance, legal review, public communication, quality improvement, emergency response, and community trust.

When AI is treated as a one-off tool purchase, departments can end up with disconnected pilots, uneven safeguards, unclear ownership, and unsustainable costs. A systems-shift approach connects AI work to existing modernization, equity, workforce, and accountability priorities.

Your training should help leaders and staff see dependencies. A use case may require governance approval, data quality improvements, staff training, vendor review, funding, public notice, and monitoring before it can responsibly move forward.

### Module Overview

AI adoption is a systems change for public health departments. It affects data modernization, procurement, workforce roles, governance authority, legal review, community engagement, communications, emergency response, program operations, and evaluation. Treating AI as a one-time technology purchase leaves agencies with fragmented pilots and unmanaged risk.

### Systems Affected

Data systems need quality checks, access rules, documentation, interoperability, and appropriate AI environments.

Workforce systems need training, role clarity, bridge professionals, change support, and leadership expectations.

Governance systems need intake, risk review, approval, monitoring, incident response, and policy updates.

Community systems need transparency, plain-language explanation, feedback pathways, and attention to missing voices.

### Planning Implications

Sequence adoption through plays rather than approving isolated pilots.

Connect AI planning to data modernization, workforce development, funding, procurement, and quality improvement.

Identify where existing policies can be extended and where AI-specific standards are needed.

Avoid pilots that cannot be sustained, monitored, evaluated, or governed.

### Leadership Role

Leaders should set the expectation that responsible AI is mission infrastructure, not a side project.

Executive sponsors should ensure governance has authority, staff have time, and public accountability is built into decisions.

### Why This Matters for Your Practice

AI changes public health infrastructure, not just individual tasks. Departments need to align AI adoption with data modernization, workforce development, procurement, legal review, community engagement, funding, and evaluation so AI does not become a series of disconnected pilots.

### Reflection Questions

Which agency systems must change for AI to be governed and sustained?

Where do existing policies already apply, and where are AI-specific standards needed?

How will leadership coordinate AI work across programs rather than approving isolated tools?

### Practical Exercise

Create a systems map showing how AI adoption affects governance, data, technology, workforce, procurement, communications, equity, and funding. Identify gaps that must be addressed before pilots scale.

### Expected Takeaways

AI systems-change map

Cross-program implementation dependencies

Leadership decision agenda

### Beyond Tool Adoption

AI should be treated as a public health systems shift. It affects how agencies govern information, structure work, communicate with the public, procure technology, train staff, and maintain trust.

### Why This Matters for STLTs

State, tribal, local, and territorial public health departments often operate under constrained budgets, changing legal requirements, distributed authority, and high public accountability. Fragmented AI adoption can create uneven privacy protections, unclear ownership, duplicated vendor purchases, and inconsistent public explanations.

### Systems affected by AI

Governance and decision authority.

Data modernization, interoperability, and data quality.

Workforce roles, AI literacy, and change management.

Procurement, vendor oversight, cybersecurity, and public records obligations.

Community trust, transparency, and public accountability.

Monitoring, incident reporting, continuous improvement, and system retirement.

### References and Resources

ASPPH AI Framework Report. Frames AI as a public health systems issue rather than a narrow technology purchase. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

CDC STLT resources. State, tribal, local, and territorial public health implementation context. https://www.cdc.gov/public-health-gateway/php/index.html

Public Health Infrastructure Grant. Workforce, data systems, organizational capacity, and equity investments that can support responsible AI readiness. https://www.cdc.gov/infrastructure-phig/php/index.html

## AI as a Digital Determinant of Health

AI can shape access to services, quality of information, exposure to misinformation, eligibility decisions, language access, public benefits, and community trust.

AI can influence health by shaping digital access to information, services, outreach, and decision pathways. If an AI-supported process is hard to understand, unavailable in needed languages, inaccessible to people with disabilities, or based on incomplete data, it can widen existing inequities.

Departments should evaluate AI as part of the broader digital environment people must navigate. A chatbot, risk score, translation tool, scheduling system, or eligibility-support process may affect whether someone receives timely, understandable, and fair support.

Your training should ask staff to identify who may be excluded or burdened by a proposed AI use. The answer should inform design, engagement, alternatives, and monitoring before launch.

### Module Overview

AI can become a digital determinant of health because it shapes how people receive information, access services, are prioritized for outreach, experience language access, or are affected by automated decisions. Departments should examine whether AI-supported systems make services more reachable and fair, or whether they create new barriers.

### Where Digital Determinants Appear

Chatbots, eligibility tools, translation systems, online appointment systems, risk scores, outreach lists, public dashboards, and complaint intake tools.

Public health messaging that is generated, translated, personalized, or targeted with AI.

Vendor systems that embed AI into case management, inspection, contact center, or analytics platforms.

### Equity Review Questions

Who benefits from the tool, and who might be excluded because of language, disability, broadband, device access, trust, literacy, geography, or data representation?

Does the tool work for rural, Tribal, immigrant, older adult, disability, low-literacy, and limited-English-proficiency communities?

Can people receive help, appeal errors, correct information, or use a non-AI pathway?

### Action Steps

Include digital access and language access in use case prioritization.

Test public-facing outputs with affected users before launch.

Monitor service access, complaints, correction requests, and subgroup outcomes after deployment.

### Why This Matters for Your Practice

AI can influence whether people receive understandable information, timely services, fair prioritization, language access, or meaningful alternatives. Departments should treat AI-supported workflows as part of the digital environment that shapes health access and trust.

### Reflection Questions

Who might be excluded by the data, interface, language, channel, or workflow?

Does the AI-supported process create or reduce barriers to services?

What non-digital or non-AI alternative is available for important services?

### Practical Exercise

Review a public-facing AI use case and identify access barriers related to language, disability, broadband, device access, literacy, rural context, trust, and data representation.

### Expected Takeaways

Digital access impact review

Language and accessibility mitigation plan

Alternate pathway documentation

### AI and Digital Determinants of Health

AI can become part of the digital environment that affects health and access to public health services. It can influence who receives information, how quickly services are delivered, which languages are supported, which risks are surfaced, and which communities are overlooked.

### Public Health Implications

A tool that improves efficiency for one group may create new barriers for another. Agencies should review AI-enabled workflows for broadband access, digital literacy, disability access, language access, immigration-related trust concerns, rural context, tribal data sovereignty, and misinformation exposure.

### Questions to ask

Who benefits from this AI-supported workflow and who may be excluded?

Does the workflow depend on digital access, English proficiency, stable housing, or complete records?

Could AI outputs affect access to services, benefits, outreach, enforcement, or public guidance?

How will the agency detect inequitable effects after launch?

### References and Resources

HHS Civil Rights and AI. Civil rights context for AI-enabled access, language, disability, and service equity concerns. https://www.hhs.gov/civil-rights/for-individuals/special-topics/ai/index.html

ASPPH AI Framework Report. Human-centered AI, missing voices, public trust, and equity framing. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

CDC Health Equity. Public health equity context for assessing AI-supported workflows. https://www.cdc.gov/healthequity/

## Human-Centered AI

Human-centered AI keeps you and other public health professionals, affected communities, and accountable decision-makers at the center of design, review, and action.

Human-centered AI keeps people at the center of design and accountability. In public health, this includes staff who use the system, leaders who are responsible for decisions, partners who depend on agency information, and communities affected by the workflow.

The purpose of human-centered AI is not simply to keep a human somewhere in the loop. It is to define meaningful human authority: who reviews outputs, who can override recommendations, who explains decisions, and how people can raise concerns or correct errors.

Your training should focus on decision rules. For every AI-supported workflow, you should be able to say what AI may do, what it may not do, what humans must approve, and how concerns will be escalated.

### Module Overview

Human-centered AI begins with the people affected by a workflow: public health staff, community members, partners, and decision-makers. The goal is not to automate as much as possible. The goal is to improve public health work while preserving human judgment, relationships, dignity, explainability, and accountability.

### Design Principles

Start with a public health problem and affected users, not with a tool.

Define what humans must decide, approve, explain, or correct.

Make AI outputs reviewable, editable, and contestable.

Design for the staff who will use the system and the communities who may be affected by it.

### Workflow Practices

Name the decision owner for every AI-supported workflow.

Require expert review before public-facing communication, enforcement, resource allocation, or clinical/care coordination action.

Document correction, appeal, complaint, and escalation pathways.

Evaluate whether the tool reduces burden or simply moves burden to different staff or communities.

### Community Accountability

Use engagement to identify concerns before launch, especially for high-impact or community-facing systems.

Explain AI use in plain language and invite feedback.

Avoid deploying systems where affected people cannot understand or challenge the outcome.

### Why This Matters for Your Practice

Human-centered AI keeps public health purpose, staff expertise, and community accountability at the center. This is especially important when AI affects outreach, communication, prioritization, inspections, surveillance, or services.

### Reflection Questions

Who is affected by the workflow and who has been consulted?

What decision remains with a named human owner?

How can people ask questions, correct information, or challenge an outcome?

### Practical Exercise

For one proposed use case, write a human decision rule that defines what AI may support, what it may recommend, what a human must approve, and what the AI may not do.

### Expected Takeaways

Human decision rule

User and community needs summary

Appeal, correction, or feedback pathway

### Definition

Human-centered AI is designed to assist people, not displace accountability. Public health staff, communities, and accountable leaders remain responsible for interpretation, judgment, relationship-building, and consequential decisions.

### Operational Rule

For each use case, define what AI may do, what it may not do, who reviews outputs, who makes the final decision, how decisions are documented, and how people can challenge or correct an AI-supported outcome.

### Required safeguards

Named human owner for every consequential decision.

Human review before public communication, enforcement, service denial, escalation, or clinical/public health action.

Audit trail showing AI output, human review, decision, and rationale.

Correction or appeal pathway when people are affected.

Monitoring for automation bias and over-trust.

### References and Resources

Blueprint for an AI Bill of Rights. Principles for automated systems that preserve human agency, notice, explanation, and safeguards. https://bidenwhitehouse.archives.gov/ostp/ai-bill-of-rights/

NIST AI Risk Management Framework. Useful for defining human oversight, decision accountability, and risk controls. https://www.nist.gov/itl/ai-risk-management-framework

ASPPH AI Framework Report. Public health-specific framing for human-centered AI and accountable implementation. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

## AI Literacy for Public Health Staff

AI literacy means you can recognize AI use, understand major failure modes, protect sensitive data, communicate uncertainty, document use, and know when not to use AI.

AI literacy is a baseline workforce skill for responsible adoption. You may not need the same level of technical expertise, but everyone using or overseeing AI should understand approved uses, prohibited data, common failure modes, and escalation expectations.

Role-based literacy matters. Executives need to understand governance and risk. Program colleagues need workflow and review guidance. Analysts need validation and monitoring practices. Procurement staff need vendor and contract questions. Communications staff need standards for public-facing content.

Your training should give staff practical confidence: how to use approved tools, how to protect sensitive data, how to check outputs, how to document AI assistance, and when to stop and ask for review.

### Module Overview

AI literacy is a workforce capability. You should know what AI is, what it is approved for, what data may be used, how outputs can fail, how to document AI use, and when to escalate concerns. Literacy expectations should be role-based because leaders, program colleagues, analysts, IT, privacy, procurement, communications, and governance members have different responsibilities.

### Core Competencies

Recognize approved and unapproved AI use.

Protect PHI, confidential, restricted, and sensitive data.

Identify hallucination, bias, automation bias, data quality problems, and inappropriate use.

Use prompts, source materials, and review steps responsibly.

Document AI-assisted work when required by agency policy.

### Role-Based Training

Executives need governance, risk, resource, and public accountability orientation.

Program colleagues need workflow, privacy, prompt, and review guidance.

Analysts need validation, documentation, model monitoring, and data quality practices.

Communications staff need plain-language, misinformation, translation, and public review standards.

Procurement and legal staff need vendor, contract, audit, and data-rights requirements.

### Sustainment

Refresh training as tools, policies, and risks change.

Create reporting pathways for staff concerns and near misses.

Use AI champions or bridge professionals to support day-to-day adoption.

### Why This Matters for Your Practice

AI literacy is necessary for safe use at every level of the department. Staff need role-appropriate knowledge before they are asked to use AI tools, review outputs, approve vendors, participate in governance, or explain AI to the public.

### Reflection Questions

What does each role need to know to use or oversee AI responsibly?

How will the department train new staff and refresh training over time?

How will staff report concerns, near misses, or unsafe outputs?

### Practical Exercise

Create a role-based training matrix for executives, program colleagues, analysts, IT, privacy, procurement, communications, and governance members.

### Expected Takeaways

Role-based AI literacy matrix

Training plan

Staff concern reporting pathway

### What AI Literacy Means

AI literacy is the ability to recognize AI use, understand what a system can and cannot do, evaluate outputs critically, protect sensitive information, communicate uncertainty, and know when AI should not be used.

### Role-Based Expectations

All staff need basic awareness, but supervisors, communications staff, epidemiologists, data analysts, procurement staff, IT/security staff, legal/privacy staff, equity staff, and governance members need different depth and practice examples.

### Core staff competencies

Recognize generative, predictive, and agentic AI use.

Avoid entering PHI, confidential, or restricted data into unapproved tools.

Check outputs for hallucinations, bias, missing context, and unsupported claims.

Document AI assistance when required by policy.

Escalate concerns through governance or incident reporting pathways.

### References and Resources

ASPPH AI Framework Report. AI literacy, bridge professional, and workforce preparation concepts for public health. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

Public Health Foundation TRAIN Learning Network. Training platform for public health workforce development. https://www.train.org/

CDC Public Health Workforce Development. Public health workforce training and capability-building context. https://www.cdc.gov/workforce/

## Automation Bias and Over-Trust

Automation bias occurs when people accept AI outputs too readily because they appear confident, precise, or authoritative.

Automation bias occurs when people accept AI outputs too readily because they appear confident, precise, or efficient. In public health, this can affect surveillance triage, inspection documentation, outreach prioritization, public messaging, or leadership briefings.

Your training should make critical review a normal part of AI-supported work. You should learn to look for missing context, unsupported claims, outdated assumptions, subgroup effects, and uncertainty that may not be obvious in a polished output.

Departments can reduce automation bias by requiring review prompts, second checks for high-impact outputs, decision-owner sign-off, override documentation, and periodic audits of AI-assisted work.

### Module Overview

Automation bias occurs when people give too much weight to AI output because it appears confident, precise, or authoritative. In public health, this can affect surveillance review, risk scoring, inspection documentation, prioritization, public messaging, or resource decisions. Deliberate review practices are needed so AI supports, rather than substitutes for, professional judgment.

### Warning Signs

Staff stop checking sources because AI summaries are usually fluent.

Risk scores become the primary basis for decisions without review of context.

Draft messages are approved without checking public health guidance, equity implications, or local context.

A workflow lacks a named human decision owner.

### Controls

Use second-review requirements for high-impact outputs.

Require confidence, limitation, source, and uncertainty notes in briefs.

Separate AI recommendations from human decisions in documentation.

Train staff to look for omissions, unsupported claims, and plausible but wrong details.

### Monitoring

Audit samples of AI-assisted work.

Track overrides, corrections, incidents, complaints, and false positives or false negatives.

Review whether staff are using the tool as intended or developing unsafe shortcuts.

### Why This Matters for Your Practice

Automation bias is a practical operational risk. Staff may over-trust outputs that are fluent, precise, or repeated often. Public health workflows need review steps that make skepticism normal and expected.

### Reflection Questions

Where might staff accept AI output too quickly?

What second-review or sign-off is needed for high-impact outputs?

How will overrides, corrections, and disagreements be documented?

### Practical Exercise

Take one AI-assisted output and design a review form that asks staff to check sources, uncertainty, missing context, subgroup impact, and whether the recommendation should be accepted, modified, or rejected.

### Expected Takeaways

Automation bias review checklist

Decision owner sign-off process

Override and correction log

### Definition

Automation bias occurs when people over-rely on AI outputs because the system appears fast, confident, technical, or authoritative. Over-trust can be especially risky in high-pressure public health settings.

### Prevention

Workflows should require reviewers to check source evidence, local context, limitations, uncertainty, and subgroup impacts. Reviewers should have permission and time to disagree with AI outputs.

### Design controls

Display limitations and uncertainty with AI outputs.

Require evidence links or source material for factual summaries.

Use second review for high-impact decisions.

Track cases where staff override or correct AI outputs.

Train staff to ask what evidence would change the recommendation.

### References and Resources

NIST AI Risk Management Framework. Risk controls for over-trust, human review, testing, and monitoring. https://www.nist.gov/itl/ai-risk-management-framework

HHS Civil Rights and AI. Equity and civil rights considerations when automated systems influence decisions. https://www.hhs.gov/civil-rights/for-individuals/special-topics/ai/index.html

WHO: Ethics and governance of artificial intelligence for health. Health AI ethics guidance addressing human autonomy and oversight. https://www.who.int/publications/i/item/9789240029200

## Missing Voices in Data

Missing voices analysis asks whose experiences, records, language needs, disability access needs, rural context, tribal sovereignty interests, or community knowledge are absent from the data.

Missing voices analysis asks whose experiences, data, language needs, disability access needs, geography, or community knowledge are absent from the design and evaluation of an AI-supported workflow. It is a practical equity tool, not a theoretical exercise.

A model may perform well overall while failing groups that are underrepresented or misclassified. A communication tool may be readable for some audiences but not others. A prioritization workflow may reflect historical service patterns rather than current need.

Your training should help staff identify missing voices early, decide who should be consulted, and define how the department will monitor whether the AI-supported workflow works across affected communities.

### Module Overview

Missing voices analysis asks who is absent from the data, design process, validation testing, governance discussion, or evaluation. Public health AI can look accurate overall while failing groups that are underrepresented, misclassified, or affected differently by the workflow. Missing voices review should happen before use case approval and again during monitoring.

### Who May Be Missing

People with limited English proficiency, people with disabilities, rural residents, people experiencing homelessness, immigrant communities, Tribal communities where applicable, older adults, children, justice-involved populations, and groups with limited digital access.

Frontline staff who understand workflow realities but are not included in planning.

Community partners who can identify trust, access, or cultural context concerns.

### How to Apply It

Review whether source data include the populations affected by the decision or communication.

Ask whether subgroup performance will be tested before and after deployment.

Use community validation when the workflow has public-facing or community-impacting consequences.

Document what groups were consulted, what concerns were raised, and how the design changed.

### Ongoing Monitoring

Track subgroup performance, service access, complaints, corrections, and unintended impacts.

Revisit the analysis when the model, data, policy, population, or workflow changes.

### Why This Matters for Your Practice

Missing voices analysis helps agencies avoid designing AI systems around only the data and perspectives that are easiest to obtain. It is essential for equity, trust, and real-world performance.

### Reflection Questions

Whose data, experience, language needs, disability access needs, rural context, or community knowledge may be missing?

Who should validate assumptions before launch?

How will subgroup performance and community concerns be monitored after deployment?

### Practical Exercise

For a selected use case, identify groups that may be missing from the data, planning process, validation sample, or governance review. Define how each gap will be addressed.

### Expected Takeaways

Missing voices analysis

Community validation plan

Subgroup monitoring measures

### Definition

Missing voices analysis identifies people, communities, settings, and forms of knowledge that are absent or poorly represented in the data, design process, validation evidence, or monitoring plan.

### Why It Matters

An AI system may perform acceptably in aggregate while failing for small populations, rural communities, tribal communities, immigrants, people with disabilities, people with limited English proficiency, people experiencing homelessness, or communities with incomplete records.

### Review focus

Groups missing or underrepresented in source data.

Language, accessibility, and digital access barriers.

Tribal sovereignty and community data governance concerns.

Historical underreporting, misclassification, and mistrust.

Subgroup validation and monitoring plans.

### References and Resources

ASPPH AI Framework Report. Introduces missing voices and human-centered AI considerations for public health. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

CDC Health Equity. Health equity context for identifying who may be missed or harmed by public health systems. https://www.cdc.gov/healthequity/

NIH Tribal Health Research Office. Tribal data sovereignty and tribal health research context. https://dpcpsi.nih.gov/thro

## Public Transparency and Community Trust

Public health agencies should be able to explain when AI is used, why it is used, what data are involved, what humans decide, and how concerns can be raised.

Transparency is central to public trust. Health departments should be able to explain when AI is used, why it is used, what data are involved, what humans decide, what safeguards exist, and how people can ask questions or raise concerns.

Transparency should be proportionate to the impact of the AI use. An internal drafting tool may need staff-facing documentation, while a public-facing chatbot, prioritization tool, or outreach workflow may require public notice, FAQs, and feedback pathways.

Your training should help staff write clear explanations without overstating AI capability. A useful notice explains the workflow in plain language and names the human accountability structure.

### Module Overview

Transparency helps protect public trust. Public health departments should be able to explain when AI is used, why it is used, what data are involved, what humans decide, what safeguards exist, and how people can raise concerns or seek correction. Transparency should be proportional to risk and understandable to the affected audience.

### What to Explain

The public health purpose of the AI-supported activity.

Whether AI drafts, summarizes, prioritizes, routes, predicts, translates, or recommends.

What data types are involved and what data are not used.

Who reviews outputs and who makes final decisions.

How people can ask questions, report concerns, or request correction.

### Formats

Public AI use notices for community-facing systems.

FAQs for staff, partners, and affected communities.

Plain-language summaries for governing boards, advisory committees, and public meetings.

Internal records in the AI inventory and governance documentation.

### Trust-Building Practices

Be clear about limitations and human oversight rather than overstating AI capability.

Avoid vague claims such as 'AI-powered' without explaining what the system actually does.

Update notices when use, data, vendor, or risk level changes.

### Why This Matters for Your Practice

Public trust depends on whether agencies can explain AI use clearly. Transparency should not be a vague notice that AI exists; it should explain purpose, data, human review, limits, safeguards, and feedback options.

### Reflection Questions

What should staff, partners, and the public know about this AI use?

What information can be shared without compromising privacy or security?

How will notices be updated when the AI use changes?

### Practical Exercise

Draft a plain-language AI use notice for one public-facing workflow. Include purpose, what AI does, what humans decide, data types, safeguards, limitations, and contact or correction options.

### Expected Takeaways

Plain-language AI use notice

Public FAQ

Feedback and correction process

### Plain-Language Transparency

Public health agencies should be able to explain when AI is used, what purpose it serves, what data are involved, what humans still decide, what the system cannot do, and how questions or concerns can be raised.

### Trust and Accountability

Transparency is not a marketing statement. It is part of accountability, especially when AI-supported workflows affect public communication, eligibility, prioritization, surveillance, inspections, outreach, or community-facing decisions.

### Public notice elements

What AI-supported system or workflow is being used.

Why the department is using it.

What data are used and what data are not used.

How human review and final decision-making work.

Known limitations, risks, and safeguards.

How people can ask questions, request help, or report concerns.

### References and Resources

Blueprint for an AI Bill of Rights. Notice, explanation, and alternatives principles for automated systems. https://bidenwhitehouse.archives.gov/ostp/ai-bill-of-rights/

ASPPH AI Framework Report. Public transparency, trust, and community accountability expectations. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

NIST AI Risk Management Framework. Governance and transparency concepts for trustworthy AI. https://www.nist.gov/itl/ai-risk-management-framework

## Tiered Data Use for AI

Tiered data use classifies information by sensitivity and defines which AI environments are appropriate for public, internal, confidential, and highly restricted data.

Tiered data use turns privacy and security principles into practical rules. Staff need to know which data can be used in public tools, enterprise tools, restricted environments, or only within tightly governed systems.

Public health departments handle many categories of information, including public materials, internal drafts, confidential operational records, protected health information, partner data, and data governed by specific community or Tribal authorities. Each category may require different approvals and safeguards.

Your training should use realistic scenarios so staff can classify data correctly and choose the appropriate AI environment. The goal is to prevent accidental disclosure and to make safe use easier than unsafe use.

### Module Overview

Tiered data use gives staff practical rules for which AI environments can be used with which kinds of information. Public, internal, confidential, protected, restricted, and sovereign data may require different tools, approvals, vendors, contracts, security controls, and documentation. Without tiers, staff may unintentionally place sensitive data in inappropriate AI systems.

### Data Tiers

Public information that can be used in approved public or enterprise tools.

Internal information that should stay within approved organizational environments.

Confidential or sensitive operational data that require restricted access and review.

Protected health information or legally protected records that require HIPAA, security, contractual, and minimum-necessary controls.

Tribal or sovereign data, when applicable, that require governance by the appropriate Tribal authority.

### Operational Rules

Define which AI tools are approved for each data tier.

Require data use agreements, business associate agreements, or vendor addenda when needed.

Prohibit restricted information in public consumer AI tools.

Document data sources, retention, access, and model-training restrictions.

### Implementation Steps

Train staff using real examples from their workflows.

Include tiered data review in intake, procurement, governance, and incident response.

Review vendor claims about data retention, training, logging, and deletion.

### Why This Matters for Your Practice

Clear data tiers turn privacy and security rules into daily practice. Staff need to know which data can be used in which AI environments, what approvals are needed, and what tools are prohibited for sensitive information.

### Reflection Questions

What data tiers does the department use?

Which AI tools are approved for each tier?

What vendor, contract, logging, retention, and training restrictions are required?

### Practical Exercise

Create a table that maps public, internal, confidential, protected, restricted, and sovereign data categories to approved AI environments and required review steps.

### Expected Takeaways

Tiered data classification table

Approved AI environment list

Data-use approval pathway

### Purpose

Tiered data use gives staff clear rules for which data can be used with which AI tools. It prevents accidental disclosure and supports consistent decisions across programs.

### Typical Tiers

A practical framework may classify data as public, internal, confidential, or highly restricted. Highly restricted data may require in-house systems, approved enterprise tools, specific vendor terms, or complete prohibition from AI use.

### AI environment decisions

Public AI tools may be limited to public or fully de-identified content.

Enterprise AI tools may support internal drafting if contract and security terms are approved.

In-house or RAG systems may be needed for confidential reference material.

Highly restricted data require explicit privacy, legal, security, and governance approval.

Tribal data requires governance by the appropriate tribal authority.

### References and Resources

HIPAA. Privacy requirements when protected health information may be involved. https://www.hhs.gov/hipaa/index.html

FedRAMP. Cloud security authorization context for systems handling sensitive government data. https://www.fedramp.gov/

NIH Tribal Health Research Office. Tribal data governance and tribal sovereignty considerations. https://dpcpsi.nih.gov/thro

## Environmental and Resource Impacts

AI can carry energy, water, hardware, e-waste, procurement, and environmental justice implications that should be considered before scale.

AI systems can carry resource impacts related to compute, energy, water, hardware, infrastructure, and cost. These issues are not always visible to program teams, but they matter for responsible public sector decision-making and environmental justice.

Not every AI use requires the same level of review. A small drafting task has different implications than a high-volume, always-on, large-model deployment. Departments should ask whether the AI approach is proportionate to the public health value.

Your training should help staff compare alternatives. Sometimes a smaller model, retrieval-based system, existing analytic method, or non-AI workflow change may achieve the goal with less cost and burden.

### Module Overview

AI systems can require substantial compute, energy, water, hardware, and vendor infrastructure. Public health departments do not need to perform complex environmental modeling for every use, but they should consider whether a proposed AI use is proportionate to the public health value, whether lower-impact alternatives exist, and whether infrastructure burdens raise environmental justice concerns.

### Review Questions

Is the AI use necessary, or could a simpler analytic, workflow, or rule-based approach achieve the same goal?

Will the vendor disclose sustainability practices, data center location, energy use, water use, or environmental commitments?

Does the project require large-scale model training, high-volume generation, or continuous processing?

Could infrastructure siting or resource burden affect communities already experiencing environmental inequities?

### Procurement Relevance

Ask vendors for sustainability, compute, hosting, and data center information when relevant.

Compare lower-impact model sizes, retrieval approaches, or existing enterprise tools.

Include resource impacts in funding and sustainment planning.

### Decision Standard

Higher resource burden should be justified by clear public health value, governance approval, and feasible sustainment.

Environmental review should be documented for high-compute or large-scale deployments.

### Why This Matters for Your Practice

AI systems can have energy, water, hardware, cost, and environmental justice implications. Departments should consider whether the public health value of a high-compute use justifies its resource burden and whether lower-impact alternatives exist.

### Reflection Questions

Is AI necessary for this task, or would a simpler approach work?

What sustainability and infrastructure information should vendors disclose?

Could resource burdens affect communities already facing environmental inequities?

### Practical Exercise

Review one proposed AI project and compare a high-compute option, a smaller model or RAG option, and a non-AI option. Document benefits, limitations, costs, and resource implications.

### Expected Takeaways

Environmental and resource impact review

Lower-impact alternatives comparison

Procurement sustainability questions

### Why It Belongs in Public Health

AI systems can consume substantial energy, water, hardware, and cloud resources. These impacts are public health concerns when they intersect with environmental justice, climate resilience, procurement, and community burden.

### Practical Review

Most agency reviews can be lightweight: identify whether the use is compute-intensive or vendor-hosted, ask about sustainability and data center practices, consider lower-impact alternatives, and document whether the public health value justifies the resource burden.

### Review factors

Energy and water intensity of the AI service.

Hardware, e-waste, and cloud infrastructure implications.

Data center location and environmental justice concerns.

Vendor sustainability commitments and reporting.

Lower-impact alternatives such as smaller models, retrieval systems, or workflow redesign.

### References and Resources

ASPPH AI Framework Report. Resource, public health systems, and responsible AI framing. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

EPA Environmental Justice. Environmental justice context for reviewing infrastructure, procurement, and community burden. https://www.epa.gov/environmentaljustice

NIST AI Risk Management Framework. Risk management structure for documenting environmental and operational tradeoffs. https://www.nist.gov/itl/ai-risk-management-framework

## The AI Bridge Professional Role

The bridge professional translates across public health programs, IT, legal/privacy, procurement, vendors, leadership, data teams, and community partners.

The AI bridge professional is a role or function that helps departments translate across disciplines. Public health AI work often stalls when program needs, technical requirements, legal concerns, procurement rules, and community expectations are discussed separately.

Bridge capacity can be a dedicated position, a shared role, or a team function. What matters is that someone is responsible for connecting workflows, governance materials, data constraints, vendor claims, staff training, and implementation realities.

Your training should help departments identify where bridge work is needed. Smaller agencies may need regional support, shared services, or designated staff with protected time rather than a new full-time position.

### Module Overview

The AI bridge professional is a role or function that connects public health programs, data teams, IT, privacy, legal, procurement, vendors, leadership, and community partners. This role helps translate public health needs into technical requirements and technical risks into practical governance and implementation decisions.

### Core Responsibilities

Help programs define use cases, workflow needs, success measures, and documentation requirements.

Coordinate governance submissions, risk review, stakeholder engagement, and procurement questions.

Translate model limitations, data quality issues, validation findings, and vendor claims for nontechnical audiences.

Support staff training, change management, and implementation troubleshooting.

### Where the Role Fits

During readiness assessment to identify capacity gaps.

During governance to prepare complete intake and review materials.

During prioritization to compare public health value, feasibility, and risk.

During deployment to coordinate training, monitoring, and incident escalation.

### Staffing Models

A large department may create a dedicated role or small AI implementation office.

A smaller department may assign bridge responsibilities to an informatics, quality improvement, data modernization, or program leader with protected time.

Regional or shared-service models may support multiple jurisdictions.

### Why This Matters for Your Practice

Many AI problems are translation problems: program needs do not automatically become technical requirements, and technical risks do not automatically become operational controls. Bridge professionals help keep AI implementation coherent across teams.

### Reflection Questions

Who can translate between program, data, IT, privacy, procurement, legal, equity, communications, vendors, and leadership?

What authority and protected time does the bridge role need?

How will bridge work be sustained in smaller departments?

### Practical Exercise

Define the bridge role for one AI project. Identify responsibilities during intake, governance review, procurement, implementation, staff training, monitoring, and issue escalation.

### Expected Takeaways

Bridge professional role description

Cross-functional coordination map

Implementation support responsibilities

### Role Definition

The AI bridge professional is a public health translator: someone with enough technical understanding to work with IT and vendors, enough program knowledge to understand workflows, and enough communication skill to support leadership, governance, and community conversations.

### Why Agencies Need This Role

AI projects often fail at handoffs between program goals, data realities, legal constraints, vendor claims, staff concerns, and community expectations. A bridge role helps turn those handoffs into documented decisions.

### Common responsibilities

Translate use case needs into governance and technical requirements.

Help staff document workflows, risks, data needs, and human review points.

Coordinate between program owners, IT, legal/privacy, procurement, equity, and vendors.

Support AI literacy, change management, and community-facing explanations.

Track unresolved questions and route them to the right decision-makers.

### References and Resources

ASPPH AI Framework Report. Bridge professional concept and AI workforce implications. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

Public Health Foundation TRAIN Learning Network. Training infrastructure for building cross-functional workforce capacity. https://www.train.org/

CDC STLT Data Connection. Peer-learning context for public health data modernization and implementation support. https://www.cdc.gov/data-modernization/php/stlt-data-connection/index.html

## Federal Funding Opportunities

AI work can often be positioned as a capability layer on top of data modernization, infrastructure, workforce, and equity investments.

Funding strategy should make the full cost of responsible AI visible. Software is only one cost. Departments may also need data modernization, integration, security review, staff training, governance time, evaluation, monitoring, accessibility support, translation, and community engagement.

AI work can often align with existing public health investment priorities such as data modernization, workforce capacity, emergency preparedness, health equity, communications, and service delivery. The key is to connect the AI use case to a real public health capability need.

Your training should prepare staff to avoid unfunded pilots. A responsible funding plan explains what is needed for planning, pilot, scale, and sustainment, and what happens when short-term funding ends.

### Module Overview

AI projects need funding for more than software licenses. Responsible implementation may require data modernization, cloud or secure infrastructure, staff time, training, governance, legal and procurement review, evaluation, monitoring, translation, accessibility, community engagement, and sustainment. Funding strategy should be developed before pilots are approved for scale.

### Funding Alignment

Position AI as an enabling capability within data modernization, workforce, equity, emergency preparedness, surveillance, communications, and service delivery investments.

Match use cases to allowable costs in DMI, PHIG, HRSA, FEMA, EPA, SAMHSA, NIH, NSF, or state and local funding streams when appropriate.

Avoid creating pilots that cannot be maintained after short-term funds end.

### Budget Categories

Technology licenses, hosting, security review, integration, and vendor support.

Staff time for governance, implementation, training, monitoring, and evaluation.

Community engagement, accessibility, translation, and communications support.

Evaluation, model monitoring, incident response, and policy maintenance.

### Sustainment Questions

Who pays after the pilot?

What staffing is required to keep the system safe and useful?

What costs increase if the system scales across programs or jurisdictions?

What functions can be shared regionally or through partnerships?

### Why This Matters for Your Practice

AI projects often require resources that are easy to overlook: staff time, governance, training, validation, data modernization, monitoring, accessibility, community engagement, and sustainment. Funding strategy should make the full cost of responsible implementation visible.

### Reflection Questions

What costs are required before pilot, during deployment, and after scale?

Which funding streams align with data, workforce, equity, emergency response, surveillance, or service delivery goals?

What happens when short-term funding ends?

### Practical Exercise

Build a funding map for one approved use case that includes pilot costs, scale costs, sustainment costs, staffing, evaluation, governance, and possible funding sources.

### Expected Takeaways

Funding alignment table

Sustainment plan

Budget categories for responsible AI implementation

### Funding Strategy

Public health departments do not need to fund AI from scratch. AI can often be positioned as a capability layer on top of data modernization, workforce, infrastructure, equity, and evaluation investments.

### DMI and PHIG

CDC Data Modernization Initiative investments can support interoperable, cloud-ready, standards-based infrastructure. Public Health Infrastructure Grant resources can support workforce, data systems, organizational capacity, and health equity work needed for responsible AI.

### Reference Table

CDC Data Modernization Initiative - Shared data infrastructure, cloud environments, APIs, standards, and AI-ready data pipelines.

Public Health Infrastructure Grant - AI-related workforce, governance capacity, data systems, organizational change, and equity monitoring.

HRSA digital health and telehealth programs - Patient communication drafting, document search, and health equity analysis.

NIH / NSF smart health programs - Research partnerships, model evaluation, fine-tuning, and agentic system development.

SAMHSA technology-based services - Early identification, intervention support, client communication, and care coordination.

EPA environmental justice grants - GeoAI, environmental health analysis, and heat risk mapping.

FEMA emergency management grants - Disaster resilience and agentic outbreak forecasting workflows.

### References and Resources

CDC Data Modernization Initiative. Potential alignment for data infrastructure and AI-ready modernization investments. https://www.cdc.gov/surveillance/data-modernization/index.html

Public Health Infrastructure Grant. Potential alignment for workforce, data systems, organizational capacity, and equity investments. https://www.cdc.gov/infrastructure-phig/php/index.html

HRSA Telehealth Programs. Potential alignment for digital health, telehealth, and access-related AI use cases. https://www.hrsa.gov/rural-health/telehealth

## Procurement and Vendor Oversight

AI procurement requires public health departments to evaluate vendor claims, contract terms, data rights, model documentation, auditability, accessibility, cybersecurity, support, and exit plans before an AI-enabled product is approved.

Vendor oversight is a public health governance issue, not only a purchasing task. A product may look efficient in a demonstration but still create risks if the department cannot verify how data are used, how outputs are produced, how errors are handled, or how the system can be audited.

You should be trained to ask practical questions before procurement moves forward. What decision or workflow will the tool affect? What data are involved? Who owns the output? What performance evidence exists for populations similar to the department's communities? What contract terms protect the department if the system fails?

This module prepares you to use procurement as a safeguard. Strong procurement requirements can turn responsible AI principles into enforceable vendor obligations.

### Module Overview

Public health departments often encounter AI through vendor platforms, not custom-built internal systems. Procurement staff, program owners, IT, security, privacy, legal, and governance members need shared criteria for evaluating vendor claims before contracts are signed or pilots begin.

### What Staff Should Look For

Clear description of what AI capability is included and whether it is generative, predictive, agentic, or rules-based.

Model documentation, validation evidence, limitations, monitoring approach, and known failure modes.

Contract terms covering data ownership, data reuse, model training, audit rights, breach notification, accessibility, support, subcontractors, and termination.

Evidence that the vendor can support public-sector privacy, security, records, and procurement obligations.

### Public Health Procurement Questions

What data will the vendor receive, store, process, or use to improve models?

Can the department audit performance, errors, bias, access logs, and system changes?

What happens if the model changes, performance declines, guidance changes, or the contract ends?

How will the vendor support language access, disability access, incident response, and staff training?

### Implementation Check

Route vendor AI proposals through governance before pilot approval.

Use risk tiering to decide what validation, privacy, legal, and procurement review is required.

Do not accept vendor performance claims without evidence, test data, monitoring plans, and department review.

### Why This Matters for Your Practice

Most departments will buy or inherit AI-enabled systems before they build their own. Vendor oversight protects public health authority, data rights, security, equity, and operational continuity.

### Reflection Questions

What AI-enabled vendor tools are already in use or under consideration?

Which contract terms would prevent the department from auditing or safely exiting the system?

Who must review vendor claims before a pilot or purchase is approved?

### Practical Exercise

Review a sample AI vendor proposal and identify missing documentation, contract protections, validation evidence, data-use terms, accessibility requirements, and governance questions.

### Expected Takeaways

Vendor AI review checklist

Procurement questions for governance

Draft AI contract requirements

### References and Resources

NIST AI Risk Management Framework. Use to structure vendor risk, documentation, transparency, and accountability review. https://www.nist.gov/itl/ai-risk-management-framework

FedRAMP. Cloud security authorization context for vendor-hosted systems that may handle sensitive government data. https://www.fedramp.gov/

HHS Civil Rights and AI. Equity, nondiscrimination, and civil rights considerations for AI-enabled vendor tools. https://www.hhs.gov/civil-rights/for-individuals/special-topics/ai/index.html

## Privacy, Confidentiality, and Public Records

AI use in public health must account for PHI, PII, confidential public health records, investigation data, data-sharing limits, retention rules, and public records obligations.

Privacy training needs to be practical. You should not have to interpret complex law in the moment of writing a prompt. They need clear categories, approved tools, examples of prohibited data, and a simple escalation path when they are unsure.

Public records issues are especially important for government agencies. AI-assisted drafts, prompts, summaries, and decision notes may become part of the administrative record. Departments should decide how these materials are stored and reviewed before AI use becomes routine.

The goal is not to stop all AI use. The goal is to match the sensitivity of the data to the correct environment, review pathway, and documentation standard.

### Module Overview

AI can change where data travel, who can access them, how long they are retained, and whether outputs become records. Staff need plain-language training on what information may be used, which AI environments are approved, and when legal, privacy, records, or data-sharing review is required.

### Key Data Categories

Public information that can safely be used in approved public-facing contexts.

Internal information that may be used in enterprise tools under agency policy.

Confidential, identifiable, or protected information that requires restricted environments and review.

Highly restricted data such as investigations, legal matters, sensitive surveillance data, or data governed by special agreements.

### Public Records and Retention

AI prompts, outputs, summaries, edits, decisions, and approvals may become records depending on jurisdiction and use.

Departments should define when AI-assisted work must be retained, where it is stored, and how it is labeled.

You should avoid creating unofficial records in personal accounts or unapproved AI tools.

### Implementation Check

Classify data before selecting an AI tool.

Review data use agreements, vendor terms, retention rules, and public records obligations.

Train staff on prohibited data entry and escalation pathways for uncertain cases.

### Why This Matters for Your Practice

Privacy, confidentiality, and records controls are foundational for STLT public health AI because departments handle sensitive information, regulatory records, investigations, partner data, and public accountability obligations.

### Reflection Questions

Which types of department data should never be entered into public AI tools?

Where should AI prompts and outputs be stored when they support official work?

Who decides whether a proposed AI use requires privacy, legal, or records review?

### Practical Exercise

Sort example AI tasks into public, internal, confidential, and highly restricted data-use categories, then identify the approved AI environment and review pathway for each.

### Expected Takeaways

AI data classification examples

Privacy escalation rules

Public records documentation notes

### References and Resources

HIPAA. Federal privacy framework when protected health information may be involved. https://www.hhs.gov/hipaa/index.html

CDC Public Health Data Policy and Standards. Public health data policy and standards context for responsible data use. https://www.cdc.gov/surveillance/data-modernization/policy.html

NIST Privacy Framework. Privacy risk management structure for data processing and technology decisions. https://www.nist.gov/privacy-framework

## Model Validation and Evaluation Basics

Validation helps departments decide whether an AI system performs well enough, for the right users and populations, before it is piloted, scaled, or sustained.

Validation is not just a technical score. A technically impressive model may be inappropriate if it creates staff burden, performs poorly for certain communities, or cannot be explained well enough for public health accountability.

You should understand the difference between vendor validation, local validation, pilot evaluation, and ongoing monitoring. Vendor evidence may be useful, but the department still needs to know whether the system works in its own data, workflows, populations, and operating conditions.

This module should help you ask better questions of data scientists and vendors, and help governance groups interpret validation evidence before decisions are made.

### Module Overview

Validation is the disciplined process of checking whether an AI-supported workflow is accurate, reliable, safe, equitable, usable, and appropriate for its intended public health purpose. It should be understandable to nontechnical staff because validation results inform governance decisions.

### What Validation Should Cover

Purpose fit: whether the system solves the public health problem it is intended to support.

Performance: accuracy, false positives, false negatives, completeness, reliability, and stability.

Equity: subgroup performance, missing voices, language access, disability access, and geographic variation.

Workflow impact: staff time, burden, usability, review quality, and downstream consequences.

Safety: harmful outputs, hallucinations, unsafe recommendations, and incident triggers.

### Evaluation Over Time

Pilot evaluation should compare the AI-supported workflow to the current process.

Monitoring should continue after deployment because models, data, staff behavior, guidance, and populations change.

Governance should define thresholds for continue, revise, pause, scale, or retire decisions.

### Implementation Check

Define acceptance criteria before testing begins.

Use realistic examples and local workflow conditions.

Document limitations and do not scale until governance reviews evaluation evidence.

### Why This Matters for Your Practice

Validation protects agencies from scaling systems that are inaccurate, inequitable, poorly integrated, or untrusted by staff and communities.

### Reflection Questions

What would count as acceptable performance for this workflow?

Which groups or locations need subgroup review?

What evidence should governance require before scale-up?

### Practical Exercise

Design a validation plan for one proposed AI use case, including test examples, performance measures, subgroup checks, human review expectations, and go/no-go criteria.

### Expected Takeaways

Validation plan outline

Evaluation metric list

Governance decision thresholds

### References and Resources

NIST AI Risk Management Framework. Risk and measurement framework for validation, monitoring, and governance. https://www.nist.gov/itl/ai-risk-management-framework

WHO: Regulatory considerations on artificial intelligence for health. Health AI validation, safety, transparency, and monitoring considerations. https://iris.who.int/handle/10665/373421

HHS Civil Rights and AI. Equity and nondiscrimination considerations when AI affects health and human services. https://www.hhs.gov/civil-rights/for-individuals/special-topics/ai/index.html

## AI Incident Response

AI incident response defines how staff report, triage, investigate, correct, communicate, and document problems involving AI-supported systems or outputs.

AI incident response should feel familiar to public health departments because it builds on existing approaches to privacy, security, quality improvement, emergency response, and corrective action. What is new is the range of AI-specific failure modes that you may not recognize without training.

The most important training message is simple: if an AI output seems wrong, harmful, biased, unsafe, or outside approved use, staff should know where to report it and should not have to resolve it alone.

Incident response also supports learning. Every incident should feed back into policy updates, tool design, staff training, monitoring, and vendor oversight.

### Module Overview

AI incidents can involve incorrect outputs, privacy exposure, biased results, unsafe recommendations, unauthorized use, vendor failure, staff over-reliance, public misinformation, or model performance drift. Staff need to know what to report and what happens next.

### Incident Types

Harmful or inaccurate output used in a public health workflow.

Sensitive data entered into an unapproved AI tool or exposed through a vendor system.

Bias or disparate impact concern raised by staff, partners, or community members.

Model drift, hallucination, unsafe recommendation, or unexplained performance change.

Public-facing AI response that creates confusion, misinformation, or loss of trust.

### Response Steps

Capture the issue, system, date, user, output, data involved, and immediate risk.

Triage severity and determine whether the system should continue, be limited, paused, or shut off.

Notify privacy, security, legal, program leadership, communications, vendor, or governance contacts as appropriate.

Document corrective actions, user communications, policy updates, and evidence of closure.

### Implementation Check

Train staff to report concerns without blame.

Define emergency contacts and pause authority before deployment.

Review incidents regularly through governance and continuous improvement.

### Why This Matters for Your Practice

AI incidents can affect privacy, public trust, legal compliance, staff confidence, equity, and operational safety. A clear response pathway reduces harm and improves governance.

### Reflection Questions

What AI-related problems should staff be required to report?

Who has authority to pause an AI-supported workflow?

How will lessons from incidents update training, policy, and monitoring?

### Practical Exercise

Walk through a tabletop scenario involving an incorrect AI-generated public message or privacy exposure, then document reporting steps, escalation contacts, communications needs, corrective actions, and governance review.

### Expected Takeaways

AI incident scenario response

Escalation pathway

Corrective action log

### References and Resources

NIST AI Risk Management Framework. Governance and response structure for AI-related harms and failures. https://www.nist.gov/itl/ai-risk-management-framework

WHO: Ethics and governance of artificial intelligence for health. Health AI accountability, safety, and oversight principles. https://www.who.int/publications/i/item/9789240029200

HHS Office for Civil Rights Breach Notification. Context for privacy breach response when protected health information may be involved. https://www.hhs.gov/hipaa/for-professionals/breach-notification/index.html

## Role-Based AI Use Guidelines

Different public health roles need different AI permissions, responsibilities, training expectations, review duties, and escalation pathways.

AI policy becomes much easier to follow when you can see how it applies to their actual role. A communications specialist, epidemiologist, procurement officer, supervisor, and community engagement lead should not receive identical instructions and be expected to infer the rest.

Role-based guidance also supports security and accountability. You should only have access to the AI tools and data environments they need, and they should understand what documentation is required when they use AI for official work.

This module helps you move your department from broad AI literacy into operational readiness.

### Module Overview

Role-based AI guidelines translate policy into daily practice. Leaders, program colleagues, analysts, communications staff, IT/security, privacy/legal, procurement, equity staff, supervisors, and governance members each need practical guidance for their responsibilities.

### Role Differences

Leaders approve direction, resources, governance authority, and risk tolerance.

Program colleagues define workflow needs, review outputs, and report concerns.

Analysts and informatics staff support data quality, validation, monitoring, and documentation.

Communications staff review public-facing language, plain language, translations, and misinformation risk.

Legal, privacy, security, procurement, and equity staff apply specialized review requirements.

### Training Expectations

Every role needs baseline AI literacy, prohibited-use guidance, data-use rules, and escalation expectations.

High-impact roles need deeper training on governance, validation, procurement, public communication, or monitoring.

Supervisors need guidance on approving use, checking documentation, and supporting staff adoption.

### Implementation Check

Create a role-by-role matrix of allowed uses, prohibited uses, required approvals, and documentation expectations.

Connect role guidance to onboarding, annual training, governance participation, and tool access.

### Why This Matters for Your Practice

Role clarity prevents inconsistent AI use, unsupported individual experimentation, unreviewed public communications, and unclear accountability.

### Reflection Questions

Which roles need permission to use which AI tools?

Which roles must review outputs before they are used?

Which roles need advanced training before governance or procurement decisions?

### Practical Exercise

Build a role-based AI use matrix for one department, including allowed uses, prohibited uses, approval requirements, documentation, and escalation contacts.

### Expected Takeaways

Role-based AI use matrix

Training assignment plan

Access and approval rules

### References and Resources

ASPPH AI Framework Report. Public health workforce, AI literacy, and role preparation framing. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

CDC Public Health Workforce Development. Public health workforce capability-building context. https://www.cdc.gov/workforce/

Public Health Foundation TRAIN Learning Network. Training platform for role-based public health workforce development. https://www.train.org/

## Responsible Prompting and Review

Responsible prompting helps staff use generative AI safely by protecting data, asking precise questions, requiring sources when needed, and reviewing outputs before use.

Responsible prompting training should be hands-on. Staff learn best by comparing a vague prompt, a safer prompt, and a reviewed final output. The point is not to create perfect prompts; the point is to create safer drafts and stronger review habits.

Departments should be clear that generative AI can support drafting and synthesis, but it does not replace subject matter expertise, legal review, privacy review, or communications approval.

This module should give staff enough confidence to use approved tools productively while recognizing when a task is too sensitive, too consequential, or too uncertain for AI assistance.

### Module Overview

Staff need practical guidance for everyday generative AI use. Prompting is not magic language; it is a structured way to define task, audience, source material, constraints, review criteria, and prohibited data. The review step is more important than the prompt.

### Prompting Practices

State the task, audience, purpose, tone, and output format.

Provide approved source material when the output must reflect agency policy or current guidance.

Ask the tool to identify assumptions, limitations, uncertainty, and items needing human review.

Never include PHI, confidential records, investigation details, credentials, or restricted partner data in public AI tools.

### Review Practices

Check factual claims, dates, citations, calculations, recommendations, and legal or policy statements.

Review plain language, accessibility, cultural context, language access, and potential stigma.

Confirm that the output does not imply an action, authority, or guarantee the department cannot support.

Document AI assistance when required by agency policy.

### Implementation Check

Train staff with examples from their own workflows.

Provide approved prompt templates and review checklists.

Use escalation rules for public-facing, high-risk, or uncertain outputs.

### Why This Matters for Your Practice

Responsible prompting and review reduce the chance that staff use AI in ways that expose data, spread misinformation, create inaccessible communication, or bypass expert review.

### Reflection Questions

Which AI-assisted drafting tasks should be allowed for staff?

Which outputs require source verification, supervisor review, or communications approval?

How should staff document AI-assisted work?

### Practical Exercise

Rewrite three unsafe prompts into responsible prompts, then review sample AI outputs for data exposure, hallucinations, tone, equity concerns, missing sources, and required approvals.

### Expected Takeaways

Responsible prompt examples

Output review checklist

Documentation expectations

### References and Resources

OpenAI Prompt Engineering Guide. Core prompt engineering practices for clear instructions, examples, task decomposition, and systematic iteration. https://platform.openai.com/docs/guides/prompt-engineering

Google Cloud Prompt Engineering Guide. High-quality overview of prompt components, prompt patterns, and how prompts shape generative AI outputs. https://cloud.google.com/discover/what-is-prompt-engineering

Microsoft Prompt Engineering Techniques. Operational prompting techniques for structured outputs, grounding, examples, and model-specific prompt refinement. https://learn.microsoft.com/en-us/azure/ai-services/openai/concepts/prompt-engineering

NIST Generative AI Profile. Risk management concepts for generative AI systems and outputs. https://www.nist.gov/itl/ai-risk-management-framework

WHO: Ethics and governance of artificial intelligence for health. Ethics and governance principles for health AI use. https://www.who.int/publications/i/item/9789240029200

CDC Clear Communication Index. Useful for reviewing plain-language public health materials. https://www.cdc.gov/ccindex/

## Community Engagement for AI

Community engagement helps departments understand how AI-supported workflows may affect trust, access, surveillance concerns, language needs, disability access, and public accountability.

Community engagement is not a public relations step after technical decisions are complete. It is a way to improve design, identify harms, clarify accountability, and build trust before implementation choices harden.

AI systems may change how people are contacted, prioritized, informed, or served. Communities should be able to understand those changes and raise concerns before the department launches a tool that affects them.

This module should help staff design engagement that is specific enough to influence AI decisions rather than simply announcing that AI will be used.

### Module Overview

Community engagement for AI should happen before use cases are finalized, especially when a system affects public communication, surveillance, outreach, service access, prioritization, or resource allocation. Engagement helps departments surface concerns that technical testing may miss.

### Engagement Focus Areas

What the AI-supported workflow will and will not do.

What data are involved and how privacy is protected.

What decisions remain human and how concerns can be raised.

How language, disability, digital access, rural context, Tribal context, immigration concerns, or historical mistrust may affect the workflow.

### Engagement Methods

Listening sessions, advisory groups, community partner consultation, usability testing, plain-language review, and feedback forms.

Internal engagement with frontline staff who understand how communities experience department services.

Ongoing feedback after launch, not only pre-implementation input.

### Implementation Check

Document who was engaged, what concerns were raised, what changed, and what remains unresolved.

Route unresolved community concerns to governance.

Close the feedback loop with plain-language summaries.

### Why This Matters for Your Practice

Engagement helps departments avoid AI uses that appear efficient internally but create confusion, mistrust, stigma, surveillance concerns, or access barriers externally.

### Reflection Questions

Which communities or partners may be affected by the proposed AI use?

What should be explained in plain language before implementation?

How will community feedback change governance, design, monitoring, or communication?

### Practical Exercise

Create a community engagement plan for one AI-supported workflow, including audiences, engagement methods, plain-language explanation, feedback documentation, and governance escalation.

### Expected Takeaways

AI community engagement plan

Plain-language AI explanation

Feedback-to-decision log

### References and Resources

CDC Health Equity. Public health equity context for community engagement and accountability. https://www.cdc.gov/healthequity/

ASPPH AI Framework Report. Human-centered AI, missing voices, and public accountability framing. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

Blueprint for an AI Bill of Rights. Notice, explanation, human alternatives, and protections from automated harms. https://bidenwhitehouse.archives.gov/ostp/ai-bill-of-rights/

## Accessibility and Language Access

AI-supported public health materials, tools, dashboards, chatbots, translations, and workflows should be reviewed for disability access, language access, readability, cultural context, and usability.

AI can make communication faster, but speed is not the same as access. Public health departments need to know whether messages can be understood, whether tools can be used by people with disabilities, and whether translations are accurate enough for the purpose.

Language access and accessibility are also trust issues. Communities may lose confidence if AI-generated messages are confusing, culturally inappropriate, inaccessible, or inconsistent with staff communication.

This module helps you build access review into AI planning rather than treating it as a final proofreading step.

### Module Overview

AI can support translation, plain-language rewriting, alternative formats, and communication drafts, but those outputs still need human review. Accessibility and language access should be part of planning, testing, communications approval, and monitoring.

### What Needs Review

AI-generated public health messages, FAQs, chatbot responses, translations, summaries, forms, dashboards, and outreach lists.

Reading level, clarity, disability access, screen-reader compatibility, captions, plain-language structure, cultural context, and stigmatizing language.

Whether non-digital and human assistance pathways remain available.

### Translation and Language Access

AI translation should not be used for high-stakes public messaging without qualified human review.

Departments should review dialect, cultural context, health terminology, and risk communication accuracy.

You should document which languages were reviewed and by whom.

### Implementation Check

Include accessibility and language access in use case scoring.

Test public-facing tools with users before launch.

Monitor complaints, failed interactions, correction requests, and access barriers after deployment.

### Why This Matters for Your Practice

Accessible and language-appropriate AI-supported communication is essential for equitable public health service delivery and public trust.

### Reflection Questions

Which AI-supported outputs will be public-facing or client-facing?

Who reviews translations, accessibility, readability, and cultural context?

What non-AI or human pathway remains available?

### Practical Exercise

Review an AI-generated public health message and identify changes needed for plain language, accessibility, language access, cultural context, and human assistance pathways.

### Expected Takeaways

Accessibility and language access review notes

Revised public message

Monitoring indicators for access barriers

### References and Resources

HHS Section 1557. Nondiscrimination and language access context in health programs and activities. https://www.hhs.gov/civil-rights/for-individuals/section-1557/index.html

ADA.gov. Federal accessibility requirements and guidance. https://www.ada.gov/

CDC Clear Communication Index. Plain-language review support for health communication materials. https://www.cdc.gov/ccindex/

## Cybersecurity and Secure AI Use

Secure AI use requires approved environments, access controls, vendor security review, audit logs, prompt-injection awareness, data-loss prevention, and incident escalation.

AI tools can blur the boundary between software, data processing, content generation, and workflow automation. That makes security review especially important before departments connect AI to email, document repositories, case systems, dashboards, or public-facing services.

Your training should make secure AI use concrete. Which tools are approved? What data are prohibited? What are signs of prompt injection or suspicious AI behavior? Who should be notified when something goes wrong?

This module helps you understand why security is a shared responsibility and why shortcuts can create agency-wide risk.

### Module Overview

AI security is broader than protecting the model. It includes user accounts, data flows, integrations, APIs, vendor hosting, prompts, outputs, logs, plugins, browser extensions, and connections to existing systems. Staff need to know how secure AI use differs from general software use.

### Security Concerns

Sensitive data entered into unapproved tools or retained by vendors.

Prompt injection or malicious content that manipulates AI behavior.

Unauthorized access through weak role controls, shared accounts, or unmanaged integrations.

Unverified AI-generated code, formulas, or instructions introduced into operational systems.

Vendor outages, model changes, or compromised services affecting public health operations.

### Secure Practices

Use only approved AI tools for official work.

Apply role-based access, multi-factor authentication, logging, data-loss prevention, and least-privilege access.

Review vendor security documentation, hosting, subcontractors, breach notification, and audit rights.

Train staff to treat AI outputs and external content as potentially unsafe until reviewed.

### Implementation Check

Include security review before pilot approval.

Test integrations in controlled environments.

Coordinate AI incident response with cybersecurity and privacy response plans.

### Why This Matters for Your Practice

Cybersecurity protects public health operations, sensitive data, system integrity, and community trust.

### Reflection Questions

Which AI tools are approved for official work?

Which integrations or data flows require security review?

How should staff report suspicious AI behavior, data leakage, or unauthorized access?

### Practical Exercise

Map the security controls needed for one AI use case, including data classification, access controls, vendor hosting, integrations, logging, incident response, and staff training.

### Expected Takeaways

AI security review notes

Approved-use rules

Security escalation checklist

### References and Resources

NIST Cybersecurity Framework. Cybersecurity risk management structure for organizational systems. https://www.nist.gov/cyberframework

CISA AI and Cybersecurity. Cybersecurity context for AI systems and AI-enabled threats. https://www.cisa.gov/ai

FedRAMP. Cloud security authorization context for vendor-hosted government systems. https://www.fedramp.gov/

OWASP LLM01: Prompt Injection. Security guidance on prompt injection risks, including malicious instructions, indirect prompt injection, and mitigation considerations for LLM applications. https://genai.owasp.org/llmrisk/llm01-prompt-injection/

## When Not to Use AI

Departments need a clear decision framework for situations where AI is inappropriate, premature, too risky, unsupported by data, legally uncertain, or not worth the operational burden.

You may feel pressure to find AI uses because the technology is highly visible. Your training should make it acceptable to conclude that AI is not the right tool for a particular problem.

The strongest AI programs are not the ones with the most pilots. They are the ones that select use cases carefully, say no to poor fits, and invest in readiness before moving forward.

This module gives you a shared language for declining, deferring, or redesigning proposals without making the discussion feel anti-innovation.

### Module Overview

Responsible AI adoption includes saying no. Some tasks should remain human-only, some require more readiness work before AI is considered, and some can be improved more safely through workflow redesign, staffing, training, or better data systems.

### Red Flags

The use case affects rights, enforcement, eligibility, resource allocation, public warnings, or clinical/care decisions without strong governance and human review.

Data are poor quality, incomplete, unrepresentative, sensitive, or not legally available for the proposed use.

The department cannot explain, validate, monitor, audit, or pause the system.

Affected communities or staff have not been engaged.

The expected benefit does not justify cost, risk, environmental burden, or staff disruption.

### Alternative Actions

Improve the workflow without AI.

Strengthen data quality, documentation, staffing, or training first.

Use a simpler rules-based tool, checklist, dashboard, or template.

Limit AI to internal drafting or evidence organization rather than decision support.

Pause the proposal until governance conditions are met.

### Implementation Check

Create prohibited-use and restricted-use categories.

Require governance review for high-impact proposals.

Document why a use case was rejected, deferred, limited, or redesigned.

### Why This Matters for Your Practice

A clear no-go framework protects departments from avoidable harm, unfunded pilots, weak accountability, and loss of trust.

### Reflection Questions

Which public health decisions should remain human-only?

What conditions would cause governance to reject or defer an AI proposal?

What non-AI alternatives could solve the problem more safely?

### Practical Exercise

Review three proposed AI use cases and decide whether each should proceed, be limited, be deferred, be redesigned without AI, or be rejected.

### Expected Takeaways

AI no-go decision notes

Restricted-use criteria

Alternative solution options

### References and Resources

Blueprint for an AI Bill of Rights. Principles for human alternatives, notice, and protection from automated harms. https://bidenwhitehouse.archives.gov/ostp/ai-bill-of-rights/

NIST AI Risk Management Framework. Risk-based framing for deciding whether and how AI should be used. https://www.nist.gov/itl/ai-risk-management-framework

ASPPH AI Framework Report. Public health framing for responsible adoption, governance, and human-centered AI. https://aspph.org/initiatives/ai-for-public-health/ai-framework-report/

## Areas Where AI Can Support Public Health Activities

Expanded examples showing how AI can support specific public health activities, what safeguards are needed, and which plays and tools help agencies move from idea to responsible implementation.

### Why This Matters for Your Practice

Support areas help staff move from abstract AI concepts to concrete public health opportunities. They should be used to identify possible use cases, not to skip readiness, governance, stakeholder engagement, or risk review.

### Reflection Questions

Which support areas align with current public health priorities?

Which areas are feasible given current data, workforce, governance, and funding?

Which areas could create equity, privacy, transparency, or public trust concerns?

### Practical Exercise

Select three support areas and score each for public health value, feasibility, risk, equity impact, data readiness, staff readiness, and sustainment.

### Expected Takeaways

AI opportunity list

Use case screening notes

Prioritized concepts for governance review

# Areas Where AI Can Support Public Health Activities

These expanded examples are drawn from the learning modules and organized as practical planning topics for public health agencies. Each area includes potential activities, required safeguards, example concepts, and related plays and tools.

## Surveillance, Signal Detection, and Outbreak Intelligence

AI can help staff review high-volume surveillance streams, detect unusual patterns, summarize incoming reports, and prioritize signals for epidemiologist review.

### Useful Activities

Summarize surveillance reports into trend, geography, population, and uncertainty sections.

Flag anomalies or clusters for human investigation.

Assemble evidence packets from laboratory, syndromic, emergency department, and partner reports.

Draft internal situation updates from approved source data.

### Required Safeguards

AI should flag and organize information, not declare outbreaks or issue public alerts.

Epidemiologists should validate signals and document decisions.

Data latency, false positives, false negatives, and subgroup effects should be monitored.

Learning examples: Summarize surveillance reports, Route high-priority surveillance signals, Detect anomalies, Synthesize outbreak updates

Related plays: 2, 3, 7, 11, 13. Related tools: 7, 13, 14, 41, 44, 47.

## Evidence Review, Policy Scans, and Research Synthesis

AI can accelerate first-pass reviews of literature, public health guidance, policy requirements, grant notices, and program examples, while staff verify sources and applicability.

### Useful Activities

Conduct literature scans for emerging threats or interventions.

Compare policy requirements across jurisdictions.

Summarize scientific, legal, or funding documents for leadership review.

Create annotated evidence tables with source links and open questions.

### Required Safeguards

Require citations and source verification.

Separate evidence strength from opinion, vendor claims, or early findings.

Have subject matter experts review conclusions before decisions are made.

Learning examples: Literature scans for emerging threats, Policy scans across jurisdictions, Comparative program analysis, Summarize policy documents with human review

Related plays: 1, 3, 7, 8, 13. Related tools: 2, 4, 32, 48.

## Plain-Language Communication and Health Education

Generative AI can help convert technical material into accessible drafts for staff, partners, and public audiences when communications staff and subject matter experts review the final content.

### Useful Activities

Draft health education materials, FAQs, and talking points.

Translate analytic findings into plain language for briefings or partner updates.

Adapt content for different literacy levels, languages, channels, and audiences.

Prepare first drafts of public notices about AI-supported activities.

### Required Safeguards

Review for accuracy, tone, reading level, cultural context, accessibility, and current guidance.

Avoid unsupervised public-facing generation.

Use approved source material and document human review.

Learning examples: Draft health education materials, Translate analytic findings into plain language, Community-facing FAQs, Public AI use notices

Related plays: 1, 3, 4, 10, 12. Related tools: 19, 20, 29, 46.

## Leadership Briefings and Decision Support

AI can organize evidence, options, risks, tradeoffs, and recommended next steps so leaders receive clearer decision packages.

### Useful Activities

Prepare decision briefs from approved evidence and agency records.

Summarize options, benefits, risks, constraints, and open questions.

Convert assessment findings into recommended plays, tools, owners, and timelines.

Draft governance memos for review by accountable staff.

### Required Safeguards

Clearly label AI-assisted drafts.

Require decision owner sign-off.

Include uncertainty, limitations, and source references.

Prevent AI from making final policy, resource, or emergency decisions.

Learning examples: Support decision briefings, Decision owner sign-off, Confidence and limitation notes in briefs

Related plays: 1, 2, 3, 7, 12. Related tools: 1, 6, 7, 13, 46.

## Grants, Funding, and Sustainability Planning

AI can help departments align AI work with funding streams, draft grant narratives, compare allowable costs, and prepare sustainment plans.

### Useful Activities

Create first drafts of grant narratives and logic models.

Map use cases to DMI, PHIG, HRSA, FEMA, EPA, SAMHSA, NIH, NSF, or state/local funding opportunities.

Estimate staffing, technology, evaluation, training, and sustainment costs.

Draft budget justification language for reviewed AI projects.

### Required Safeguards

Verify funding requirements, deadlines, eligibility, and allowable costs.

Avoid committing to AI capabilities that cannot be supported or monitored.

Include governance, evaluation, accessibility, and change management costs.

Learning examples: Create first drafts of grant narratives, DMI-supported data pipelines, PHIG-supported workforce and governance, Grant-aligned pilots

Related plays: 8, 9. Related tools: 36, 32, 33.

## Workflow Routing, Task Queues, and Operational Coordination

Agentic or semi-agentic workflows can help turn incoming information into routed tasks, evidence packets, reminders, and status updates for staff review.

### Useful Activities

Create task queues from incoming reports, meeting notes, complaints, or surveillance items.

Route materials to the appropriate program, geography, subject matter expert, or governance reviewer.

Prepare internal reminders for owners, deadlines, approvals, and follow-up actions.

Update implementation workplans as milestones are completed or blocked.

### Required Safeguards

Define what the AI can create, route, update, or escalate.

Require audit logs and role-based permissions.

Give administrators control over assignments, deadlines, and workflow changes.

Keep humans responsible for final action and external communication.

Learning examples: Create task queues from incoming reports, Coordinate governance submissions, Staff reporting pathways for concerns

Related plays: 3, 6, 10, 11, 12. Related tools: 12, 13, 17, 23, 30, 36.

## Equity, Missing Voices, and Community Validation

AI can support equity review by helping teams identify affected groups, compare subgroup performance, draft engagement materials, and track mitigation commitments.

### Useful Activities

Identify underrepresented groups or data gaps during use case review.

Draft community validation questions and engagement summaries.

Monitor subgroup performance after deployment.

Track equity concerns, mitigation owners, and follow-up deadlines.

### Required Safeguards

Use community expertise and affected-user input, not only data analysis.

Document who was consulted and what changed as a result.

Do not deploy systems that cannot be evaluated for disparate impact when they affect access, services, enforcement, or public communication.

Learning examples: Identify underrepresented groups, Add community validation before launch, Monitor subgroup performance after deployment, Equity audit before scale

Related plays: 4, 7, 13. Related tools: 3, 20, 22, 47.

## Language Access, Accessibility, and Digital Inclusion

AI can assist with translation, plain-language adaptation, accessibility review, and digital service support, but it must be reviewed for accuracy, cultural relevance, and equitable access.

### Useful Activities

Draft translations for human review by qualified language staff or vendors.

Convert complex guidance into plain-language and accessible formats.

Evaluate whether AI-supported services create barriers for people without broadband, devices, literacy, English proficiency, or trust in digital systems.

Develop alternate pathways for people who cannot or do not want to use AI-supported services.

### Required Safeguards

Require human review before public use of translated or accessibility-critical materials.

Test materials with affected users where feasible.

Provide non-AI or staff-supported alternatives for important services.

Learning examples: Review AI effects on language access, Evaluate service access impacts, Public AI use notices

Related plays: 1, 4, 7, 10, 13. Related tools: 3, 19, 20, 22, 47.

## Privacy, Tiered Data Use, and Secure AI Environments

AI can support work with sensitive information only when departments define data tiers, approved environments, vendor requirements, and review pathways.

### Useful Activities

Classify data as public, internal, confidential, protected, restricted, or sovereign where applicable.

Match each tier to approved AI tools and required controls.

Review vendor data retention, model training, logging, deletion, and access claims.

Prepare data use agreements, BAAs, and procurement addenda when needed.

### Required Safeguards

Restrict PHI and sensitive data from public AI tools.

Use enterprise, in-house, or controlled RAG environments for restricted materials.

Document data sources, access rules, and human review requirements.

Escalate incidents through privacy, security, and governance channels.

Learning examples: Restrict PHI from public AI tools, Approve enterprise AI for internal drafts, Use in-house/RAG systems for restricted materials

Related plays: 2, 3, 11, 12. Related tools: 10, 15, 16, 34, 39.

## Procurement, Vendor Review, and Environmental Impact

AI can support procurement analysis, but departments need structured review of vendor transparency, accessibility, auditability, security, data rights, sustainability, and exit requirements.

### Useful Activities

Compare vendor responses against responsible AI, security, privacy, accessibility, and documentation requirements.

Review environmental and resource impacts for high-compute or scaled systems.

Draft procurement addenda and contract language for AI-specific obligations.

Track vendor performance, incidents, and policy updates after deployment.

### Required Safeguards

Do not rely on vendor marketing claims without documentation.

Require audit rights, data-rights language, model documentation, monitoring obligations, and exit plans.

Consider lower-impact alternatives where public health value does not justify high compute burden.

Learning examples: Review vendor sustainability claims, Compare lower-impact alternatives, Flag data center environmental justice concerns

Related plays: 3, 7, 8, 9, 12. Related tools: 4, 5, 32, 34, 45.

## Workforce Training, AI Literacy, and Bridge Roles

AI can help staff learn and coordinate work, but departments need role-based AI literacy and bridge capacity to connect programs, governance, technology, procurement, and community expectations.

### Useful Activities

Develop role-based training for leaders, program staff, analysts, IT, privacy, procurement, communications, and governance members.

Create prompt and privacy coaching materials.

Designate AI champions or bridge professionals to support adoption.

Track staff concerns, training completion, and workflow barriers.

### Required Safeguards

Do not ask staff to use AI before they understand privacy, hallucination, bias, documentation, and escalation expectations.

Protect staff time for training and implementation support.

Use feedback loops to identify workload, trust, and usability problems.

Learning examples: Role-based AI training, Prompt and privacy coaching, Coordinate data modernization with workforce training, Help program staff document AI workflows

Related plays: 5, 6, 10. Related tools: 23, 24, 25, 27, 28, 29, 30.

## Performance Improvement, Metrics, and Quality Dashboards

Generative and agentic AI can support public health performance improvement by helping teams define meaningful measures, build baseline profiles, generate improvement ideas, track action plans, and maintain dashboards for ongoing monitoring.

### Useful Activities

Use generative AI to draft candidate process, output, outcome, balancing, equity, and experience measures from a program aim statement.

Use AI to convert broad goals into SMART measures, operational definitions, numerators, denominators, data sources, reporting frequency, and accountable owners.

Use agentic AI to pull approved data from dashboards, registries, logs, surveys, or workplan trackers and prepare routine performance summaries for staff review.

Generate improvement hypotheses, Plan-Do-Study-Act ideas, root-cause prompts, and meeting agendas based on current performance trends.

Create action trackers that assign owners, due dates, dependencies, status, barriers, and follow-up items for each improvement activity.

Monitor dashboards for trends, thresholds, missed deadlines, equity gaps, data quality issues, and measures that need governance or leadership attention.

### Required Safeguards

Staff should approve all measures before use so the dashboard reflects public health priorities rather than whatever data are easiest to collect.

AI-generated measures should be checked for feasibility, validity, equity relevance, burden, and unintended incentives.

Agentic monitoring should only use approved data sources and should not alter official records, contact partners, or escalate externally without human review.

Dashboards should show definitions, data freshness, limitations, subgroup views, and interpretation notes so users do not over-read noisy or incomplete data.

Performance summaries should distinguish observed trends from AI-generated explanations or improvement suggestions.

Learning examples: Draft performance measures from an aim statement, Identify leading and lagging indicators, Generate PDSA ideas from dashboard trends, Monitor dashboard thresholds and equity gaps, Create owner-based improvement action trackers

Related plays: 2, 3, 7, 9, 10, 12, 13. Related tools: 7, 8, 9, 13, 23, 36, 41, 42, 44, 45, 47, 48.

## Monitoring, Evaluation, Incident Response, and Continuous Improvement

AI-supported systems require ongoing review after launch. Departments need dashboards, incident processes, policy logs, equity monitoring, and clear retirement or pause criteria.

### Useful Activities

Monitor model performance, data quality, subgroup outcomes, drift, incidents, complaints, and staff adoption.

Track hallucination or misinformation risks for public-facing outputs.

Maintain policy update and version control logs.

Evaluate whether the AI system improves public health outcomes, timeliness, quality, equity, or staff workload.

### Required Safeguards

Define thresholds for pausing, modifying, or retiring systems.

Assign owners for monitoring and incident response.

Review high-impact systems through governance on a regular cadence.

Document lessons learned and update tools, policies, training, and public notices.

Learning examples: Hallucination audit for public-facing products, Incident response for unsafe outputs, Policy update process, Monitor subgroup performance after deployment

Related plays: 12, 13. Related tools: 14, 17, 18, 41, 42, 44, 45, 46, 47, 48.

# Readiness Assessment

The readiness assessment uses six domains scored on a 0-3 question scale and converted to a 100-point score for intuitive interpretation. Section scores identify where the department should focus next plays and tools.

## Leadership and Governance

Leadership has articulated an AI vision aligned with strategic priorities.

A clear governance structure exists or is planned.

AI ethics and equity principles have been established.

Budget authority exists to support AI infrastructure and workforce.

Recommended plays: 1, 3, 12. Recommended tools: 1, 2, 12, 46, 17.

## Data Infrastructure

Data systems are integrated or interoperable.

Data quality is regularly monitored.

Cloud or modern analytics infrastructure is available.

Data governance policies exist for access, privacy, security, and use.

Recommended plays: 2, 9, 11, 13. Recommended tools: 7, 9, 15, 39, 44.

## Workforce Capacity

Staff with data science, analytics, or AI skills are available.

Training programs build AI literacy across the workforce.

Job descriptions and career paths support data and AI roles.

Academic or technical partnerships provide additional capacity.

Recommended plays: 5, 6, 10. Recommended tools: 23, 24, 26, 28, 29, 30.

## Equity and Community Engagement

Equity impact assessment is part of AI planning.

Community engagement informs design of community-impacting systems.

Local context and applicable community or Tribal data governance expectations are identified and respected.

Subgroup performance monitoring is planned before deployment.

Recommended plays: 4, 7, 13. Recommended tools: 3, 20, 21, 47.

## Partnerships and Collaboration

Cross-program collaboration supports AI use cases.

External partners are identified and governed appropriately.

Procurement and vendor pathways are understood.

Roles and responsibilities are documented.

Recommended plays: 4, 7, 8. Recommended tools: 20, 21, 32, 33.

## Privacy and Security

PHI and sensitive data protections are defined.

Security review occurs before AI tools are used.

Data use agreements are required for vendors and partners.

Incident response and escalation processes exist.

Recommended plays: 3, 11, 12. Recommended tools: 15, 16, 17.

## Policy, Procurement, and Public Accountability

AI policy landscape, procurement requirements, public records obligations, and agency restrictions have been reviewed before tools are selected.

Vendor and procurement reviews include transparency, data rights, model documentation, auditability, accessibility, security, and exit requirements.

Environmental and resource impacts, including compute, energy, water, sustainability, and environmental justice considerations, are assessed for AI projects.

Plain-language public notice, human-centered decision rules, and limits on automated decision-making are documented for public-impacting AI uses.

Recommended plays: 1, 3, 7, 8, 11, 12. Recommended tools: 4, 5, 6, 19, 32, 34.

# AI Maturity Model

| Level | Stage | Focus | Recommended Plays |
| --- | --- | --- | --- |
| 1 | Awareness | Learning and exploration | 1 |
| 2 | Readiness | Planning and preparation | 2, 3, 4, 5, 6, 7, 8, 9 |
| 3 | Pilots | Governed initial development | 7, 10, 11 |
| 4 | Deployment | Operational integration | 11, 13 |
| 5 | Optimization | Continuous improvement | 12, 13 |

# 13-Play Planning and Implementation Framework

## Play 1: Vision & Guardrails

Establish a clear strategic vision for how AI will support the agency's public health mission while defining principles that ensure responsible, ethical, and legally compliant use.

Why it matters: Every AI initiative begins with leadership alignment. Setting guardrails early around equity, human oversight, privacy, and prohibited uses prevents downstream harms and builds institutional trust.

Who should participate: Executive leadership, Program leads, Legal and privacy, Equity leaders, IT and data leaders

### Key Questions

Which strategic public health problems should AI help address?

Which uses are prohibited?

What level of human review is required?

### Key Actions

Convene a 60-90 minute leadership session.

Agree on non-negotiable guardrails for human oversight, equity, privacy, and prohibited uses.

Draft a 1-2 page AI Vision and Principles document.

Align principles with NIST AI RMF 1.0.

Identify executive sponsorship and update annually.

### Outputs

Draft AI vision statement.

Draft responsible AI principles.

Initial guardrails and boundaries.

List of current known or suspected AI uses.

Initial strategic priority areas.

List of unresolved issues requiring legal, privacy, IT, equity, or leadership review.

Recommended next steps and owners.

Decision on whether to establish or convene an AI governance committee.

### Resources

NIST AI Risk Management Framework (AI RMF 1.0): Use as the anchor framework for responsible AI principles, risk language, and agency guardrails.

ASPPH AI Framework Report: Human-centered AI framing, public health systems-change language, AI literacy, and transparency expectations.

World Health Organization: Ethics and governance of AI for health: Supports health-sector principles for transparency, equity, responsibility, and human oversight.

OECD AI Principles: Useful for drafting high-level principles that are recognized across governments and institutions.

Blueprint for an AI Bill of Rights: Rights, protections, notice, human alternatives, and algorithmic discrimination safeguards.

## Play 2: Readiness Assessment

Assess current state across leadership, data infrastructure, workforce, equity, partnerships, privacy, and security so planning reflects organizational reality.

Why it matters: A frank readiness assessment finds gaps while they are still manageable, before a project discovers midstream that data, skills, infrastructure, or governance are insufficient.

Who should participate: Leadership, IT, Data and analytics, Programs, Legal/privacy, Equity, Community engagement

### Key Questions

Which gaps block pilots?

Which gaps can be addressed in parallel?

What constraints shape feasible use cases?

### Key Actions

Run a half-day assessment workshop.

Rate each indicator honestly.

Identify 5-8 high-priority gaps.

Assign owners and timelines.

Brief leadership and the governance sponsors on constraints and next steps.

### Outputs

Completed AI Readiness Self-Assessment.

Total readiness score on the 100-point scale, with raw score retained for transparency.

Section scores for each readiness domain: leadership and governance, data infrastructure, workforce capacity, equity and community engagement, partnerships and collaboration, and privacy and security.

Evidence notes, assumptions, and disagreements used to support each section score.

Readiness stage interpretation based on the total score.

Priority weak domains that should shape the next steps, even if the total score is high.

Gap register identifying the gap, domain, section score, blocking or parallel status, risk level, owner, timeline, related play, and related tool.

List of blocking gaps that must be addressed before pilots, procurement, deployment, or scaling can move forward.

List of parallel gaps that can be addressed while planning continues.

Recommended 2-4 plays to complete next, based on total score and lowest-scoring domains.

Play prioritization plan showing which plays should be completed first, which can proceed in parallel, and which should wait.

Recommended supporting tools for each prioritized play.

30-, 60-, and 90-day action plan with owners and due dates.

Leadership or governance briefing summary, including constraints, risks, decisions needed, and recommended next steps.

Decision list identifying any current or proposed AI activities that should be paused, delayed, revised, or routed to governance review.

STLT AI policy landscape scan identifying legal, public records, procurement, IT, and agency restrictions.

Tiered data classification summary showing which data may be used in public, enterprise, in-house, vendor, or restricted AI environments.

Reassessment plan, including when the department will repeat the assessment and what changes should trigger reassessment.

Downloadable assessment summary for documentation and governance records.

### Resources

CDC Data Modernization Initiative: Use to assess data modernization, interoperability, cloud readiness, and AI-ready infrastructure gaps.

ASPPH AI Framework Report: Readiness review of fragmented adoption, policy gaps, staff capacity, and legal or political constraints.

CDC STLT resources: State, territorial, local, and tribal public health capacity, planning, and implementation context.

CSTE: Driving public health in the fast lane: Supports readiness discussions about modern surveillance, data modernization, and public health data capacity.

Public Health Infrastructure Grant: Useful when readiness gaps point to workforce, data systems, organizational capacity, or equity investments.

## Play 3: Establish AI Governance

Create the governance structures, policies, decision-making processes, and oversight mechanisms needed to guide responsible AI use before projects begin.

Why it matters: Governance should not be added after AI tools are already in use. It should be established before use case selection, vendor engagement, pilot approval, or deployment. Public health departments need clear authority, consistent review processes, and documented accountability for AI use. Strong governance helps ensure that AI supports the public health mission while protecting privacy, security, equity, scientific integrity, workforce trust, and community confidence.

Who should participate: Health officer or executive sponsor, Executive leadership or designated governance sponsor, Legal and privacy staff, IT and cybersecurity staff, Equity and community engagement staff, Program owners, Informatics, epidemiology, data, or analytics staff, Communications staff, Procurement or contracting staff, as needed, External advisors or community representatives, when appropriate, Governance committee or board members, once appointed

### Key Questions

Who has authority to approve, pause, suspend, or retire AI use?

What types of AI use are allowed, restricted, or prohibited?

What documentation is required before AI use cases move forward?

What review is required for privacy, security, equity, data quality, and legal compliance?

How will AI use cases be classified by risk?

Who is accountable for each AI-supported workflow or system?

How will incidents, errors, bias concerns, or harmful outputs be reported and addressed?

How will policies, standards, and approved-use records be updated over time?

### Key Actions

Confirm the governance mandate. Define why AI governance is needed, what decisions it will cover, and how it will support the department's AI vision, principles, and guardrails.

Establish the governance body. Create or designate a cross-functional AI governance committee or board with clear membership, leadership, authority, and decision rights.

Adopt responsible AI policy expectations. Define department-wide expectations for transparency, privacy and security, equity, human oversight, safety, legal compliance, scientific integrity, and accountability.

Create the governance charter. Document the governance body's purpose, scope, membership, meeting cadence, decision process, documentation requirements, and escalation procedures.

Define the AI review pathway. Establish how proposed AI uses will be submitted, screened, classified by risk, reviewed, approved, paused, or rejected.

Align governance with existing agency processes. Connect AI oversight with data governance, IT governance, cybersecurity, privacy, legal review, procurement, communications, equity review, program leadership, and quality improvement.

Set minimum documentation requirements. Define what must be documented for each AI use case, including purpose, owner, users, data involved, risk level, human review process, limitations, approval status, and review schedule.

Require appropriate review before approval. Ensure that privacy, security, equity, data quality, legal, vendor, and model validation reviews occur when required based on the risk and nature of the AI use case.

Create an AI system inventory. Maintain a central record of approved AI systems and AI-supported workflows, including owners, purpose, risk level, approval date, monitoring schedule, and review status.

Establish ongoing oversight. Define how approved AI uses will be monitored, how incidents will be handled, how systems can be paused or retired, and how policies will be updated over time.

### Outputs

AI governance committee or board.

Responsible AI policy.

Governance charter.

Risk-tiered AI review pathway.

AI use case intake and approval process.

Documentation standards.

AI system inventory.

Tiered data classification rules for AI use.

Plain-language AI public notice process.

STLT procurement and vendor review requirements.

AI-specific incident categories, including hallucinations, bias concerns, unsafe automation, misinformation, privacy exposure, and model drift.

Monitoring and incident response process.

Policy update process.

### Resources

NIST AI Risk Management Framework (AI RMF 1.0): Use to structure governance, risk tiers, documentation, oversight, and monitoring expectations.

ASPPH AI Framework Report: Modular AI policy, community trust, tiered data classification, incident reporting, and AI management system considerations.

HHS AI use case inventory requirements: Guidance for documenting AI use cases, owners, purposes, and reporting obligations.

HHS Civil Rights and AI: Supports governance requirements for equity, nondiscrimination, and civil rights review.

HIPAA and Business Associate Agreements: Use when governance decisions involve PHI, vendors, cloud tools, or partner data access.

FedRAMP: Reference when reviewing cloud services, hosted AI tools, and federal security authorization status.

## Play 4: Engage Stakeholders

Build a structured stakeholder engagement framework for internal and external input throughout planning, implementation, and evaluation.

Why it matters: Stakeholder and community engagement is an early planning activity, not a late deployment activity. It should begin after the department has a basic readiness picture and governance pathway, but before formal use case selection, roadmap design, funding commitments, pilots, procurement, or deployment. AI systems built without genuine community and workforce input often fail in deployment even when they perform well technically.

Who should participate: Program leads, Community advisors, Equity staff, Tribal partners where applicable, Communications, Governance committee

### Key Questions

Who is affected by the AI use case?

What concerns must shape design?

How will feedback change the project?

What stakeholder input is required before use cases can be prioritized?

### Key Actions

Map stakeholder groups and assign engagement leads.

Form advisory groups for community-impacting use cases.

Share plain-language explanations of what AI will and will not do.

Hold feedback sessions before use case selection and before design is finalized.

Document what changed based on feedback.

Route unresolved stakeholder concerns to the AI governance committee before pilots or procurement move forward.

### Outputs

Stakeholder map.

Internal stakeholder list.

External stakeholder list.

RACI or role clarification matrix.

Community and partner engagement plan.

Summary of stakeholder concerns and recommendations.

Equity and trust considerations.

Missing voices analysis identifying underrepresented groups, language access needs, disability access needs, tribal sovereignty concerns, rural context, and other perspectives not captured in available data.

Plain-language explanation plan for communities, partner organizations, and affected populations.

Documentation of how stakeholder input will inform governance, use case prioritization, implementation, monitoring, and evaluation.

Recommendations for ongoing engagement or advisory structures.

### Resources

CDC STLT resources: Use for state, territorial, local, and tribal public health engagement context.

ASPPH AI Framework Report: Community trust, plain-language transparency, and missing voices analysis.

ASTHO: Peer network for state and territorial health agency implementation examples and policy learning.

NACCHO: Peer network for local health departments, community engagement, and local implementation learning.

Tribal data sovereignty principles: Reference when AI planning involves Tribal communities, Tribal data, or Tribal governance contexts.

HHS Civil Rights and AI: Supports stakeholder engagement around equity, nondiscrimination, and disparate impact concerns.

## Play 5: Workforce Development

Develop the workforce capabilities needed to responsibly adopt generative and agentic AI across public health programs.

Why it matters: Training alone is not enough. Peer learning networks, champions, office hours, and communities of practice help staff build confidence and solve practical problems.

Who should participate: HR, Training leads, AI champions, Supervisors, Program staff, IT and data staff

### Key Questions

What AI literacy is needed by role?

Where are skill gaps?

Who will support adoption day to day?

### Key Actions

Define role-based AI literacy levels.

Conduct a training needs assessment.

Designate AI champions across divisions.

Create training pathways.

Assign learning modules by role and set completion standards.

Establish office hours and communities of practice.

### Outputs

AI workforce competency framework by role.

Training needs assessment summary.

Role-based AI literacy expectations.

Priority staff groups for training and support.

AI champion roles and selection criteria.

AI bridge professional role description and capacity plan.

Training pathway and delivery plan.

Role-based learning module assignment matrix.

Role-based training plan with required modules, optional modules, deadlines, completion standards, owners, and verification approach.

Training completion and competency tracker.

Community of practice or office-hours plan.

Measures for tracking AI literacy, adoption readiness, and ongoing support needs.

### Resources

Public Health Infrastructure Grant: Use when workforce development requires funding for staff capacity, training, governance, or organizational infrastructure.

ASPPH AI Framework Report: AI literacy, ethical reasoning, communicating uncertainty, and the AI bridge professional role.

CDC STLT Data Connection: Peer-learning and community-of-practice resource for public health data modernization and AI capacity building.

Public Health Foundation TRAIN Learning Network: Trusted training platform for public health workforce development and competency-building.

NACCHO: Resource for local public health workforce learning, implementation examples, and peer exchange.

## Play 6: Plan Change Management

Plan for adoption before deployment by identifying affected workflows, staff concerns, communication needs, training requirements, and support structures.

Why it matters: Change management starts while the project is still being planned. Early planning prevents technically sound AI projects from failing because staff roles, trust, workflow impacts, or communication needs were addressed too late.

Who should participate: Change leads, Supervisors, Communications, AI champions, Program staff, Governance committee

### Key Questions

What workflows may change?

Who needs early communication?

What concerns or barriers should shape the plan?

### Key Actions

Draft a change management plan before pilot launch.

Identify affected staff groups and workflow impacts.

Prepare staff communication and FAQ materials.

Surface resistance, privacy, equity, and usability concerns.

Define training, support, and feedback channels.

### Outputs

Change management plan.

Affected workflow and staff impact summary.

Stakeholder and staff communication plan.

Staff communication and FAQ materials.

Training and support plan for affected users.

Resistance, barrier, and concern inventory.

Mitigation actions with owners and due dates.

Feedback and escalation pathway for concerns raised before deployment.

### Resources

CDC Crisis and Emergency Risk Communication: Useful for planning clear communications, trust-building, and response messaging when workflows change.

plainlanguage.gov: Supports plain-language communication planning for staff, partners, and public-facing materials.

AHRQ TeamSTEPPS: Team communication, role clarity, and operational change support in health settings.

NIST AI Risk Management Framework (AI RMF 1.0): Use to connect change management with human oversight, accountability, and risk communication.

## Play 7: Prioritize Use Cases

Identify and prioritize AI use cases aligned with public health priorities and readiness, selecting a small number most likely to deliver meaningful impact.

Why it matters: Disciplined prioritization keeps resources focused and ensures every project is reviewed for equity risk, data feasibility, legal compliance, change readiness, and alignment with the AI vision.

Who should participate: Program areas, Governance committee, Data owners, Equity staff, Community advisors, IT/security, Change leads

### Key Questions

Which use cases are high impact and feasible?

Which risks require mitigation?

Which pilots should start first?

### Key Actions

Invite program areas to submit candidate use cases.

Score impact, feasibility, equity, scalability, sustainability, and data availability.

Apply the Use Case Fit Test.

Select 1-3 initial pilots.

Submit selected use cases for governance approval.

### Outputs

AI use case intake list.

Initial use case descriptions and business/public health rationale.

Use case scoring and prioritization matrix.

Equity, privacy, legal, data, and operational risk flags.

Human-centered decision rule for each prioritized use case.

Missing voices analysis for high-impact or community-facing use cases.

Environmental and resource impact review for compute-intensive, vendor-hosted, or large-scale AI uses.

Data readiness and feasibility notes.

Governance-approved use case portfolio.

Pilot recommendations, sequencing, and conditions.

Deferred or rejected use cases with rationale.

### Resources

NIST AI Risk Management Framework (AI RMF 1.0): Supports risk-based screening, governance review, and use case prioritization.

ASPPH AI Framework Report: Human-centered decision rules, missing voices analysis, and environmental/resource impact considerations during prioritization.

HHS Civil Rights and AI: Use when scoring use cases for equity, nondiscrimination, and potential disparate impact.

Fairness and Machine Learning: Bias, fairness limitations, and tradeoffs when prioritizing AI use cases.

Mehrabi et al. (2021): A survey on bias and fairness in machine learning: Peer-reviewed overview of bias sources and fairness considerations.

## Play 8: Develop a Funding Strategy

Build a coordinated multi-year funding strategy that maps approved use cases and implementation needs to funding sources, staffing, change management, procurement, infrastructure, monitoring, evaluation, and sustainment investments.

Why it matters: AI projects often fail when resources are misaligned: funded for one phase but not the next, approved without dedicated staff, missing change supports, or dependent on missing infrastructure. Funding strategy should shape the roadmap before the agency commits to sequencing.

Who should participate: Finance, Grants, Program sponsors, IT leadership, Procurement, Governance committee

### Key Questions

Which grants or budgets support each phase?

What sustainment costs must be covered?

What contingency plans are needed?

### Key Actions

Map each approved or proposed project to potential funding sources.

Document FTE, contractor, infrastructure, training, evaluation, procurement, and sustainment costs.

Update DMI, PHIG, and other grant work plans.

Confirm funding assumptions before roadmap sequencing is finalized.

Review resource allocation quarterly.

### Outputs

Funding strategy for the AI roadmap.

Funding source inventory and eligibility notes.

Grant alignment table for approved or proposed AI activities.

Pilot, scale, sustainment, staffing, infrastructure, training, and evaluation cost estimates.

Total cost of ownership and sustainability analysis.

Procurement and vendor cost assumptions.

Sustainment plan beyond pilot funding.

Funding gaps, contingencies, and decision points.

Leadership or governance briefing on resource needs.

### Resources

CDC Data Modernization Initiative: Use to align the roadmap with data infrastructure, interoperability, cloud, and analytics modernization.

ONC Trusted Exchange Framework and Common Agreement: Interoperability and exchange considerations that may affect roadmap dependencies.

CSTE: Peer network and implementation resource for data modernization and surveillance planning.

PHAB Standards and Measures: Useful for connecting AI roadmap work to public health performance, quality, and accreditation expectations.

## Play 9: Design the Roadmap

Translate vision, governance, readiness, change planning, funding assumptions, and approved use cases into a sequenced multi-year roadmap.

Why it matters: A roadmap prevents isolated pilots and makes shared infrastructure, governance reviews, staffing, funding, change supports, and dependencies visible before implementation starts.

Who should participate: Project sponsors, PMO, Governance committee, IT, Data owners, Finance, Change leads

### Key Questions

What must happen before each pilot?

Which dependencies are shared?

Where are governance, funding, and change readiness gates?

### Key Actions

Complete a project charter for each approved use case.

Place projects on the implementation timeline.

Identify shared dependencies and funding assumptions.

Present the roadmap to governance for approval.

Publish a one-page roadmap summary and update every six months.

### Outputs

Governance-approved AI roadmap.

Sequenced implementation timeline.

Project charters for approved use cases.

Shared dependencies across data, technology, governance, workforce, funding, and procurement.

Milestones, decision gates, and review points.

Resource, staffing, vendor, funding, and infrastructure assumptions.

Roadmap dependency and risk register.

Risk register for roadmap delivery.

Roadmap update cadence and ownership.

### Resources

Public Health Infrastructure Grant: Funding source for workforce, data systems, organizational capacity, governance, and health equity work.

CDC Data Modernization Initiative: Funding and strategy context for data infrastructure, interoperability, and analytics capacity.

HRSA digital health and telehealth programs: Relevant to communication, access, rural health, and digital health use cases.

EPA environmental justice grants: Relevant to environmental health, GeoAI, heat risk, and environmental justice applications.

FEMA grants: Relevant to emergency preparedness, disaster resilience, and response-oriented AI planning.

## Play 10: Execute Change Management

Execute the change management plan during pilot and deployment by communicating clearly, training staff, supporting adoption, and tracking concerns through governance.

Why it matters: Deployment is where planned change support becomes real. Staff need timely communication, hands-on support, feedback channels, clear escalation paths, and a visible training tracker as workflows change.

Who should participate: Change leads, Supervisors, Communications, AI champions, Pilot users, Governance committee

### Key Questions

Are staff prepared to use the system?

Which roles have completed the required learning modules?

What concerns are emerging during deployment?

How will feedback and errors be reported?

### Key Actions

Launch staff communications and FAQs.

Deliver role-based training and office hours.

Track completion of required learning modules by role.

Support change champions with protected time.

Track staff concerns and barriers.

Report adoption risks and feedback through governance.

### Outputs

Executed staff communication plan.

Final staff FAQ and deployment messages.

Role-based training completion summary.

Learning module completion status by role or staff group.

List of staff groups needing follow-up coaching, office hours, champion support, refresher training, or supervisor verification.

Office hours, support, and change champion activation plan.

Adoption support log.

Change management execution dashboard.

Staff concerns, barriers, and feedback tracker.

Escalation record for issues routed to governance or leadership.

Change adoption measures and lessons learned.

### Resources

CDC Crisis and Emergency Risk Communication: Use to support trusted communications during deployment and workflow change.

plainlanguage.gov: Plain-language staff communications, FAQs, and public-facing explanations.

AHRQ TeamSTEPPS: Supports team communication, implementation readiness, and adoption support.

CDC STLT Data Connection: Peer-learning resource for implementation lessons and staff support approaches.

## Play 11: Build and Deploy AI Solutions

Develop, test, pilot, deploy, and scale AI solutions that support governance-approved use cases and comply with governance, equity, change management, and validation requirements.

Why it matters: Pilots are for learning. Keep them small, time-bounded, and limited in scope. Scaling is not automatic; it requires explicit governance approval and evidence that adoption support is working.

Who should participate: Product owners, Data engineers, Vendors, Security, Pilot users, Evaluation staff, Governance committee, Change leads

### Key Questions

Has validation been completed?

What pilot evidence supports scale?

Are equity safeguards and adoption supports working?

### Key Actions

Confirm technical infrastructure and data pipelines.

Test with synthetic or de-identified data.

Run pilots for 90-120 days.

Evaluate using pilot dashboard and scale decision framework.

Submit scale-up plans to governance before expansion.

### Outputs

AI pilot or deployment plan.

Technical infrastructure readiness checklist.

Data quality and data use documentation.

Vendor evaluation record, where applicable.

STLT AI procurement and vendor addendum, where applicable.

Decision record for whether public, enterprise, in-house, RAG, or vendor-hosted AI architecture is appropriate for the data tier and use case.

Model testing and validation protocol.

Equity and subgroup testing results.

Incident response and escalation plan.

Deployment readiness and go-live checklist.

Pilot evaluation dashboard.

Pilot-to-scale decision recommendation.

Governance decision record for deploy, revise, pause, scale, or retire.

### Resources

FedRAMP: Use for hosted AI tools, cloud services, and security authorization review.

ASPPH AI Framework Report: Architecture decisions such as tiered data classification, in-house/RAG approaches, and incident tracking.

HIPAA and Business Associate Agreements: PHI, vendor relationships, and privacy obligations during development and deployment.

CISA Secure by Design: Supports secure development, vendor review, and deployment expectations.

ONC Trusted Exchange Framework and Common Agreement: Interoperability and data exchange issues in AI-enabled workflows.

Kahn et al. (2015): Transparent reporting of data quality: Peer-reviewed resource for data quality documentation and reporting.

## Play 12: Execute Governance and Oversight

Sustain responsible AI through regular governance reviews, policy maintenance, compliance auditing, incident review, version control, and named accountability for every deployed or retired AI system.

Why it matters: Governance intensifies after go-live. The agency must continually ask whether each AI system is still doing what it was intended to do, whether documentation and approvals remain current, whether incidents or monitoring findings require action, and whether the system should continue, change, pause, or be retired.

Who should participate: AI governance committee, Health officer or executive sponsor, Operational system owners, Legal and privacy officers, Compliance and audit staff, Security and incident response leads, Evaluation and equity leads, Program leadership, Vendor or partner representatives when applicable

### Key Questions

Are governance records complete, current, and stored where they can be audited?

Have monitoring results, incidents, equity findings, or user feedback triggered a governance decision?

Do policies, data use agreements, validation records, or system documentation need updating?

Are compliance obligations being met across privacy, security, procurement, accessibility, and civil rights requirements?

Should the system continue as approved, be revised, paused, scaled, retired, or replaced?

### Key Actions

Hold governance reviews monthly during pilots and quarterly in sustainment, using a standard agenda and decision log.

Review performance monitoring, equity monitoring, incident reports, user feedback, audit findings, and continuous improvement actions.

Confirm that each AI system has a named operational owner, current documentation, approved data use agreements, validation records, and escalation contacts.

Conduct annual compliance audits and targeted reviews after incidents, model changes, vendor changes, or major policy updates.

Update policies, charters, review procedures, approval conditions, and version-control logs when guidance, technology, risks, or agency priorities change.

Document governance decisions, required corrective actions, owners, deadlines, and evidence of closure.

Define sunset criteria and retire or replace AI systems that no longer meet performance, equity, safety, legal, operational, or public trust standards.

### Outputs

Governance review agenda and decision log.

AI system inventory updates.

Incident response records and corrective-action tracking.

Plain-language public notice updates and public concern review records.

Human-centered decision rule compliance review.

Compliance audit checklist and findings.

Policy update and version control log.

Review of data use agreements, validation records, and approval conditions.

Governance decisions to continue, revise, pause, retire, or replace AI systems.

Documented owners, deadlines, and evidence of closure for required actions.

### Resources

HHS AI use case inventory requirements: Use for maintaining AI system records, owners, purposes, status, and accountability.

ASPPH AI Framework Report: Public transparency, rigorous oversight, incident reporting, and bias tracking expectations.

NIST AI Risk Management Framework (AI RMF 1.0): Governance review, ongoing risk management, and oversight.

CISA Incident Response Plan Basics: Supports incident response planning and escalation processes.

HIPAA and Business Associate Agreements: Privacy, data sharing, vendor oversight, and compliance obligations.

FedRAMP: Ongoing security and cloud authorization review.

## Play 13: Monitor and Evaluate AI Systems

Assess whether deployed AI systems perform as expected and deliver measurable public health value with continuous attention to equity and adoption.

Why it matters: Deployment without monitoring is how AI systems cause harm quietly. Monitoring is a core governance function, not an administrative afterthought.

Who should participate: Operational owners, Evaluation staff, Equity staff, Data scientists, Governance committee, Program leadership

### Key Questions

Is performance stable?

Are disparities emerging?

What improvements or escalation are required?

### Key Actions

Monitor reliability monthly and report quarterly.

Track subgroup performance continuously.

Conduct hallucination and fabrication audits.

Evaluate public health outcomes.

Use a continuous improvement log to track actions.

### Outputs

Performance monitoring dashboard.

Equity and disparity impact monitoring results.

Reliability, data quality, model drift, and incident trend summaries.

Hallucination, misinformation, automation bias, and unsafe output trend review.

Community complaint, correction, and feedback trend review.

Missing voices and subgroup performance monitoring results.

User feedback and adoption findings.

Outcome evaluation report.

Continuous improvement log.

Recommendations to improve, scale, revise, pause, retire, or replace AI systems.

Monitoring cadence and next review schedule.

### Resources

NIST AI Risk Management Framework (AI RMF 1.0): Use for monitoring, measurement, model drift, and continuous risk management.

ASPPH AI Framework Report: Ongoing bias tracking, hallucination and misinformation review, human-centered AI evaluation, and public accountability.

Model drift and performance monitoring: Sustainment risks requiring dashboards, audits, and improvement actions.

Equity impact assessment and subgroup monitoring: Monitoring disparate impact and subgroup performance after deployment.

Kahn et al. (2015): Transparent reporting of data quality: Supports data quality transparency in monitoring and evaluation.

World Health Organization: Ethics and governance of AI for health: Supports ongoing oversight, accountability, and responsible use after implementation.

# Toolkit Inventory

## Tool 1: AI Vision & Principles Workshop

Facilitate leadership alignment on mission, principles, priority problems, and prohibitions.

Type: Workshop. Topic: Vision. Maturity: Awareness.

Supporting plays: 1. Roles: Leadership.

### Workshop setup

Workshop date

Facilitator

Participants

Current AI uses known or suspected

### Shared understanding

Public health problems AI might help solve

Risks the agency must avoid

Values that should guide AI use

### Outputs

Draft AI vision statement

Responsible AI principles

Initial guardrails/prohibitions

Next governance actions

## Tool 2: Responsible AI Policy Template

Create binding commitments on transparency, privacy, equity, human oversight, and legal compliance.

Type: Template. Topic: Governance. Maturity: Awareness.

Supporting plays: 1, 3. Roles: Legal, Governance.

### Policy header

Policy title

Policy number

Effective date

Owner

Approving authority

Review cadence

### Policy scope and requirements

Covered AI systems and users

Permitted uses

Prohibited uses

Required approvals before use

Privacy/security requirements

Equity and human oversight requirements

### Roles and enforcement

Governance committee responsibilities

Program responsibilities

IT/security responsibilities

Incident response requirements

Policy exceptions and enforcement

## Tool 3: Equity Impact Assessment Checklist

Evaluate potential disparate impacts and required mitigations.

Type: Checklist. Topic: Equity. Maturity: Pilots.

Supporting plays: 1, 2, 3, 7, 11. Roles: Equity, Governance.

### Project and community context

AI project/use case

Population groups affected

Community partners consulted

Known disparities or access barriers

### Equity review

Potential benefits

Potential harms

Subgroup performance concerns

Language/accessibility considerations

Tribal data sovereignty or local context considerations

### Mitigation plan

Required design changes

Monitoring metrics

Community feedback plan

Governance decision or conditions

## Tool 4: AI Policy Landscape Scan

Document state, local, tribal, territorial, agency, and program-specific laws, policies, public records rules, procurement limits, and IT restrictions that shape AI use.

Type: Worksheet. Topic: Legal and policy. Maturity: Readiness.

Supporting plays: 1, 2, 3. Roles: Legal, Privacy, IT, Governance.

### Policy landscape

Jurisdiction or agency

State/local/tribal/territorial laws

Agency IT policies

Public records requirements

Procurement restrictions

### Risk implications

Commercial AI restrictions

Confidentiality constraints

HIPAA/privacy implications

Political or legislative sensitivities

Approvals required before use

### Action plan

Policies to update

Responsible owner

Timeline

Governance decision needed

## Tool 5: AI Environmental and Resource Impact Review

Assess energy, water, e-waste, data center, procurement, and environmental justice considerations before approving AI use cases or vendors.

Type: Checklist. Topic: Sustainability. Maturity: Pilots.

Supporting plays: 1, 7, 8. Roles: Procurement, Equity, Leadership.

### AI resource profile

Use case or vendor

Model or service type

Expected scale of use

Hosting environment

### Environmental considerations

Energy intensity

Water use or cooling concerns

E-waste or hardware needs

Data center location or environmental justice concerns

Vendor sustainability claims

### Decision record

Lower-impact alternatives

Procurement requirements

Equity or community concerns

Approval conditions

## Tool 6: Human-Centered AI Decision Rule Checklist

Document which decisions AI may support, summarize, prioritize, or draft and which decisions must remain with named human owners.

Type: Checklist. Topic: Human oversight. Maturity: Pilots.

Supporting plays: 1, 7, 11, 12, 13. Roles: Governance, Program leads, Evaluation.

### Decision context

AI system or use case

Decision or action supported

Potentially affected populations

Consequence level

### Human-centered rule

AI may summarize/draft/prioritize

AI may not independently decide

Named human decision owner

Required review before action

Appeal or correction pathway

### Oversight

Automation bias safeguards

Audit trail requirements

Monitoring metrics

Governance review cadence

## Tool 7: AI Readiness Self-Assessment

Assess capacity across leadership, data, workforce, equity, partnerships, privacy, and security.

Type: Assessment. Topic: Governance. Maturity: Readiness.

Supporting plays: 2. Roles: Leadership, IT, Equity.

### Assessment setup

Agency/division

Assessment date

Facilitator

Participating roles

### Scoring logic

Question scale: 0 None, 1 Some, 2 Good, 3 Excellent

Section score formula: raw section score divided by 12, multiplied by 100

Total score formula: raw total score divided by 72, multiplied by 100

Interpretation rule: total score shows the overall readiness stage; section scores determine the next plays

### Readiness domains

Leadership and governance 100-point score/rationale

Data infrastructure 100-point score/rationale

Workforce capacity 100-point score/rationale

Equity and community engagement 100-point score/rationale

Partnerships and collaboration 100-point score/rationale

Privacy and security 100-point score/rationale

### Gap register

Highest priority gaps

Owners and due dates

Governance review flags

Recommended next plays

## Tool 8: AI Project Charter

Define project scope, success criteria, data needs, safeguards, timeline, budget, and risks.

Type: Planning. Topic: Project management. Maturity: Readiness.

Supporting plays: 2, 7, 11. Roles: Program leads, PMO.

### Project identity

Project name

Program area

Project sponsor

Project lead

Technical lead

Governance review date

### Problem and scope

Problem statement

Public health goal

In scope

Out of scope

Affected populations

Data sources

### Delivery plan

Success measures

Risks and mitigations

Equity considerations

Partners/vendors

Milestones

Decision requested

## Tool 9: Data Quality Assessment Checklist

Assess completeness, timeliness, accuracy, interoperability, and data governance.

Type: Checklist. Topic: Data. Maturity: Readiness.

Supporting plays: 2, 11. Roles: Data owners, IT.

### Data source profile

Dataset/system name

Data owner

Program context

Intended AI use

Data refresh cadence

### Data quality review

Completeness

Timeliness

Accuracy

Consistency

Interoperability

Representativeness

### Readiness decision

Quality gaps

Bias or missingness concerns

Privacy/security constraints

Required remediation

Go/no-go recommendation

## Tool 10: Tiered Data Classification for AI Use

Classify data as public, internal, confidential, or highly restricted and define which AI environments may use each tier.

Type: Worksheet. Topic: Data governance. Maturity: Readiness.

Supporting plays: 2, 3, 11. Roles: Data owners, Privacy, Security.

### Data tier profile

Dataset or data category

Data owner

Classification tier

Sensitivity rationale

### Allowable AI environments

Public AI tool allowed?

Enterprise AI tool allowed?

In-house/RAG tool allowed?

Vendor-hosted tool allowed?

Highly restricted data prohibitions

### Controls and approvals

Access controls

Retention/destruction rules

Legal/privacy approval

Security approval

Review cadence

## Tool 11: AI Advisory Committee Charter

Define advisory committee membership, cadence, responsibilities, and decision flow.

Type: Template. Topic: Governance. Maturity: Awareness.

Supporting plays: 3, 4. Roles: Governance, Community engagement.

### Committee purpose and authority

Mission statement

Decision authority

Escalation authority

Policy recommendation authority

### Membership

Required roles

Community/advisory participation

Chair/co-chair

Term or rotation

Quorum

### Operations

Meeting cadence

Decision process

Documentation requirements

Conflict of interest approach

## Tool 12: AI Governance Board Charter

Establish authority, membership, voting, meeting cadence, and oversight responsibilities.

Type: Template. Topic: Governance. Maturity: Awareness.

Supporting plays: 3. Roles: Leadership, Governance.

### Board identity and authority

Board name

Binding authority

Covered AI activities

Approval/suspension powers

### Membership and structure

Required members

Chair

Voting rules

Quorum

Conflict of interest process

### Governance operations

Review cadence

Submission requirements

Decision documentation

Appeals/escalation process

## Tool 13: AI Use Case Intake, Risk Review, and System Inventory Template

Capture proposed AI uses, classify risk, document review status, and maintain the approved AI system inventory.

Type: Template. Topic: Governance. Maturity: Readiness.

Supporting plays: 3, 7, 12. Roles: Governance, Program leads.

### Use case intake

Use case name

Submitting program/division

Business owner

Intended users

Public health purpose

AI functionality requested

### Risk review

Data involved

PHI or sensitive data present?

Population groups affected

Privacy/security review required

Equity review required

Validation required

Risk tier

### System inventory record

Approval status

Governance decision date

Operational owner

Monitoring cadence

Review/renewal date

Retirement or pause conditions

## Tool 14: Model Validation & Documentation Standards

Set documentation, validation, testing, and evidence standards before deployment.

Type: Standard. Topic: Validation. Maturity: Pilots.

Supporting plays: 3, 11. Roles: Data science, Governance.

### System documentation card

System name

System version

Program area/use case

AI system type

Data sources

Vendor or model owner

### Validation standards

Performance metrics

Test population

Equity/disparity tests

Human review requirements

Known limitations

### Approval record

Documentation complete?

Legal/privacy review

Governance decision

Conditions before deployment

## Tool 15: Data Use Agreement (AI) Template

Document AI-specific data-sharing, privacy, security, and sovereignty requirements.

Type: Template. Topic: Data. Maturity: Pilots.

Supporting plays: 3, 11. Roles: Legal, Privacy.

### Agreement header

Agreement title

Agreement number

Effective date

Expiration/review date

Parties

### Data terms

Data sources

Permitted AI uses

Prohibited uses

Retention and destruction

Access controls

Security requirements

### Oversight

Audit rights

Incident reporting

Subcontractor restrictions

Model/data reuse restrictions

Approval signatures

## Tool 16: Incident Response Checklist

Prepare escalation, containment, documentation, and corrective-action steps.

Type: Checklist. Topic: Security. Maturity: Deployment.

Supporting plays: 3, 11, 12. Roles: Security, Legal.

### Incident intake

Incident date/time

AI system

Reported by

Incident type

Who or what was affected

### Immediate response

Containment steps taken

System paused or limited?

Notifications made

Privacy/security concerns

Evidence preserved

### Resolution

Root cause

Corrective actions

Governance review outcome

Communication needs

Closure date

## Tool 17: Compliance Audit Checklist

Audit compliance with policies, legal requirements, documentation, and monitoring obligations.

Type: Checklist. Topic: Compliance. Maturity: Optimization.

Supporting plays: 3, 12. Roles: Compliance, Legal.

### Audit profile

Audit period

Lead auditor

Date initiated

Date completed

### Compliance review

Governance structure compliance

Project charter compliance

Equity impact assessment compliance

Validation compliance

Data use agreement compliance

Community engagement compliance

### Audit summary

Compliant count

Partially compliant count

Non-compliant count

Overall rating

Corrective action plan

## Tool 18: Policy Update & Version Control Log

Track AI governance policy changes, approvals, effective dates, and owners.

Type: Log. Topic: Governance. Maturity: Optimization.

Supporting plays: 3, 12. Roles: Governance, Legal.

### Policy register

Policy/document name

Document number

Current version

Effective date

Next review due

Owner

### Version history

Document name

Version

Date changed

Change summary

Reason for change

Approved by

### Annual review

Policies reviewed

Updates required

Retired documents

Next review cycle

Governance approval record

## Tool 19: Plain-Language AI Public Notice Template

Explain what AI is being used, why, what data are involved, what humans decide, known limits, and how people can raise concerns.

Type: Template. Topic: Transparency. Maturity: Deployment.

Supporting plays: 3, 4, 10, 12. Roles: Communications, Equity, Governance.

### Notice basics

AI system or workflow

Public health purpose

Audience

Where notice will appear

### Plain-language explanation

What the AI does

What data are involved

What humans still decide

Known limitations

How to request help or raise concerns

### Review and publication

Legal/privacy review

Equity and language access review

Governance approval

Publication date

Next review date

## Tool 20: Community Engagement Planning

Plan inclusive engagement, feedback loops, accessibility, and community accountability.

Type: Planning. Topic: Engagement. Maturity: Readiness.

Supporting plays: 4, 7. Roles: Community engagement, Equity.

### Engagement overview

AI project/use case

Communities affected

Engagement lead

Engagement timeframe

### Engagement plan

Stakeholder groups

Engagement methods

Accessibility and language needs

Questions for community input

How feedback will influence design

### Documentation

Feedback received

Changes made based on feedback

Unresolved concerns

Next engagement touchpoint

## Tool 21: Stakeholder Mapping & RACI

Map stakeholders, roles, responsibilities, and engagement owners.

Type: Template. Topic: Engagement. Maturity: Readiness.

Supporting plays: 4. Roles: Program leads.

### Stakeholder universe

Internal stakeholders

Community stakeholders

Partner organizations

Groups affected by AI decisions or outputs

### RACI mapping

Responsible roles

Accountable decision-maker

Consulted stakeholders

Informed stakeholders

### Engagement strategy

Influence/interest notes

Engagement approach

Timing

Owner

Risks if not engaged

## Tool 22: Missing Voices Analysis

Identify groups whose data, perspectives, language needs, access barriers, or community context may be missing from AI design, validation, or monitoring.

Type: Checklist. Topic: Equity. Maturity: Pilots.

Supporting plays: 4, 7, 13. Roles: Equity, Community engagement, Evaluation.

### Population and context scan

Use case or system

Groups affected

Groups represented in available data

Groups missing or underrepresented

### Missing voices review

Language access gaps

Disability access gaps

Rural or small-population concerns

Tribal sovereignty considerations

Community knowledge not captured in data

### Mitigation and validation

Engagement needed

Data supplementation or limitations

Subgroup validation plan

Decision conditions

Monitoring indicators

## Tool 23: Change Management Plan

Plan communications, training, workflow changes, adoption support, and deployment execution.

Type: Template. Topic: Workforce. Maturity: Pilots.

Supporting plays: 5, 6, 10. Roles: HR, Supervisors, Change leads.

### Change context

AI system or workflow change

Affected programs/staff

What will change in daily work

Expected benefits

### Adoption plan

Communication audiences

Training needs

AI champions/change leads

Support channels

Feedback collection plan

### Resistance and sustainment

Anticipated concerns

Mitigation actions

Metrics for adoption

Owner and review cadence

## Tool 24: AI Workforce Competency Framework

Define AI literacy, proficient, and practitioner capabilities by role.

Type: Framework. Topic: Workforce. Maturity: Readiness.

Supporting plays: 5. Roles: HR, Training.

### Role inventory

Staff groups covered

Current AI literacy level

Target AI literacy level

Priority roles for training

### Competency expectations

AI aware competencies

AI proficient competencies

AI practitioner competencies

Supervisor/leader competencies

### Training implications

Required training modules

Champion support needs

Timeline

Measures of competency

## Tool 25: AI Champion Designation & Role Guide

Select and support AI champions who help peers adopt responsible practices.

Type: Guide. Topic: Workforce. Maturity: Readiness.

Supporting plays: 5, 10. Roles: Supervisors, Champions.

### Champion role design

Program areas needing champions

Champion responsibilities

What champions are not responsible for

Time allocation

### Selection and support

Selection criteria

Nomination process

Training provided

Community of practice cadence

### Feedback loop

Issues champions should surface

Reporting channel

Success measures

## Tool 26: Training Needs Assessment Checklist

Identify role-based training gaps before designing training pathways.

Type: Checklist. Topic: Workforce. Maturity: Readiness.

Supporting plays: 5. Roles: HR, Training.

### Assessment profile

Assessment period

Conducted by

Date completed

Number of staff surveyed/consulted

### Training needs

Staff by AI literacy level

Current percent meeting target

Priority skill gaps

Role-specific training needs

### Training plan

Recommended modules

Priority audiences

Timeline

Resource needs

Evaluation measures

## Tool 27: AI Bridge Professional Role Guide

Define the cross-functional role that translates between program staff, IT, leadership, legal, vendors, community partners, and data teams.

Type: Guide. Topic: Workforce. Maturity: Readiness.

Supporting plays: 5. Roles: Leadership, HR, Training.

### Role purpose

Bridge professional title

Program or enterprise scope

Primary problems this role solves

Reporting relationship

### Core responsibilities

Technical translation

Program and workflow translation

Community and equity coordination

Vendor/procurement support

Governance documentation support

### Capacity plan

Required skills

Training needed

Time allocation

Success measures

## Tool 28: Role-Based Training Plan and Completion Tracker

Assign learning modules by role, set completion standards, track deadlines, verify completion, and identify follow-up support needs.

Type: Tracker. Topic: Workforce. Maturity: Readiness.

Supporting plays: 5, 10. Roles: Training, Supervisors, Organization administrators, AI champions.

### Training plan profile

Training plan name

Training period

Training owner

Organization administrator

Related play or deployment

Last updated

### Role-based module assignments

Executive leadership required modules

Governance committee required modules

Program staff required modules

Data/analytics staff required modules

IT/security staff required modules

Legal/privacy/procurement required modules

Communications/equity/community engagement required modules

### Completion tracking

Role or staff group

Required completion date

Completion standard

Completion status

Supervisor or administrator verification

Evidence or notes

### Follow-up and support

Staff groups needing additional support

Office hours or coaching schedule

Champion or mentor assigned

Refresher training needs

Escalation or governance issues

## Tool 29: Staff Communication & FAQ Template

Prepare transparent staff communications and answers to expected questions.

Type: Template. Topic: Change. Maturity: Pilots.

Supporting plays: 6, 10. Roles: Communications, Supervisors.

### Announcement draft

Subject line

What the AI does

Why it is being used

What staff should expect

What AI will not do

### FAQ

Privacy and data protections

Human review and decision authority

Training and support

How to report concerns

### Communication plan

Audiences

Channels

Timing

Spokesperson/owner

## Tool 30: Resistance & Barrier Identification

Surface operational, cultural, and trust barriers before launch and during deployment.

Type: Worksheet. Topic: Change. Maturity: Pilots.

Supporting plays: 6, 10. Roles: Change leads, Staff.

### Concern inventory

Concern raised

Source or role

Concern type

Frequency raised

Leadership response

### Barrier analysis

Workforce/job security barriers

Privacy/data barriers

Equity/fairness barriers

Technical/usability barriers

Organizational/resource barriers

### Response plan

Actions to address concerns

Owner

Due date

How resolution will be communicated

## Tool 31: Use Case Scoring & Prioritization Matrix

Score use cases for impact, feasibility, equity, scalability, sustainability, and risk.

Type: Matrix. Topic: Use cases. Maturity: Pilots.

Supporting plays: 7. Roles: Governance, Program leads.

### Use case submission

Use case name

Submitting program/division

Problem to solve

Target users

Data needed

Expected public health value

### Scoring matrix

Impact score/rationale

Feasibility score/rationale

Equity score/rationale

Risk score/rationale

Sustainability score/rationale

### Prioritization decision

Weighted score

Rank

Governance conditions

Pilot recommendation

## Tool 32: Vendor Evaluation Checklist

Evaluate vendors for privacy, security, transparency, validation, support, and cost.

Type: Checklist. Topic: Procurement. Maturity: Pilots.

Supporting plays: 8, 11. Roles: Procurement, IT.

### Vendor and solution profile

Vendor name

Product/service

Use case supported

Data involved

Procurement stage

### Evaluation criteria

Security and privacy controls

BAA/FedRAMP or equivalent status

Transparency and documentation

Validation evidence

Equity and bias testing

Support and exit terms

### Comparison and recommendation

Strengths

Risks

Contract requirements

Recommended decision

## Tool 33: Funding Strategy Checklists

Align projects with funding sources, grant work plans, sustainment, and contingency plans.

Type: Checklist. Topic: Funding. Maturity: Readiness.

Supporting plays: 8. Roles: Finance, Grants.

### Funding landscape

AI initiative or portfolio

Estimated pilot cost

Estimated scale/sustainment cost

Existing funding sources

### Funding alignment

DMI alignment

PHIG alignment

Other federal/state/private opportunities

Allowable activities

Grant deadlines

### Sustainment plan

Staffing plan

Infrastructure costs

Procurement costs

Evaluation costs

Contingency plan

## Tool 34: STLT AI Procurement and Vendor Addendum

Add public-sector AI requirements for data residency, audit rights, model training restrictions, cybersecurity, accessibility, public records, exit terms, and subcontractors.

Type: Checklist. Topic: Procurement. Maturity: Pilots.

Supporting plays: 8, 11. Roles: Procurement, Legal, IT.

### Procurement profile

Vendor/product

Use case supported

Data involved

Contract vehicle

Procurement stage

### STLT requirements

Data residency and retention

No model training on agency data

Audit rights

Subcontractor disclosure

Public records considerations

Accessibility requirements

Cybersecurity requirements

### Contract decision

Required contract language

Unresolved risks

Exit or transition terms

Recommended decision

## Tool 35: AI Total Cost of Ownership and Sustainability Worksheet

Estimate pilot, scale, sustainment, staffing, infrastructure, vendor, procurement, training, monitoring, and evaluation costs.

Type: Worksheet. Topic: Funding. Maturity: Readiness.

Supporting plays: 8, 9, 11. Roles: Finance, Grants, Procurement, IT.

### Cost profile

AI initiative or portfolio

Pilot cost estimate

Scale cost estimate

Sustainment period

Cost owner

### Cost categories

Staffing and contractor costs

Vendor and licensing costs

Infrastructure and hosting costs

Procurement and legal costs

Training and change management costs

Monitoring and evaluation costs

### Sustainability decision

Confirmed funding sources

Funding gaps

Contingency plan

Total cost of ownership risk

Decision or next action

## Tool 36: AI Implementation Timeline

Sequence milestones, dependencies, approvals, pilot phases, and scale decisions.

Type: Planning. Topic: Roadmap. Maturity: Readiness.

Supporting plays: 9, 11. Roles: PMO, IT.

### Roadmap overview

Roadmap period

Strategic priorities

Approved use cases

Shared dependencies

### Timeline

Quarter 1 milestones

Quarter 2 milestones

Quarter 3 milestones

Quarter 4 milestones

12-36 month roadmap items

### Governance and resources

Approval gates

Funding dependencies

Staffing dependencies

Risks to timeline

Next update date

## Tool 37: Roadmap Dependency and Risk Register

Track roadmap dependencies, governance gates, risks, owners, due dates, mitigation actions, and escalation decisions.

Type: Register. Topic: Roadmap. Maturity: Readiness.

Supporting plays: 9, 11, 12. Roles: PMO, Governance, IT.

### Roadmap item

Project or dependency

Related play or use case

Owner

Target date

Current status

### Dependency and risk review

Upstream dependency

Downstream impact

Governance gate

Funding dependency

Infrastructure or staffing dependency

Risk level

### Mitigation and escalation

Mitigation action

Escalation trigger

Escalation owner

Decision needed

Resolution date

## Tool 38: Change Management Execution Dashboard

Track training completion, communication delivery, adoption support, staff feedback, barriers, escalations, and deployment readiness during change execution.

Type: Dashboard. Topic: Change. Maturity: Deployment.

Supporting plays: 10. Roles: Change leads, Supervisors, AI champions.

### Deployment change profile

AI system or workflow

Deployment phase

Affected staff groups

Change lead

Reporting period

### Execution dashboard

Communications delivered

Training completion

Office hours/support provided

Champion activity

Adoption indicators

Staff feedback themes

### Escalation and readiness

Open barriers

Issues escalated to governance

Corrective actions

Readiness status

Lessons learned

## Tool 39: Technical Infrastructure Readiness Checklist

Confirm environments, access controls, integrations, monitoring, and secure deployment paths.

Type: Checklist. Topic: Technology. Maturity: Pilots.

Supporting plays: 11. Roles: IT, Security.

### Project readiness profile

Project/system name

Assessment date

IT lead

AI program manager

### Infrastructure checklist

Cloud/computing readiness

Integration/API readiness

Data pipeline readiness

Backup/recovery readiness

### Security and access

Role-based access controls

Logging/monitoring

Security review status

Gaps/actions/timeline

## Tool 40: AI Model Testing & Validation Protocol

Define test design, performance thresholds, human review, and validation evidence.

Type: Protocol. Topic: Validation. Maturity: Pilots.

Supporting plays: 11. Roles: Data science.

### Testing profile

System/model name

Version

Testing lead

Testing period

Deployment environment

### Testing phases

Unit/component testing

Integration testing

Performance testing

Equity/subgroup testing

User acceptance testing

### Validation decision

Pass criteria

Results

Open defects

Required remediation

Approval recommendation

## Tool 41: AI Pilot Evaluation Dashboard

Track pilot performance, adoption, equity, incidents, and go/no-go evidence.

Type: Dashboard. Topic: Evaluation. Maturity: Pilots.

Supporting plays: 11. Roles: Evaluation, Product owners.

### Pilot profile

AI system/pilot name

Program area

Pilot period

Report date

### Pilot dashboard

Pilot scope planned vs actual

Staff trained/active users

Performance results

Equity results

User feedback

Incidents

### Pilot conclusion

Benefits observed

Risks or limitations

Required changes

Recommendation for Tool 42

## Tool 42: Pilot-to-Scale Decision Framework

Support governance decisions on scale, revise, pause, or retire after pilot evaluation.

Type: Framework. Topic: Scale. Maturity: Pilots.

Supporting plays: 11. Roles: Governance, Leadership.

### Decision context

AI system/pilot name

Pilot period

Program area

Decision review date

### Evidence review

Pilot targets vs actual results

Equity and safety findings

Operational readiness

Funding/sustainment readiness

### Scale decision

Go / revise / pause / stop recommendation

Conditions for scale

Governance decision

Next review date

## Tool 43: AI Deployment Readiness and Go-Live Checklist

Confirm governance approval, validation, security, data readiness, staff training, communications, support, rollback plans, and go-live decision criteria before deployment.

Type: Checklist. Topic: Deployment. Maturity: Deployment.

Supporting plays: 11. Roles: Product owners, IT, Governance, Change leads.

### Go-live profile

AI system or release

Program area

Go-live date

Product owner

Technical owner

Governance review date

### Readiness checks

Governance approval complete

Validation complete

Security review complete

Data readiness confirmed

Training complete

Communications complete

Support plan ready

### Launch decision

Rollback or pause plan

Known risks

Approval conditions

Go/no-go recommendation

Post-launch review date

## Tool 44: Performance Monitoring Dashboard

Track reliability, performance, equity, incident trends, and improvement actions.

Type: Dashboard. Topic: Monitoring. Maturity: Deployment.

Supporting plays: 12, 13. Roles: Evaluation, Governance.

### Monitoring setup

AI system name

Program area

Reporting period

Operational owner

Governance review date

### Performance dashboard

Reliability/performance metrics

Usage metrics

Data quality indicators

Equity monitoring indicators

Incidents or anomalies

### Action tracking

Findings requiring action

Improvement actions

Owners and deadlines

Escalations to governance

## Tool 45: Continuous Improvement Log

Track improvement actions, owners, timelines, evidence, and closure.

Type: Log. Topic: Improvement. Maturity: Optimization.

Supporting plays: 12, 13. Roles: Operational owners.

### Log entry

Log ID

Date

AI system

Source

Issue/opportunity

### Action plan

Priority

Corrective or improvement action

Owner

Due date

Dependencies

### Closure

Status

Evidence of completion

Verified by

Date closed

Lessons learned

## Tool 46: AI Governance Review Meeting Template

Structure governance agendas, decisions, escalations, and action tracking.

Type: Template. Topic: Governance. Maturity: Optimization.

Supporting plays: 12. Roles: Governance.

### Pre-meeting preparation

Meeting date

Board chair

Quorum status

Dashboard package distributed

Equity report distributed

Incidents for review

### Agenda and decisions

Project approvals

Performance review

Equity review

Incident review

Policy/compliance update

### Meeting record

Decisions made

Conditions or follow-ups

Owners and deadlines

Next meeting date

## Tool 47: Equity & Disparity Impact Monitoring

Monitor subgroup performance and disparate impacts after deployment.

Type: Dashboard. Topic: Equity. Maturity: Deployment.

Supporting plays: 13. Roles: Equity, Evaluation.

### Monitoring profile

AI system name

Reporting period

Prepared by

Date

### Equity dashboard

Subgroups monitored

Sample sizes

Performance by subgroup

Disparity thresholds

Access or language barriers

### Response plan

Triggered concerns

Corrective actions

Community/stakeholder communication

Governance escalation

## Tool 48: AI Evaluation & Outcomes Reporting

Report public health outcomes, operational effects, and lessons learned.

Type: Template. Topic: Evaluation. Maturity: Deployment.

Supporting plays: 13. Roles: Evaluation, Leadership.

### Report header

AI system/program name

Reporting period

Report type

Audience

### Evaluation findings

Performance outcomes

Public health outcomes

Operational impacts

Equity impacts

User/staff feedback

### Recommendations

Continue/modify/scale/retire recommendation

Lessons learned

Next reporting period actions

# Case Studies and Promising Practices

## California Health Care Facility Inspection Documentation

Challenge: Health care facility inspectors must document findings clearly and connect observations to applicable laws, regulations, and requirements. That work can be time-consuming and difficult to standardize across inspection teams.

AI Solution: California's GenAI program identifies this as a CDPH pilot testing generative AI support for inspection report drafting and regulatory linkage.

Data Sources: Inspection notes, facility inspection findings, relevant laws, regulations, and state documentation requirements.

Workflow Impact: Inspectors would continue performing inspections and exercising professional judgment, while generative AI helps draft or organize report language and identify potentially relevant regulatory citations for human review.

Outcomes: The expected benefit is reduced documentation burden and faster linkage between inspection findings and applicable requirements. Because this is described as a pilot, the page should not present final outcome claims until public evaluation results are available.

Ethical/Privacy: Human inspector review is essential before any report language or regulatory linkage is finalized. Governance should address accuracy, explainability, legal sufficiency, record retention, bias in inspection language, and the risk of over-relying on generated citations.

California GenAI: GenAI projects

California GenAI: Health care facility inspections project

## California Language Access Translation Support

Challenge: Residents with limited English proficiency need timely, understandable, and culturally appropriate access to health and social services information. Traditional translation workflows can be slow, inconsistent, or difficult to scale across programs.

AI Solution: California's GenAI language access work explores generative AI to improve translation speed, consistency, efficiency, and cultural awareness, with human review and editing.

Data Sources: Health and social services content, source-language materials, translated drafts, terminology guidance, program context, and human reviewer feedback.

Workflow Impact: Generative AI can create first-draft translations or language-access materials that qualified staff review, edit, and approve before use. The workflow shifts translation from a fully manual first draft to an AI-assisted draft plus human quality review.

Outcomes: The expected benefit is faster, more consistent translation support for public-facing health and social services materials. Public-facing use should still depend on human review, quality assurance, and language access governance.

Ethical/Privacy: Risk controls should address mistranslation, cultural fit, health literacy, privacy, accessibility, and human review by qualified language-access staff before any material is released.

California GenAI: Language access project

California Health and Human Services Agency: Language Access

## Kansas Local Health Department AI Roadmap and GenAI Tools

Challenge: Local health departments need practical guidance on whether and how to use generative AI for routine operations, communications, grant writing, health literacy, and content review without creating privacy, quality, or trust risks.

AI Solution: The Kansas Public Health Collaborative created AI guidance and roadmap resources for local health departments, including practical GenAI tools and FAQs for communications, grant writing, health literacy, campaign planning, and content review.

Data Sources: Local health department operational needs, communication materials, grant narratives, public health campaign content, health literacy materials, and staff questions about responsible AI use.

Workflow Impact: Local health departments can use the roadmap and tools to move from informal experimentation toward structured, governed use of GenAI in communications and administrative workflows.

Outcomes: The primary documented outcome is the availability of a roadmap, tools, and community-of-practice support for Kansas local health departments. The page should not claim implementation impact until local deployment outcomes are publicly documented.

Ethical/Privacy: Risk controls should address privacy, source verification, human review, accessibility, health literacy, transparency, and whether generated content is appropriate for public-facing communication.

Kansas Public Health Collaborative: AI in Public Health

Kansas Health Institute: Why and How Kansas Public Health Could Be Key in Shaping a Statewide AI Roadmap

## Egyptian Health Department Agentic Operations Platform

Challenge: A regional public health and human services agency needed to coordinate screenings, referrals, client information, reporting, and program workflows across public health and human services operations.

AI Solution: The agency implemented Creatio's CRM platform, described by the vendor as supporting automation and AI-ready operations for care coordination, reporting, eligibility validation, client portals, and population health workflows.

Data Sources: Client records, screenings, referrals, care coordination information, portal interactions, reporting data, claims or population health data, and program workflow records.

Workflow Impact: The platform centralizes client and program workflows so staff can coordinate referrals, manage screenings, generate reports, and prepare for future AI-assisted risk identification or forecasting within a unified operational system.

Outcomes: The vendor case study reports reduced manual data entry, faster reporting, and improved operational coordination. Because the main source is a vendor case study, the website presents this as an operational example rather than a validated best practice.

Ethical/Privacy: Governance should address vendor oversight, privacy, role-based access, data minimization, audit logs, explainability for future AI analytics, human review of eligibility or risk outputs, and compliance with health and human services data requirements.

Creatio: Public Health Agency Cuts TCO by 50% and Improves Client Outcomes with Creatio

Egyptian Health Department: About Us

## Outbreak Early Warning and Investigation Support

Challenge: A state health department needed to identify potential infectious disease outbreaks more quickly using multiple data streams, including syndromic surveillance, laboratory reports, and emergency department chief complaints. Manual review processes delayed detection and limited the department's ability to identify geographic clusters early enough for timely investigation.

AI Solution: The department used machine learning to detect unusual patterns and potential geographic clusters that could indicate an emerging outbreak. The system was designed as a human-in-the-loop decision-support tool. It flagged potential clusters for review by epidemiologists, but it did not automatically issue public notifications, initiate enforcement actions, or make final outbreak determinations.

Data Sources: The system used syndromic surveillance data, laboratory reports, emergency department chief complaints, geographic data, and related public health surveillance records. During readiness assessment, the department identified a 48-hour lag in syndromic surveillance reporting and addressed that gap through a data pipeline improvement before launching the pilot.

Workflow Impact: The AI system shifted the department from primarily manual review toward earlier automated signal detection followed by human investigation. Epidemiologists received prioritized cluster alerts instead of manually scanning multiple data sources. This allowed staff to focus time on validating signals, contacting local partners, and determining whether additional public health action was needed.

Outcomes: In the first year, the system detected three potential outbreak clusters that were later confirmed through investigation. Average detection time decreased by 4 days compared with the department's previous manual review process. The system improved situational awareness while preserving human judgment in all investigation and response decisions.

Ethical/Privacy: The department established clear guardrails before implementation. The AI system could only flag geographic clusters for human review and could not trigger automatic public alerts or enforcement actions. Community engagement surfaced concerns from immigrant communities about data use, leading the department to add explicit language to its AI principles prohibiting the use or sharing of individual-level data for law enforcement purposes.

How It Could Become Agentic: The system could evolve into an agentic AI workflow by allowing the AI to take defined, bounded actions after a potential cluster is detected. For example, the AI could automatically gather supporting laboratory, syndromic, emergency department, and geographic data; generate a preliminary investigation brief; compare the signal against historical baselines; create a draft case investigation ticket; recommend next investigation steps; and route the alert to the appropriate epidemiology team based on geography, disease category, or staffing availability. The AI could also monitor incoming data after the alert is created and update the investigation brief as new information becomes available. Human epidemiologists would still review the evidence, validate the signal, approve any external communications, and decide whether public health action is warranted. Additional safeguards would be needed, including role-based permissions, audit logs for every AI-initiated action, human approval before external communication, limits on what data the AI can access, and explicit prohibitions on enforcement or law enforcement uses.

Source Basis: Syndromic surveillance uses emergency department and other near-real-time data to detect unusual patterns before confirmed diagnoses are available, and AI/machine learning methods are increasingly discussed as tools for forecasting, anomaly identification, and outbreak detection.

## Tribal Chronic Disease Risk Stratification for Care Management

Challenge: A tribal health department needed a more systematic way to identify tribal members at elevated risk for type 2 diabetes complications and prioritize care management outreach. Existing outreach processes relied heavily on manual review and did not consistently identify the members who could benefit most from early intervention.

AI Solution: The department used AI-assisted risk stratification to identify tribal members at higher risk for diabetes-related complications. The tool supported, but did not replace, clinical and care management judgment. Tribal health staff used the risk scores to prioritize outreach, review individual needs, and determine appropriate follow-up.

Data Sources: The model used tribal health department data, including clinical records, diabetes-related indicators, care management records, utilization history, demographic information, and other locally governed data sources approved for use by tribal leadership. All data remained under tribal jurisdiction.

Workflow Impact: The AI tool helped care management staff move from broad, manual outreach lists to more targeted outreach based on risk level. Staff could prioritize members most likely to benefit from follow-up, review each case, and coordinate outreach through existing tribal health workflows. The system supported earlier intervention while keeping decisions and outreach activities within the tribal health department.

Outcomes: Care management outreach rates increased by 35% among high-risk members. The project improved the department's ability to identify and engage members at elevated risk for diabetes complications. The governance model was also shared with other tribal health departments as an example of how AI oversight can be adapted to a tribal sovereignty context.

Ethical/Privacy: The department's AI principles explicitly recognized tribal sovereignty and data governance. All data remained under tribal jurisdiction, and no data could be shared with state or federal systems without explicit tribal council approval. AI tools were operated only by tribal health staff. Governance oversight was assigned to the tribal council, with reporting to the tribal health board rather than to a state health department.

How It Could Become Agentic: The system could evolve into an agentic AI workflow by allowing the AI to support defined care management tasks under tribal health staff supervision. For example, the AI could identify members whose risk scores have increased, prepare a prioritized outreach list, generate a draft care management summary for staff review, suggest culturally appropriate outreach scripts, recommend follow-up intervals, and create internal task reminders for care managers. The AI could also monitor whether follow-up visits, lab tests, referrals, or education sessions were completed and flag cases that require additional attention. Tribal health staff would retain authority over outreach decisions, care planning, member communication, and any referrals or clinical actions. Additional controls would be needed, including tribal approval of allowable AI actions, audit logs, human review before member contact, culturally grounded communication standards, opt-out processes where appropriate, and strict limits preventing the AI from sharing data outside tribal governance structures.

Source Basis: Diabetes remains a major public health priority in American Indian and Alaska Native communities, and community-based outreach and care models have been used to support people living with type 2 diabetes. Tribal data sovereignty guidance emphasizes that Tribes have authority over the collection, ownership, application, sharing, and interpretation of their data, including health data.

# Resources and Bibliography

## Responsible AI and Federal Guidance

European Commission High-Level Expert Group on Artificial Intelligence. (2019). Ethics guidelines for trustworthy AI.: Trustworthy AI ethics guidelines.

Association of Schools and Programs of Public Health. (2026). Harnessing innovation: Artificial intelligence for academic public health. A framework for the responsible and ethical use of artificial intelligence in public health education, research, and practice.: ASPPH AI framework report with recommendations on human-centered AI, AI literacy, bridge professionals, missing voices analysis, public transparency, policy architecture, and governance.

NIST AI Risk Management Framework (AI RMF 1.0): Anchor framework for agency AI vision, principles, risk management, and credibility with federal funders.

National Institute of Standards and Technology. (2023). Artificial intelligence risk management framework (AI RMF 1.0).: NIST AI Risk Management Framework citation from the source bibliography.

HHS AI use case inventory requirements: Governance guidance for maintaining and reporting AI use case inventories.

CDC STLT resources: Evolving guidance for state, territorial, local, and tribal public health agencies.

FedRAMP-authorized tools and environments: Procurement, security review, and production deployment guidance for AI systems handling sensitive public health data.

HIPAA and Business Associate Agreements: Privacy compliance guidance when protected health information may be processed by vendors, cloud systems, or AI tools.

Office of the National Coordinator for Health Information Technology. (2023). Trusted exchange framework and common agreement (TEFCA).: ONC Trusted Exchange Framework and Common Agreement.

Organisation for Economic Co-operation and Development. (2019). OECD principles on artificial intelligence.: OECD AI principles.

Tribal data sovereignty principles: Required consideration when AI projects involve Tribal communities, Tribal data, or Tribal governance contexts.

White House Office of Science and Technology Policy. (2022). Blueprint for an AI bill of rights: Making automated systems work for the American people.: Blueprint for an AI Bill of Rights.

World Health Organization. (2021). Ethics and governance of artificial intelligence for health.: WHO AI ethics and governance guidance.

World Health Organization. (2023). Regulatory considerations on artificial intelligence for health. Geneva: World Health Organization.: WHO regulatory considerations for AI in health.

Panch, T., Pearson-Stuttard, J., Greaves, F., & Atun, R. (2019). Artificial intelligence: Opportunities and risks for public health. The Lancet Digital Health, 1(1), e13-e14.: AI opportunities and risks for public health.

## Funding Sources

CDC Data Modernization Initiative (DMI): Described as a backbone for AI-ready data infrastructure, interoperability, cloud readiness, APIs, data pipelines, and workforce capacity.

Centers for Disease Control and Prevention. (2023). CDC data modernization initiative.: CDC data modernization source from the source bibliography.

Public Health Infrastructure Grant (PHIG): Described as a flexible funding source for workforce, data systems, organizational capacity, governance, and health equity work.

Centers for Disease Control and Prevention. (2024). Public health infrastructure grant program guidance.: CDC public health infrastructure grant source.

HRSA digital health and telehealth programs: Potential support for patient communication drafting, document search, and health equity analysis.

NIH / NSF smart health programs: Support for research partnerships, model evaluation, public health AI development, and agentic system research.

SAMHSA technology-based services: Relevant to early identification, intervention support, client communication, and care coordination.

EPA environmental justice grants: Relevant to environmental health analysis, GeoAI, and heat risk mapping.

FEMA emergency management grants: Relevant to disaster resilience and agentic outbreak forecasting workflows.

## Public Health Peer Networks and Partners

CDC STLT Data Connection: Peer-learning and community-of-practice connection for public health data modernization and AI capacity building.

Council of State and Territorial Epidemiologists (CSTE): National partner and peer-learning network for public health AI adoption.

Council of State and Territorial Epidemiologists. (2019). Driving public health in the fast lane: The importance of data modernization.: CSTE data modernization source from the source bibliography.

Association of State and Territorial Health Officials (ASTHO): National partner for agency learning, implementation examples, and peer exchange.

National Association of County and City Health Officials (NACCHO): Peer network for local public health agencies and implementation learning.

## AI Platforms and Model Ecosystem Examples

OpenAI GPT-4 and GPT-4o: Leading large language models available through commercial platforms such as Microsoft Azure OpenAI.

Microsoft Azure OpenAI: Commercially hosted API option that may support enterprise controls and Business Associate Agreement pathways.

Anthropic Claude: Large language model family and Deep Research-capable vendor ecosystem.

Google Gemini and Google Vertex AI: Commercial AI models and hosted AI platforms relevant to public health agency procurement decisions.

Meta Llama: Open-source model option that agencies may consider for controlled or self-managed infrastructure.

Deep Research tools from Google, OpenAI, and Anthropic: Practical agentic capabilities for literature synthesis, legal scans, policy scans, scenario analysis, and comparative program analysis.

## Risk, Validation, and Governance Concepts

Human review and subject matter expert adjudication: Emphasized throughout the playbook for consequential outputs, public-facing content, and AI-assisted decision support.

Equity impact assessment and subgroup monitoring: Core safeguards for preventing or detecting disparate impact across communities and populations.

Hallucination and fabrication audits: Safeguards for generative AI systems used in public-facing or consequential internal products.

Automation bias: Governance risk that occurs when staff reduce scrutiny after repeated exposure to AI outputs.

Model drift and performance monitoring: Sustainment risks requiring ongoing dashboards, audits, and continuous improvement.

## Books, Reports, and Foundational Texts

Barocas, S., Hardt, M., & Narayanan, A. (2019). Fairness and machine learning: Limitations and opportunities. MIT Press.: Fairness and machine learning reference.

Goodfellow, I., Bengio, Y., & Courville, A. (2016). Deep learning. MIT Press.: Deep learning textbook.

National Academies of Sciences, Engineering, and Medicine. (2022). Artificial intelligence in health care: The hope, the hype, the promise, the peril. National Academies Press.: National Academies AI in health care report.

Russell, S., & Norvig, P. (2021). Artificial intelligence: A modern approach (4th ed.). Pearson.: Artificial intelligence textbook.

Topol, E. (2019). Deep medicine: How artificial intelligence can make healthcare human again. Basic Books.: AI and medicine book.

## Journal Articles and Peer-Reviewed Research

Beam, A. L., & Kohane, I. S. (2018). Big data and machine learning in health care. JAMA, 319(13), 1317-1318.: Machine learning in health care.

Birkhead, G. S., Klompas, M., & Shah, N. R. (2015). Uses of electronic health records for public health surveillance to advance public health. Annual Review of Public Health, 36, 345-359.: Electronic health records and public health surveillance.

Buolamwini, J., & Gebru, T. (2018). Gender shades: Intersectional accuracy disparities in commercial gender classification. Proceedings of Machine Learning Research, 81, 1-15.: Bias and accuracy disparities in commercial AI systems.

Chin, M. H., Afsar-Manesh, N., Bierman, A. S., et al. (2023). Guiding principles to address the impact of algorithm bias on racial and ethnic disparities in health and health care. JAMA Network Open, 6(12), e2345050.: Algorithm bias and health disparities.

Esteva, A., Kuprel, B., Novoa, R., et al. (2017). Dermatologist-level classification of skin cancer with deep neural networks. Nature, 542, 115-118.: Deep learning in clinical image classification.

Floridi, L., Cowls, J., Beltrametti, M., et al. (2018). AI4People: An ethical framework for a good AI society. Minds and Machines, 28, 689-707.: AI ethics framework.

Ghassemi, M., Oakden-Rayner, L., & Beam, A. (2021). The false hope of current approaches to explainable artificial intelligence in health care. Lancet Digital Health, 3(11), e745-e750.: Explainable AI in health care critique.

Greenhalgh, T., Wherton, J., Papoutsi, C., Lynch, J., Hughes, G., A'Court, C., Hinder, S., Fahy, N., Procter, R., & Shaw, S. (2017). Beyond adoption: A new framework for theorizing and evaluating nonadoption, abandonment, and challenges to the scale-up, spread, and sustainability of health and care technologies. Journal of Medical Internet Research, 19(11), e367.: Health care technology adoption, abandonment, scale-up, spread, and sustainability.

Jordan, M. I., & Mitchell, T. M. (2015). Machine learning: Trends, perspectives, and prospects. Science, 349(6245), 255-260.: Machine learning trends and prospects.

Kahn, M. G., Brown, J. S., Chun, A. T., Davidson, B. N., Meeker, D., Ryan, P. B., Schilling, L. M., Weiskopf, N. G., Williams, A. E., & Zozus, M. N. (2015). Transparent reporting of data quality in distributed data networks. eGEMs, 3(1), 1052.: Data quality reporting in distributed networks.

LeCun, Y., Bengio, Y., & Hinton, G. (2015). Deep learning. Nature, 521, 436-444.: Deep learning overview.

Mehrabi, N., Morstatter, F., Saxena, N., et al. (2021). A survey on bias and fairness in machine learning. ACM Computing Surveys, 54(6).: Bias and fairness survey.

Miotto, R., Wang, F., Wang, S., Jiang, X., & Dudley, J. (2017). Deep learning for healthcare: Review, opportunities and challenges. Briefings in Bioinformatics, 19(6), 1236-1246.: Deep learning for health care review.

Obermeyer, Z., Powers, B., Vogeli, C., & Mullainathan, S. (2019). Dissecting racial bias in an algorithm used to manage the health of populations. Science, 366(6464), 447-453.: Racial bias in health population management algorithms.

Rajkomar, A., Dean, J., & Kohane, I. (2019). Machine learning in medicine. New England Journal of Medicine, 380(14), 1347-1358.: Machine learning in medicine.

Shilo, S., Rossman, H., & Segal, E. (2020). Axes of a revolution: Challenges and promises of big data in healthcare. Nature Medicine, 26, 29-38.: Big data in health care.

Vespignani, A., et al. (2020). Modelling COVID-19. Nature Reviews Physics, 2, 279-281.: COVID-19 modeling.

# In the News

Curated developments in generative and agentic AI that may affect state, territorial, local, and tribal public health departments.

## Colorado lawmakers introduce new AI rules for automated decisions

Source: Axios Denver. Date: May 3, 2026. Category: State AI Legislation.

Colorado lawmakers introduced a replacement framework for the state's AI law that would regulate automated decision-making in areas including health care, insurance, employment, housing, education, and financial services.

Why it matters for public health: Public health departments should watch this because state AI rules may affect procurement, vendor documentation, human review, data correction rights, risk review, and the use of AI in eligibility, services, inspections, case management, and health programs.

Original source

## New York lawmakers consider guardrails for high-risk AI decisions

Source: Times Union. Date: January 15, 2026. Category: State AI Legislation.

New York lawmakers examined proposed AI rules for high-risk decision-making, including requirements related to discrimination prevention, audits, transparency, and human review in sectors such as health care, housing, employment, and public services.

Why it matters for public health: Relevant to health departments because similar state bills could require documented risk controls, bias review, appeal pathways, human oversight, and audit-ready records when AI supports public health decisions or services.

Original source

## New York legislature advances several AI regulation bills

Source: Times Union. Date: June 4, 2026. Category: State AI Legislation.

New York lawmakers moved multiple AI bills near the end of session, including measures focused on AI training data transparency, chatbot risks, workforce impacts, and AI-generated media disclosure.

Why it matters for public health: Public health departments should monitor these types of bills because they may affect staff training, chatbot use, workforce planning, public communications, transparency expectations, and records needed for AI-supported workflows.

Original source

## Federal AI draft could override some state AI laws

Source: Axios. Date: June 4, 2026. Category: State AI Legislation.

A bipartisan House discussion draft for a national AI framework would preempt some state AI laws while adding provisions related to AI whistleblowers, fraud penalties, AI literacy, education, and research.

Why it matters for public health: This matters for public health departments tracking state AI obligations because federal preemption proposals could change whether departments follow state-specific rules, federal requirements, or both.

Original source

## California announces discounted Claude access for state government

Source: TechRadar. Date: June 30, 2026. Category: Government AI.

California announced a statewide arrangement to make Claude available to government agencies at reduced cost, reinforcing the need for procurement, access controls, approved-use guidance, and workforce training before broad GenAI access expands.

Why it matters for public health: Useful for public health departments thinking about enterprise AI access, member permissions, role-based guidance, and how state-level procurement decisions may affect local implementation.

Original source

## FDA launches agencywide AI tool

Source: Axios. Date: June 2, 2025. Category: Federal Health AI.

FDA introduced an internal AI tool for agencywide use, showing how health agencies are moving from experimentation toward enterprise AI environments with governance, acceptable-use boundaries, and operational support.

Why it matters for public health: Helpful context for health departments planning approved AI environments, staff guidance, and governance review for internal AI assistants.

Original source

## California inspection report search tool uses AI-assisted public records workflows

Source: San Francisco Chronicle. Date: December 22, 2025. Category: Transparency and Inspection Data.

A newsroom project used AI-supported search and document processing to make California health facility inspection reports easier to find and analyze, illustrating public demand for clearer access to complex regulatory information.

Why it matters for public health: Relevant to public health teams considering AI-supported inspection documentation, regulatory linkage, document search, public transparency, and quality review workflows.

Original source

## Opportunities and risks of generative AI across the health information journey

Source: arXiv. Date: May 21, 2026. Category: Evidence and Risk.

This paper examines how generative AI may affect the health information journey, including possible benefits and risks across information creation, interpretation, access, and use.

Why it matters for public health: Supports learning modules on responsible prompting, evidence review, misinformation risk, communication quality, and human review.

Original source

## Agentic AI governance and lifecycle management in healthcare

Source: arXiv. Date: January 22, 2026. Category: Agentic AI Governance.

This paper focuses on governance and lifecycle management for agentic AI in healthcare, including oversight needs when systems can plan, act, monitor, and adapt within defined boundaries.

Why it matters for public health: Useful for public health governance, system inventory, monitoring, incident response, role permissions, and organization-level accountability design.

Original source

## HIPAA-compliant agentic AI system design in healthcare

Source: arXiv. Date: April 24, 2025. Category: Privacy and Security.

This paper discusses design considerations for agentic AI systems in healthcare environments where privacy, auditability, and compliance controls are central.

Why it matters for public health: Helpful for departments reviewing privacy safeguards, approved environments, audit logs, data minimization, and vendor or architecture requirements.

Original source